## 2 · RFC PROGRESS
PS5 COMPLETION PLATFORM ¦ 2 · RFC PROGRESS
SUB SYSTEM | PRIO | RFC BHM | RFC EIT | BASE | RECOV | SIGNED | MILESTONE | TOT% | B |  |  | E |  |  | H |  |  | I |  |  | M |  |  | P |  |  | S |  |  | T |  |  | ITRs | CL | BAL | ITR% | CPP-1 | EIT | EACOP | REMARK EACOP | REMARK CPP-EIT | REMARK CPP-1 | WALKDOWN | ● | MY NOTES
[9 empty] | T | CL | % | T | CL | % | T | CL | % | T | CL | % | T | CL | % | T | CL | % | T | CL | % | T | CL | %
PS5-01-01 - Fire Water Jockey Pump A/B | 1.1 | Yes | 08-Sep-26 | 2026-09-08 00:00:00 | 2026-09-09 | Full | DONE(partial) | 98% | 0 | 12 | 0 | 40 | 6 | 28 | 0 | 0 | 0 | - | [14 empty] | 86 | 84 | 2 | 98% | 0 | 0 | 0 | 0
PS5-01-02 - Fire Water Pump A | 1.1 | Yes | E,I,M,P | 2026-09-07 00:00:00 | 2026-09-09 | Full | Partial | 96% | 0 | 6 | 0 | 27 | 3 | 49 | 0 | 0 | 0 | - | [14 empty] | 85 | 82 | 3 | 96% | 0 | 0 | 0 | 0 |  | EACOP(MR.BENHER TBC)-EXPECTED 19-08-2026
PS5-01-03 - Fire Water Pump B | 1.1 | Yes | E,I,M,P | 2026-09-08 00:00:00 | 2026-09-09 | Full | Partial | 96% | 0 | 6 | 0 | 23 | 3 | 44 | 0 | 0 | 0 | - | [14 empty] | 76 | 73 | 3 | 96% | 0 | 0 | 0 | 0
PS5-01-04 - Fire Water Pump Mini Flow Recycle | 1.1 | Yes | P | 2026-09-08 00:00:00 | 2026-09-09 | Full |  | 100% | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | - | [14 empty] | 8 | 8 | 0 | 100% | 0 | 0 | 0 | 0
PS5-01-05 - Foam Skid | 2 | Yes | E,I,M,P | 2026-09-16 00:00:00 | 2026-10-02 | Full | PS5 - Milestone F | 100% | 0 | 9 | 0 | 7 | 3 | 9 | 0 | 0 | 0 | - | [14 empty] | 28 | 28 | 0 | 100% | 0 | 0 | 0 | 0
PS5-01-06 - Foam Concentrate Distribution | 2 | Yes | P | 2026-09-16 00:00:00 | 2026-09-15 | Full |  | 100% | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | - | [14 empty] | 8 | 8 | 0 | 100% | 0 | 0 | 0 | 0
PS5-01-07 - Fire Water Ring Main & Distribution | 2 | Yes | I,P,S | 2026-10-08 00:00:00 | 2026-11-05 | - |  | 96% | 0 | 0 | 0 | 16 | 0 | 87 | 29 | 0 | 0 | - | [14 empty] | 132 | 127 | 5 | 96% | 0 | 0 | 0 | 0
PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | 2 | Yes | E,I,M,P,S | 2026-10-09 00:00:00 | TBC | - | Full | 98% | 0 | 3 | 0 | 7 | 2 | 34 | 8 | 0 | 0 | - | [14 empty] | 54 | 53 | 1 | 98% | 0 | 0 | 0 | 0
PS5-01-09 - Inergen for EITS Building | 1 | Yes | P | Complete |  | 2026-08-08 |  | 100% | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | - | [14 empty] | 2 | 2 | 0 | 100% | 0 | 0 | 0 | 0
PS5-01-10 - Water Mist Package | 1.1 | Yes | E,I,M,P | 2026-09-12 00:00:00 | 2026-09-19 | Full | Full | 100% | 0 | 5 | 0 | 44 | 2 | 47 | 0 | 0 | 0 | - | [14 empty] | 98 | 98 | 0 | 100% | 0 | 0 | 0 | 0
PS5-01-11 - Inergen for Power Gen Building | 1.1 | Yes | E,I,M,P | 2026-09-01 00:00:00 | 2026-10-16 | FULL | full | 100% | 0 | 7 | 0 | 74 | 2 | 2 | 0 | 0 | 0 | - | [14 empty] | 85 | 85 | 0 | 100% | 0 | 0 | 14 | 0
PS5-02-01 - Miscellaneous Safety equipment | 3 | Yes | E,M,S | 2026-10-25 00:00:00 | TBC | - |  | 61% | 0 | 4 | 0 | 0 | 3 | 0 | 59 | 0 | 0 | - | [14 empty] | 66 | 40 | 26 | 61% | 0 | 0 | 0 | 0
PS5-02-02 - Portable Fire Fighting Equipments | 3 | Yes | M,S | 2026-10-03 00:00:00 | TBC | - |  | 1% | 0 | 0 | 0 | 0 | 1 | 0 | 76 | 0 | 0 | - | [14 empty] | 77 | 1 | 76 | 1% | 0 | 0 | 0 | 0
PS5-03-01 - FZ-01 - Process Area | 2 | Yes | E,I | N/A | 2026-09-25 | - | Full | 100% | 0 | 8 | 0 | 143 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 151 | 151 | 0 | 100% | 0 | 0 | 0 | 0
PS5-03-03 - FZ-03 - Buildings Area | 5 | Yes | I | N/A |  | - |  | 6% | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 16 | 1 | 15 | 6% | 0 | 0 | 0 | 0
PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 1.1 | Yes | E,I | N/A | 2026-09-15 | - | Partial | 94% | 0 | 1 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 34 | 32 | 2 | 94% | 0 | 0 | 0 | 0
PS5-03-06 - FZ-06 - Transformer Area | 2 | Yes | I | N/A | 2026-09-25 | - | Full | 100% | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 62 | 62 | 0 | 100% | 0 | 0 | 0 | 0
PS5-03-07 - FZ-07 - Pretreatment Area | 2 | Yes | I | N/A | 2026-09-28 | - | Full | 100% | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 23 | 23 | 0 | 100% | 0 | 0 | 0 | 0
PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2 | Yes | I | N/A | 2026-10-10 | - | Full | 98% | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 47 | 46 | 1 | 98% | 0 | 0 | 0 | 0
PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 1 | Yes | I | N/A | 2026-09-22 | - | Full | 100% | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 62 | 62 | 0 | 100% | 0 | 0 | 0 | 0
PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 1.1 | Yes | I | N/A | 2026-09-23 | - | Full | 100% | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 64 | 64 | 0 | 100% | 0 | 0 | 0 | 0
PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2 | Yes | I | N/A | 2026-10-03 | full | full | 100% | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 64 | 64 | 0 | 100% | 0 | 0 | 0 | 0
PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | 2 | Yes | I | N/A | 2026-10-08 | - | Full | 100% | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 35 | 35 | 0 | 100% | 0 | 0 | 0 | 0
PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | 1.1 | Yes | I | N/A | 2026-09-15 | - | Full | 100% | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 12 | 12 | 0 | 100% | 0 | 0 | 0 | 0
PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 1 | Yes | E,I,M,T | complete | HOLD/meterial issue | - |  | 51% | 0 | 6 | 0 | 68 | 1 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 77 | 39 | 38 | 51% | 0 | 0 | 24 | 0
PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | 1 | Yes | I | N/A | HOLD/meterial issue | - |  | 0% | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 6 | 0
PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | 1.1 | Yes | I | N/A | HOLD/meterial issue | - |  | 0% | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 6 | 0
PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | 2 | Yes | I | N/A | 2026-11-05 | - |  | 0% | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 0 | 0
PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | 2 | Yes | I | N/A | 2026-11-05 | - |  | 0% | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 0 | 0
PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | 1 | Yes | I | N/A | HOLD/meterial issue | - |  | 0% | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 6 | 0
PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | 1 | Yes | I | N/A |  | 07-Aug-26 | Full | 100% | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 5 | 0 | 100% | 0 | 0 | 0 | 0
PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | 3 | Yes | I | N/A |  | - |  | 0% | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 0 | 0
PS5-03-22 - FZ-G1 - Guard House | 5 | No | E,I | N/A |  | - |  | 0% | 0 | 2 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 0 | 11 | 0% | 0 | 0 | 0 | 0
PS5-03-23 - FZ-E1 to E3 - EITS Building | [5 empty] | - |  | 99% | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 96 | 95 | 1 | 99% | 0 | 0 | 0
PS5-03-24 - FZ - Office and Facilities Building | 5 | No | I | N/A |  | - |  | 0% | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 120 | 0 | 120 | 0% | 0 | 0 | 0 | 0
PS5-03-25 - FZ - Workshop & Warehouse | 5 | No | I | N/A |  | - |  | 0% | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 120 | 0 | 120 | 0% | 0 | 0 | 0 | 0
PS5-04-01 - Office Building PCS System | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | [14 empty] | 3 | 0 | 3 | 0% | 0 | 0 | 0
PS5-04-02 - Office Building SIS/FGS System | 5 | No | I | N/A |  | - |  | 0% | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 0 | 0
PS5-04-03 - 33kV ICSS System | [5 empty] | - |  | 99% | 0 | 12 | 0 | 5 | 0 | 0 | 0 | 65 | 65 | 100% | [14 empty] | 82 | 81 | 1 | 99% | 0 | 0 | 0
PS5-04-04 - 33kV PCS System | [5 empty] | - |  | 99% | 0 | 69 | 0 | 325 | 0 | 0 | 0 | 9 | 9 | 100% | [14 empty] | 403 | 397 | 6 | 99% | 0 | 0 | 0
PS5-04-05 - 33kV SIS/FGS System | [5 empty] | - |  | 97% | 0 | 177 | 0 | 276 | 0 | 0 | 0 | 19 | 19 | 100% | [14 empty] | 472 | 460 | 12 | 97% | 0 | 0 | 0
PS5-05-01 - Emergency Diesel Generator Package | 1 | 9 | E,I,M,P | complete |  | PARTIAL | Full | 100% | 0 | 70 | 0 | 36 | 2 | 1 | 0 | 0 | 0 | - | [14 empty] | 109 | 109 | 1 | 100% | 0 | 0 | 0 | 0
PS5-05-02 - Emergency Diesel Generator Package (UCP) | 1 | Yes | E,I | N/A |  | COMPLETE | Full | 100% | 0 | 51 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 53 | 53 | 0 | 100% | 0 | 0 | 0 | 0
PS5-06-01 - AC UPS - EITS Building | [5 empty] | - |  | 99% | 0 | 152 | 0 | 19 | 0 | 0 | 0 | 12 | 12 | 100% | [14 empty] | 183 | 182 | 1 | 99% | 0 | 0 | 0
PS5-06-02 - AC UPS - Power Generator Building | 1 | Yes | E,I | N/A | 2026-08-24 | - | Full | 100% | 0 | 60 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 62 | 62 | 0 | 100% | 0 | 0 | 0 | 0
PS5-06-03 - AC UPS - Office & Facilities Building | 5 | No | E | N/A |  | - |  | 0% | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 8 | 0 | 8 | 0% | 0 | 0 | 0 | 0
PS5-06-04 - AC UPS - Guard House | 5 | No | E | N/A |  | - |  | 0% | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 2 | 0 | 2 | 0% | 0 | 0 | 0 | 0
PS5-06-05 - AC UPS - Workshop & Warehouse | 5 | No | E | N/A |  | - |  | 0% | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0 | 0
PS5-08-01 | 3 | Partially | T | N/A |  | - |  | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 0 | 0 | 0 | - | 0 | 0 | 0 | 0
PS5-08-01a - PAGA (Required for SU) | [5 empty] | - |  | 9% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 9 | 9% | [14 empty] | 96 | 9 | 87 | 9% | 0 | 0 | 0
PS5-08-01b - PAGA (Not required for SU) | [5 empty] | - |  | 2% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 3 | 2% | [14 empty] | 134 | 3 | 131 | 2% | 0 | 0 | 0
PS5-08-03 - Telephone | 4 | No | T | N/A |  | - |  | 22% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 4 | 22% | [14 empty] | 18 | 4 | 14 | 22% | 0 | 0 | 0 | 0
PS5-08-04 - Hotline | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0% | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0
PS5-08-07 - Multi-Channel Voice Recorder | [5 empty] | - |  | 0% | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0
PS5-08-11 - Corporate LAN (SIE) | 3 | Yes | E | N/A |  | - |  | 88% | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 8 | 7 | 1 | 88% | 0 | 0 | 0 | 0
PS5-08-12 - Corporate Wireless LAN (SIE) | 3 | No | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0% | [14 empty] | 34 | 0 | 34 | 0% | 0 | 0 | 0 | 0
PS5-08-13 - Safety Data Network (SII SP3 SAF) | 3 | No | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0% | [14 empty] | 13 | 0 | 13 | 0% | 0 | 0 | 0 | 0
PS5-08-14 - Industrial Data Network (SII SP1) | 4 | No | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0% | [14 empty] | 12 | 0 | 12 | 0% | 0 | 0 | 0 | 0
PS5-08-15 - Security Data Network (SII SP3 SEC) | 4 | No | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0% | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 0 | 0
PS5-08-23 - VHF Trunk Radio System | 4 | Yes | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0% | [14 empty] | 11 | 0 | 11 | 0% | 0 | 0 | 0 | 0
PS5-08-34 - Satphone | 4 | Yes | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0% | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0 | 0
PS5-08-35 - Optical Transport Network | [5 empty] | - |  | 87% | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 46 | 40 | 87% | [14 empty] | 61 | 53 | 8 | 87% | 0 | 0 | 0
PS5-08-36 - Pipeline FO Cable & EPRS | 3 | No | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | [14 empty] | 2 | 0 | 2 | 0% | 0 | 0 | 0 | 0
PS5-08-51 - Entertainment | 4 | No | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0% | [14 empty] | 18 | 0 | 18 | 0% | 0 | 0 | 0 | 0
PS5-08-52a - Process & Security CCTV (Required for SU) | [5 empty] | - |  | 0% | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0% | [14 empty] | 51 | 0 | 51 | 0% | 0 | 0 | 0
PS5-08-52b - Process & Security CCTV (Not required for SU) | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0% | [14 empty] | 23 | 0 | 23 | 0% | 0 | 0 | 0
PS5-08-55 - Videoconference | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0% | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-08-61 - Meteocean | 4 | No | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0% | [14 empty] | 10 | 0 | 10 | 0% | 0 | 0 | 0 | 0
PS5-08-71 - Structured Cabling (CAT6) | 4 | Yes | T | N/A |  | - |  | 4% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 10 | 4% | [14 empty] | 250 | 10 | 240 | 4% | 0 | 0 | 0 | 0
PS5-08-72 - Structured Cabling (FO) | 3 | Yes | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0% | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0 | 0
PS5-08-81 - Guard tour | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0% | [14 empty] | 12 | 0 | 12 | 0% | 0 | 0 | 0
PS5-08-82 - Key Management | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0% | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0
PS5-08-83 - Perimeter & Pipeline intrusion detection system | 4 | No | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | [14 empty] | 2 | 0 | 2 | 0% | 0 | 0 | 0 | 0
PS5-08-85 | 4 | Yes | E,T | N/A |  | - |  | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 50% | [14 empty] | 2 | 1 | 1 | 50% | 0 | 0 | 0 | 0
PS5-08-85a - Access Control, POB & e-Mustering (Required for SU) | [5 empty] | - |  | 7% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 6 | 7% | [14 empty] | 92 | 6 | 86 | 7% | 0 | 0 | 0
PS5-08-85b - Access Control, POB & e-Mustering (Not required for SU) | [5 empty] | - |  | 12% | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 151 | 19 | 13% | [14 empty] | 157 | 19 | 138 | 12% | 0 | 0 | 0
PS5-08-86 - Integrated Security Management System | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0% | [14 empty] | 16 | 0 | 16 | 0% | 0 | 0 | 0
PS5-08-92 - Telecom Mast | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | [14 empty] | 2 | 0 | 2 | 0% | 0 | 0 | 0
PS5-08-93 - Telecom Monitoring System | 4 | No | T | N/A |  | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | [14 empty] | 1 | 0 | 1 | 0% | 0 | 0 | 0 | 0
PS5-09-01 - HVAC for Office and Facilities building | 5 | No | H,I | 2026-12-15 00:00:00 |  | - |  | 0% | 0 | 0 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 29 | 0 | 29 | 0% | 0 | 0 | 0 | 0
PS5-09-02 - HVAC for Guard House | 5 | No | E | N/A |  | - |  | 0% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0 | 0
PS5-09-03 - HVAC for Generator Building | 2 | Yes | E,H,I,M,T | 2026-10-10 00:00:00 | 2026-11-15 | - |  | 18% | 0 | 380 | 93 | 620 | 9 | 0 | 0 | 4 | 0 | 0% | [14 empty] | 1106 | 194 | 912 | 18% | 0 | 0 | 0 | 3
PS5-09-04 - HVAC for Workshop & Warehouse | 5 | No | H,I | 2026-12-20 00:00:00 |  | - |  | 0% | 0 | 0 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 20 | 0 | 20 | 0% | 0 | 0 | 0 | 0
PS5-09-05 - HVAC for EITS Building | 1 | Yes | H,M | 2026-10-11 00:00:00 |  | Full |  | 100% | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 5 | 0 | 100% | 0 | 0 | 3 | 0
PS5-0H-01 - HIPPS | [5 empty] | - |  | 86% | 0 | 11 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 28 | 24 | 4 | 86% | 0 | 0 | 0
PS5-25-01 - Export Pipeline Pig Receiver | 3 | Yes | E,I,M,P | 2026-10-25 00:00:00 |  | Full |  | 95% | 0 | 15 | 0 | 84 | 2 | 46 | 0 | 0 | 0 | - | [14 empty] | 147 | 140 | 7 | 95% | 0 | 0 | 0 | 1
PS5-25-02 - Crude Oil Export Pump A | 3 | Yes | E,I,M,P | 2026-10-26 00:00:00 |  | Full |  | 87% | 0 | 95 | 0 | 95 | 9 | 24 | 0 | 0 | 0 | - | [14 empty] | 223 | 195 | 28 | 87% | 0 | 0 | 0 | 0
PS5-25-03 - Crude Oil Export Pump B | 3 | Yes | E,I,M,P | 2026-10-27 00:00:00 |  | Full |  | 97% | 0 | 92 | 0 | 95 | 9 | 24 | 0 | 0 | 0 | - | [14 empty] | 220 | 213 | 7 | 97% | 0 | 0 | 0 | 0
PS5-25-04 - Crude Oil Export Pump C | 3 | Yes | E,I,M,P | 2026-10-28 00:00:00 |  | Full |  | 97% | 0 | 92 | 0 | 95 | 9 | 24 | 0 | 0 | 0 | - | [14 empty] | 220 | 213 | 7 | 97% | 0 | 0 | 0 | 0
PS5-25-05 - Crude Oil Export Pumps Bypass | 3 | Yes | E,I,P | 2026-10-28 00:00:00 |  | Full | full | 100% | 0 | 6 | 0 | 33 | 0 | 9 | 0 | 0 | 0 | - | [14 empty] | 48 | 48 | 0 | 100% | 0 | 0 | 0 | 0
PS5-25-06 - Crude Oil Export Pumps Discharge | 3 | Yes | E,I,P | 2026-10-29 00:00:00 |  | Full |  | 93% | 0 | 5 | 0 | 32 | 0 | 19 | 0 | 0 | 0 | - | [14 empty] | 56 | 52 | 4 | 93% | 0 | 0 | 0 | 0
PS5-25-07 - Export Pipeline Pig Launcher | 3 | Yes | E,I,M,P | 2026-10-29 00:00:00 |  | Full |  | 96% | 0 | 12 | 0 | 73 | 3 | 35 | 0 | 0 | 0 | - | [14 empty] | 123 | 118 | 5 | 96% | 0 | 0 | 0 | 0
PS5-28-01 - Closed Drain Header 1 | 3 | Yes | P | 2026-10-30 00:00:00 | 2026-10-13 | full |  | 93% | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | - | [14 empty] | 14 | 13 | 1 | 93% | 0 | 0 | 0 | 0
PS5-28-02 - Closed Drain Header 2 | 1.1 | Yes | P | 2026-09-01 00:00:00 | 2026-09-11 | Full |  | 100% | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | - | [14 empty] | 15 | 15 | 0 | 100% | 0 | 0 | 0 | 0
PS5-28-03 - Closed Drain Drum and Pump 01 | 3 | Yes | E,I,M,P | 2026-10-31 00:00:00 | 2026-11-12 | FULL | partial | 98% | 0 | 10 | 0 | 35 | 3 | 56 | 0 | 0 | 0 | - | [14 empty] | 104 | 102 | 2 | 98% | 0 | 0 | 0 | 0
PS5-28-04 - Closed Drain Drum and Pump 02 | 1.1 | Yes | E,I,M,P | 2026-09-07 00:00:00 | 2026-10-22 | Full | Partial | 96% | 0 | 14 | 0 | 38 | 7 | 46 | 0 | 0 | 0 | - | [14 empty] | 105 | 101 | 4 | 96% | 0 | 0 | 4 | 0
PS5-28-05 - HP Relief Header | 2 | Yes | I,P | 2026-09-15 00:00:00 | 2026-09-25 | Full | Full | 100% | 0 | 0 | 0 | 2 | 0 | 9 | 0 | 0 | 0 | - | [14 empty] | 11 | 11 | 0 | 100% | 0 | 0 | 0 | 0
PS5-28-06 - Relief Drum and Pump | 2 | Yes | E,I,M,P | 2026-09-21 00:00:00 | 2026-10-02 | Full | Full | 100% | 0 | 4 | 0 | 20 | 4 | 36 | 0 | 0 | 0 | - | [14 empty] | 64 | 64 | 0 | 100% | 0 | 0 | 0 | 0
PS5-28-07 - Open Drains (OD2) | 3 | Yes | E,I,P | 2026-11-01 00:00:00 | 2026-10-30 | - |  | 100% | 0 | 2 | 0 | 3 | 0 | 273 | 0 | 0 | 0 | - | [14 empty] | 278 | 278 | 0 | 100% | 0 | 0 | 0 | 0
PS5-28-08 - Open Drain Sump and Pumps | 2 | Yes | E,I,M,P | 2026-10-03 00:00:00 | 2026-10-10 | partial | full | 99% | 0 | 14 | 0 | 18 | 9 | 29 | 0 | 0 | 0 | - | [14 empty] | 70 | 69 | 1 | 99% | 0 | 0 | 0 | 0
PS5-28-09 - Observation Basin | 3 | Yes | P | 2026-11-03 00:00:00 |  | - |  | 93% | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | - | [14 empty] | 14 | 13 | 1 | 93% | 0 | 0 | 0 | 0
PS5-28-10 - Oil Skimmer Package | 3 | Yes | E,I,M | 2026-11-03 00:00:00 |  | - |  | 45% | 0 | 8 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 5 | 6 | 45% | 0 | 0 | 0 | 0
PS5-28-11 - Open Drain Interceptor | 3 | Yes | E,I,M,P | 2026-10-20 00:00:00 | 2026-10-16 | FULL | FULL | 100% | 0 | 2 | 0 | 2 | 1 | 8 | 0 | 0 | 0 | - | [14 empty] | 13 | 13 | 0 | 100% | 0 | 0 | 0 | 0
PS5-28-12 - Open Drains (OD3) | 3 | Yes | P | 2026-10-21 00:00:00 | 2026-11-07 | - |  | 100% | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 0 | - | [14 empty] | 43 | 43 | 0 | 100% | 0 | 0 | 0 | 0
PS5-28-13 - Seal Oil Drain Drum & Pump A | 3 | Yes | E,I,M,P | 2026-10-15 00:00:00 | 2026-10-22 | FULL | Full | 100% | 0 | 6 | 0 | 24 | 3 | 35 | 0 | 0 | 0 | - | [14 empty] | 68 | 68 | 0 | 100% | 0 | 0 | 0 | 0
PS5-28-14 - Seal Oil Drain Drum & Pump B | 3 | Yes | E,I,M,P | 2026-09-15 00:00:00 | 2026-10-22 | FULL | Full | 100% | 0 | 6 | 0 | 24 | 3 | 35 | 0 | 0 | 0 | - | [14 empty] | 68 | 68 | 0 | 100% | 0 | 0 | 0 | 0
PS5-28-15 - Seal Oil Drain Drum & Pump C | 3 | Yes | E,I,M,P | 2026-09-15 00:00:00 | 2026-10-28 | FULL | FULL | 100% | 0 | 6 | 0 | 24 | 3 | 35 | 0 | 0 | 0 | - | [14 empty] | 68 | 68 | 0 | 100% | 0 | 0 | 0 | 0
PS5-28-16 - LP Relief Header | 2 | Yes | I,P | 2026-09-16 00:00:00 |  | Full | Full | 100% | 0 | 0 | 0 | 2 | 0 | 9 | 0 | 0 | 0 | - | [14 empty] | 11 | 11 | 0 | 100% | 0 | 0 | 0 | 0
PS5-28-17 - Reinjection Pump | 2 | Yes | E,I,M,P | 2026-10-02 00:00:00 | 2026-10-29 | Full |  | 95% | 0 | 16 | 0 | 37 | 6 | 24 | 0 | 0 | 0 | - | [14 empty] | 83 | 79 | 4 | 95% | 0 | 0 | 0 | 0
PS5-50-01 - Water Well Submersible Pumps (3100) | 4 | Yes | E,I,M,P | 2026-09-18 00:00:00 |  | - |  | 56% | 0 | 5 | 0 | 6 | 1 | 13 | 0 | 0 | 0 | - | [14 empty] | 25 | 14 | 11 | 56% | 0 | 0 | 0 | 0
PS5-50-02 - Water Well Submersible Pumps (3200) | 4 | Yes | E,I,M,P | 2026-09-18 00:00:00 |  | - |  | 56% | 0 | 5 | 0 | 6 | 1 | 13 | 0 | 0 | 0 | - | [14 empty] | 25 | 14 | 11 | 56% | 0 | 0 | 0 | 0
PS5-50-03 - Water Pre-Treatment Package | 2 | Yes | E,I,M,P | 2026-10-06 00:00:00 | 2026-10-30 | - |  | 80% | 0 | 1 | 0 | 7 | 2 | 15 | 0 | 0 | 0 | - | [14 empty] | 25 | 20 | 5 | 80% | 0 | 0 | 0 | 0
PS5-53-01 - Utility Water / Storage Tank | 2 | Yes | E,I,M,P | 2026-10-08 00:00:00 | 2026-09-11 | Partial | Partial | 96% | 0 | 6 | 0 | 10 | 1 | 30 | 0 | 0 | 0 | - | [14 empty] | 47 | 45 | 2 | 96% | 0 | 0 | 0 | 0
PS5-53-02 - Water Distribution Pump A/B | 2 | Yes | E,I,M,P | 2026-10-06 00:00:00 | 2026-10-28 | Full | Full | 100% | 0 | 8 | 0 | 7 | 6 | 8 | 0 | 0 | 0 | - | [14 empty] | 29 | 29 | 0 | 100% | 0 | 0 | 0 | 0
PS5-53-03 - Water Softener Package | 2 | Yes | E,I,M,P | 2026-10-08 00:00:00 | 2026-10-30 | - | Full | 82% | 0 | 1 | 0 | 1 | 1 | 14 | 0 | 0 | 0 | - | [14 empty] | 17 | 14 | 3 | 82% | 0 | 0 | 0 | 0
PS5-53-04 - Water Treatment Purification Package | 2 | No | E,I,M,P | 2026-10-08 00:00:00 | 2026-10-26 | - |  | 45% | 0 | 4 | 0 | 5 | 1 | 1 | 0 | 0 | 0 | - | [14 empty] | 11 | 5 | 6 | 45% | 0 | 0 | 0 | 0
PS5-53-05 - Water Distribution Header | 2 | No | P | 2026-10-05 00:00:00 | 2026-10-02 | Full | Full | 100% | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 0 | 0 | - | [14 empty] | 58 | 58 | 0 | 100% | 0 | 0 | 0 | 0
PS5-53-06 - Water Distribution Consumers | 4 | No | P | 2026-09-02 00:00:00 | 2026-10-24 | - |  | 95% | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | - | [14 empty] | 39 | 37 | 2 | 95% | 0 | 0 | 0 | 0
PS5-60-01 - Power Generation Package A | 1 | Yes | E,I,M,P | 2026-08-18 00:00:00 | 2026-08-27 | Full | Full | 100% | 0 | 93 | 0 | 67 | 9 | 22 | 0 | 0 | 0 | - | [14 empty] | 191 | 191 | 0 | 100% | 0 | 2 | 0 | 0
PS5-60-02 - Power Gen Package A (UCP) | 1 | Yes | E,I | N/A | 20-Aug-26 | - | PS5 - Milestone B | 100% | 0 | 6 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 44 | 44 | 0 | 100% | 0 | 0 | 0 | 0 |  |  | WALKDOWN COMPLETE-20-08-26--ATTENDENCE SHEET TO BE SUBMITTED
PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 1 | Yes | E,I,T | N/A | 2026-08-27 | - | Full | 100% | 0 | 18 | 0 | 4 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 24 | 24 | 0 | 100% | 0 | 3 | 3 | 0
PS5-60-04 - Power Generation Package B | 1 | Yes | E,I,M,P | 2026-08-17 00:00:00 | 2026-08-24 | Full | Full | 100% | 0 | 89 | 0 | 50 | 9 | 22 | 0 | 0 | 0 | - | [14 empty] | 170 | 170 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-05 - Power Gen Package B (UCP) | 1 | Yes | E,I,T | N/A | 2026-08-22 | - | Full | 100% | 0 | 6 | 0 | 38 | 0 | 0 | 0 | 8 | 8 | 100% | [14 empty] | 52 | 52 | 0 | 100% | 0 | 0 | 4 | 0
PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 1 | Yes | E,I,T | N/A | 2026-09-05 | - | Full | 100% | 0 | 16 | 0 | 4 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 22 | 22 | 0 | 100% | 0 | 2 | 3 | 0
PS5-60-07 - Power Generation Package C | 1.1 | Yes | E,I,M,P | 2026-08-20 00:00:00 | 2026-09-05 | Full | Partial | 99% | 0 | 89 | 0 | 50 | 8 | 22 | 0 | 0 | 0 | - | [14 empty] | 169 | 167 | 2 | 99% | 0 | 0 | 2 | 0
PS5-60-08 - Power Gen Package C (UCP) | 1.1 | Yes | E,I,T | N/A | 2026-09-07 | - | Full | 100% | 0 | 6 | 0 | 38 | 0 | 0 | 0 | 8 | 8 | 100% | [14 empty] | 52 | 52 | 0 | 100% | 0 | 0 | 2 | 0
PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 1.1 | Yes | E,I,T | N/A | 2026-09-07 | - | Full | 100% | 0 | 18 | 0 | 4 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 24 | 24 | 0 | 100% | 0 | 2 | 0 | 0
PS5-60-10 - Power Generation Package D | 1.1 | Yes | E,I,M,P,T | 2026-08-20 00:00:00 | 2026-09-11 | Full | Partial | 99% | 0 | 93 | 0 | 63 | 9 | 22 | 0 | 12 | 12 | 100% | [14 empty] | 199 | 197 | 2 | 99% | 0 | 2 | 2 | 0
PS5-60-11 - Power Gen Package D (UCP) | 1.1 | Yes | E,I,T | N/A | 2026-09-11 | - | Full | 100% | 0 | 6 | 0 | 38 | 0 | 0 | 0 | 8 | 8 | 100% | [14 empty] | 52 | 52 | 0 | 100% | 0 | 0 | 2 | 0
PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 1.1 | Yes | E,I,T | N/A | 2026-08-26 | - | Full | 100% | 0 | 16 | 0 | 4 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 22 | 22 | 0 | 100% | 0 | 2 | 0 | 0
PS5-60-13 - Power Generation Package E | 2 | Yes | E,I,M,P | 2026-08-28 00:00:00 | 2026-09-23 | Full | Full | 100% | 0 | 89 | 0 | 50 | 8 | 22 | 0 | 0 | 0 | - | [14 empty] | 169 | 169 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-14 - Power Gen Package E (UCP) | 2 | Yes | E,I,T | N/A | 2026-09-23 | - | full | 100% | 0 | 6 | 0 | 38 | 0 | 0 | 0 | 8 | 8 | 100% | [14 empty] | 52 | 52 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2 | Yes | E,I,T | N/A | 2026-09-28 | - | Full | 100% | 0 | 18 | 0 | 4 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 24 | 24 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-16 - Power Generation Package F | 2 | Yes | E,I,M,P,T | 2026-08-28 00:00:00 | 2026-10-08 | full | Partial | 99% | 0 | 93 | 0 | 63 | 9 | 22 | 0 | 12 | 12 | 100% | [14 empty] | 199 | 197 | 2 | 99% | 0 | 0 | 0 | 0
PS5-60-17 - Power Gen Package F (UCP) | 2 | Yes | E,I,T | N/A | 2026-10-07 | - | Full | 100% | 0 | 6 | 0 | 38 | 0 | 0 | 0 | 8 | 8 | 100% | [14 empty] | 52 | 52 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2 | Yes | E,I,T | N/A | 2026-09-28 | - | Full | 100% | 0 | 16 | 0 | 4 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 22 | 22 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-19 - Power Generation Package G | 2 | Yes | E,I,M,P | 2026-08-29 00:00:00 | 2026-10-12 | full | Partial | 99% | 0 | 89 | 0 | 50 | 9 | 22 | 0 | 0 | 0 | - | [14 empty] | 170 | 168 | 2 | 99% | 0 | 0 | 0 | 0
PS5-60-20 - Power Gen Package G (UCP) | 2 | Yes | E,I,T | N/A | 2026-10-03 | - | partial | 100% | 0 | 6 | 0 | 38 | 0 | 0 | 0 | 6 | 6 | 100% | [14 empty] | 50 | 50 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2 | Yes | E,I,T | N/A | 2026-09-30 | - | Full | 100% | 0 | 18 | 0 | 4 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 24 | 24 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-22 - Power Gen Master UCP | 1 | Yes | E,I,T | N/A | 2026-09-16 | - | Partial | 88% | 0 | 57 | 0 | 48 | 0 | 0 | 0 | 12 | 12 | 100% | [14 empty] | 117 | 103 | 14 | 88% | 0 | 0 | 6 | 0 | 0
PS5-60-23 - Instrument Air Distribution lines | 1 | Yes | P | 2026-08-18 00:00:00 | 2026-08-27 | Full |  | 100% | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | - | [14 empty] | 8 | 8 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-24 - Cooling Water Tank & Pump | 1 | Yes | E,I,M,P | 2026-08-26 00:00:00 | 2026-09-01 | Full | Partial | 95% | 0 | 4 | 0 | 8 | 4 | 45 | 0 | 0 | 0 | - | [14 empty] | 61 | 58 | 3 | 95% | 0 | 0 | 3 | 0
PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | 1 | Yes | E,I,M,P | 2026-08-26 00:00:00 | 2026-09-01 | Full | Partial | 95% | 0 | 4 | 0 | 8 | 4 | 40 | 0 | 0 | 0 | - | [14 empty] | 56 | 53 | 3 | 95% | 0 | 0 | 3 | 0
PS5-60-26 - Instrument Air Compressor Skid | 1 | Yes | walkdown complete | 2026-08-18 00:00:00 | 2026-08-20 | Full | Full | 100% | 0 | 9 | 0 | 3 | 2 | 14 | 0 | 0 | 0 | - | [14 empty] | 28 | 28 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-27 - Compressed Air Starting Skid | 1 | Yes | E,I,M,P | 2026-08-18 00:00:00 | 2026-08-20 | Full | Full | 100% | 0 | 7 | 0 | 3 | 2 | 14 | 0 | 0 | 0 | - | [14 empty] | 26 | 26 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-28 - Air Receiver A & Air Regulator A | 1 | Yes | I,P | 2026-08-18 00:00:00 | 2026-08-20 | PARTIAL | Full | 100% | 0 | 0 | 0 | 4 | 0 | 9 | 0 | 0 | 0 | - | [14 empty] | 13 | 13 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-29 - Air Receiver B & Air Regulator B | 1 | Yes | I,P | 2026-08-22 00:00:00 | 2026-08-22 | Full | Full | 100% | 0 | 0 | 0 | 4 | 0 | 9 | 0 | 0 | 0 | - | [14 empty] | 13 | 13 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-30 - Air Receiver C & Air Regulator C | 1.1 | Yes | I,P | 2026-08-21 00:00:00 | 2026-08-28 | Full | Full | 100% | 0 | 0 | 0 | 4 | 0 | 9 | 0 | 0 | 0 | - | [14 empty] | 13 | 13 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-31 - Air Receiver D & Air Regulator D | 1.1 | Yes | I,P | 2026-08-21 00:00:00 | 2026-08-28 | Full | Full | 100% | 0 | 0 | 0 | 4 | 0 | 9 | 0 | 0 | 0 | - | [14 empty] | 13 | 13 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-32 - Air Receiver E & Air Regulator E | 2 | Yes | I,P | 2026-08-29 00:00:00 | 2026-09-15 | Full | Full | 100% | 0 | 0 | 0 | 4 | 0 | 9 | 0 | 0 | 0 | - | [14 empty] | 13 | 13 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-33 - Air Receiver F & Air Regulator F | 2 | Yes | I,P | 2026-08-30 00:00:00 | 2026-09-15 | Full | Full | 100% | 0 | 0 | 0 | 4 | 0 | 9 | 0 | 0 | 0 | - | [14 empty] | 13 | 13 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-34 - Air Receiver G & Air Regulator G | 2 | Yes | I,P | 2026-08-30 00:00:00 | 2026-09-22 | Full | Full | 100% | 0 | 0 | 0 | 4 | 0 | 9 | 0 | 0 | 0 | - | [14 empty] | 13 | 13 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-35 - Injector Tip Cooling Module A | 1 | Yes | E,I,M,P | 2026-08-17 00:00:00 |  | COMPLETE | Full | 100% | 0 | 9 | 0 | 3 | 4 | 17 | 0 | 0 | 0 | - | [14 empty] | 33 | 33 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-36 - Injector Tip Cooling Module B | 1 | Yes | E,I,M,P | 2026-08-17 00:00:00 |  | Full | Full | 100% | 0 | 9 | 0 | 3 | 4 | 17 | 0 | 0 | 0 | - | [14 empty] | 33 | 33 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-37 - Injector Tip Cooling Module C | 1.1 | Yes | E,I,M,P | 2026-09-01 00:00:00 | 2026-09-01 | Full | Full | 100% | 0 | 9 | 0 | 3 | 5 | 17 | 0 | 0 | 0 | - | [14 empty] | 34 | 34 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-38 - Injector Tip Cooling Module D | 1.1 | Yes | E,I,M,P | 2026-09-01 00:00:00 | 2026-09-01 | Full | Full | 100% | 0 | 9 | 0 | 3 | 5 | 17 | 0 | 0 | 0 | - | [14 empty] | 34 | 34 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-39 - Injector Tip Cooling Module E | 2 | Yes | E,I,M,P | 2026-09-25 00:00:00 | 2026-09-23 | Full | Full | 100% | 0 | 9 | 0 | 3 | 4 | 17 | 0 | 0 | 0 | - | [14 empty] | 33 | 33 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-40 - Injector Tip Cooling Module F | 2 | Yes | E,I,M,P | 2026-09-26 00:00:00 | 2026-09-23 | Full | Full | 100% | 0 | 9 | 0 | 3 | 5 | 17 | 0 | 0 | 0 | - | [14 empty] | 34 | 34 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-41 - Injector Tip Cooling Module G | 2 | Yes | E,I,M,P | 2026-09-27 00:00:00 | 2026-10-03 | Full | full | 100% | 0 | 9 | 0 | 3 | 5 | 17 | 0 | 0 | 0 | - | [14 empty] | 34 | 34 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 1 | Yes | E,I,M,P | 2026-08-17 00:00:00 |  | COMPLETE | Full | 100% | 0 | 3 | 0 | 3 | 2 | 19 | 0 | 0 | 0 | - | [14 empty] | 27 | 27 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 1 | Yes | E,I,M,P | 2026-08-17 00:00:00 |  | Full | Full | 100% | 0 | 3 | 0 | 3 | 2 | 19 | 0 | 0 | 0 | - | [14 empty] | 27 | 27 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 1.1 | Yes | E,I,M,P | 2026-09-01 00:00:00 | 2026-09-07 | Full | Full | 100% | 0 | 3 | 0 | 3 | 2 | 19 | 0 | 0 | 0 | - | [14 empty] | 27 | 27 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 1.1 | Yes | E,I,M,P | 2026-09-02 00:00:00 | 2026-09-07 | Full | Full | 100% | 0 | 3 | 0 | 3 | 2 | 19 | 0 | 0 | 0 | - | [14 empty] | 27 | 27 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2 | Yes | E,I,M,P | 2026-09-28 00:00:00 | 2026-10-02 | Full | Full | 100% | 0 | 3 | 0 | 3 | 2 | 19 | 0 | 0 | 0 | - | [14 empty] | 27 | 27 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2 | Yes | E,I,M,P | 2026-09-29 00:00:00 | 2026-09-25 | Full | Full | 100% | 0 | 3 | 0 | 3 | 2 | 19 | 0 | 0 | 0 | - | [14 empty] | 27 | 27 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2 | Yes | E,I,M,P | 2026-10-01 00:00:00 | 2026-10-16 | full | Full | 100% | 0 | 3 | 0 | 3 | 2 | 19 | 0 | 0 | 0 | - | [14 empty] | 27 | 27 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 1 | Yes | E,I,M,P,T | 2026-08-19 00:00:00 | 2026-08-20 | Full | full | 100% | 0 | 5 | 0 | 11 | 2 | 15 | 0 | 2 | 2 | 100% | [14 empty] | 35 | 35 | 0 | 100% | 0 | 0 | 1 | 0 |  |  | OBSERVATION -CLEANING ON PROGRESS
PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 1 | Yes | E,I,M,P,T | 2026-08-20 00:00:00 | 2026-08-26 | Full | full | 100% | 0 | 5 | 0 | 11 | 2 | 15 | 0 | 2 | 2 | 100% | [14 empty] | 35 | 35 | 0 | 100% | 0 | 0 | 1 | 0
PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 1.1 | Yes | E,I,M,P,T | 2026-09-02 00:00:00 | 2026-09-07 | Full | full | 100% | 0 | 5 | 0 | 11 | 2 | 15 | 0 | 2 | 2 | 100% | [14 empty] | 35 | 35 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 1.1 | Yes | E,I,M,P,T | Complete | 2026-09-08 | Full | Full | 100% | 0 | 5 | 0 | 11 | 2 | 15 | 0 | 2 | 2 | 100% | [14 empty] | 35 | 35 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2 | Yes | E,I,M,P,T | 2026-10-02 00:00:00 | 2026-10-03 | Full | full | 100% | 0 | 5 | 0 | 11 | 2 | 15 | 0 | 2 | 2 | 100% | [14 empty] | 35 | 35 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2 | Yes | E,I,M,P,T | 2026-10-03 00:00:00 | 2026-10-05 | Full | Full | 100% | 0 | 5 | 0 | 11 | 2 | 15 | 0 | 2 | 2 | 100% | [14 empty] | 35 | 35 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2 | Yes | E,I,M,P,T | 2026-10-04 00:00:00 | 2026-10-05 | Full | Full | 100% | 0 | 5 | 0 | 11 | 2 | 15 | 0 | 2 | 2 | 100% | [14 empty] | 35 | 35 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 1 | Yes | E,I,M,P | 2026-08-20 00:00:00 | 2026-08-26 | Full | Full | 100% | 0 | 38 | 0 | 8 | 3 | 17 | 0 | 0 | 0 | - | [14 empty] | 66 | 66 | 0 | 100% | 0 | 0 | 2 | 0
PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 1 | Yes | E,I,T | N/A | 2026-08-22 | - | Full | 100% | 0 | 10 | 0 | 22 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 34 | 34 | 0 | 100% | 0 | 2 | 1 | 0
PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 1 | Yes | E,I,M,P | 2026-08-21 00:00:00 | 2026-08-26 | Full | Full | 100% | 0 | 38 | 0 | 8 | 4 | 17 | 0 | 0 | 0 | - | [14 empty] | 67 | 67 | 0 | 100% | 0 | 0 | 2 | 0
PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 1 | Yes | E,I,T | N/A | 2026-08-24 | - | Full | 100% | 0 | 10 | 0 | 22 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 34 | 34 | 0 | 100% | 0 | 2 | 1 | 0
PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 1.1 | Yes | E,I,M,P | 2026-09-04 00:00:00 | 2026-09-08 | Full | Full | 100% | 0 | 38 | 0 | 8 | 4 | 17 | 0 | 0 | 0 | - | [14 empty] | 67 | 67 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | 1.1 | Yes | E,I,T | N/A | 2026-09-07 | - | Full | 100% | 0 | 10 | 0 | 22 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 34 | 34 | 0 | 100% | 0 | 2 | 1 | 0
PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 1.1 | Yes | E,I,M,P | 2026-09-04 00:00:00 | 2026-09-08 | Full | Full | 100% | 0 | 38 | 0 | 8 | 4 | 17 | 0 | 0 | 0 | - | [14 empty] | 67 | 67 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 1.1 | Yes | E,I,T | N/A | 2026-09-07 | - | Full | 100% | 0 | 10 | 0 | 22 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 34 | 34 | 0 | 100% | 0 | 2 | 1 | 0
PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2 | Yes | E,I,M,P | 2026-10-01 00:00:00 | 2026-10-05 | Full | Partial | 97% | 0 | 38 | 0 | 8 | 4 | 17 | 0 | 0 | 0 | - | [14 empty] | 67 | 65 | 2 | 97% | 0 | 0 | 0 | 1
PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | 2 | Yes | E,I,T | N/A | 2026-10-05 | - | full | 100% | 0 | 10 | 0 | 22 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 34 | 34 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2 | Yes | E,I,M,P | 2026-10-02 00:00:00 | 2026-10-05 | Full | Partial | 97% | 0 | 38 | 0 | 8 | 4 | 17 | 0 | 0 | 0 | - | [14 empty] | 67 | 65 | 2 | 97% | 0 | 0 | 0 | 1
PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | 2 | Yes | E,I,T | N/A | 2026-10-05 | - | full | 100% | 0 | 10 | 0 | 22 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 34 | 34 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2 | Yes | E,I,M,P | 2026-10-04 00:00:00 | 2026-10-08 | partial | Partial | 93% | 0 | 38 | 0 | 8 | 4 | 17 | 0 | 0 | 0 | - | [14 empty] | 67 | 62 | 5 | 93% | 0 | 0 | 0 | 1
PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | 2 | Yes | E,I,T | N/A | 2026-10-07 | - | Full | 100% | 0 | 10 | 0 | 22 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 34 | 34 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-70 - Engine A Cooling system | 1 | Yes | E,I,M,P | 2026-08-19 00:00:00 | 2026-08-22 | Full | Full | 100% | 0 | 8 | 0 | 16 | 6 | 40 | 0 | 0 | 0 | - | [14 empty] | 70 | 70 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-71 - Engine B Cooling system | 1 | Yes | E,I,M,P | 2026-08-20 00:00:00 | 2026-08-22 | Full | Full | 100% | 0 | 8 | 0 | 16 | 6 | 40 | 0 | 0 | 0 | - | [14 empty] | 70 | 70 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-72 - Engine C Cooling system | 1.1 | Yes | E,I,M,P | 2026-09-04 00:00:00 | 2026-09-11 | Full | Full | 100% | 0 | 8 | 0 | 16 | 6 | 40 | 0 | 0 | 0 | - | [14 empty] | 70 | 70 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-73 - Engine D Cooling system | 1.1 | Yes | E,I,M,P | 2026-09-05 00:00:00 | 2026-09-11 | Full | Full | 100% | 0 | 8 | 0 | 16 | 6 | 40 | 0 | 0 | 0 | - | [14 empty] | 70 | 70 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-74 - Engine E Cooling system | 2 | Yes | E,I,M,P | 2026-10-05 00:00:00 | 2026-10-02 | full | Full | 100% | 0 | 8 | 0 | 16 | 6 | 40 | 0 | 0 | 0 | - | [14 empty] | 70 | 70 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-75 - Engine F Cooling system | 2 | Yes | E,I,M,P | 2026-10-05 00:00:00 | 2026-09-23 | Full | Full | 100% | 0 | 8 | 0 | 16 | 6 | 40 | 0 | 0 | 0 | - | [14 empty] | 70 | 70 | 0 | 100% | 0 | 0 | 0 | 0
PS5-60-76 - Engine G Cooling system | 2 | Yes | E,I,M,P | 2026-10-06 00:00:00 |  | FULL | Full | 100% | 0 | 8 | 0 | 16 | 6 | 40 | 0 | 0 | 0 | - | [14 empty] | 70 | 70 | 0 | 100% | 0 | 0 | 0 | 0
PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | 1 | Yes | E,M | complete | 2026-09-05 | Full | Partial | 90% | 0 | 74 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | - | [14 empty] | 82 | 74 | 8 | 90% | 0 | 0 | 4 | 0
PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | 3 | Yes | E,M | complete | 2026-10-02 | - | Full | 100% | 0 | 32 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | - | [14 empty] | 34 | 34 | 0 | 100% | 0 | 0 | 0 | 0
PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | 3 | Yes | E,M | complete | 2026-10-03 | full | Full | 100% | 0 | 32 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | - | [14 empty] | 34 | 34 | 0 | 100% | 0 | 0 | 0 | 0
PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | 1 | No | E | N/A | TBC | - |  | 0% | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 23 | 0 | 23 | 0% | 0 | 18 | 0 | 0
PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | 1 | Yes | E | N/A | 2026-08-24 | - | Full | 100% | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 114 | 114 | 0 | 100% | 0 | 0 | 0 | 0
PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | 1 | Yes | E | N/A | 2026-10-03 | - | partial | 69% | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 94 | 65 | 29 | 69% | 0 | 0 | 16 | 0
PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | 2 | Yes | E,M | complete | 2026-09-15 | Full | Full | 100% | 0 | 65 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | - | [14 empty] | 67 | 67 | 0 | 100% | 0 | 0 | 0 | 0
PS5-61-08 - Electrical Control System | 2 | Yes | E | N/A | 2026-10-31 | - |  | 96% | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 23 | 22 | 1 | 96% | 0 | 0 | 0 | 0
PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | 2 | Yes | E | N/A | 2026-11-04 | - |  | 15% | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 20 | 3 | 17 | 15% | 0 | 0 | 0 | 0
PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | 2 | Yes | E | N/A | 2026-09-19 | - | Full | 100% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 4 | 0 | 100% | 0 | 0 | 0 | 0
PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | 1.1 | Yes | E | N/A | 2026-09-19 | - | Full | 100% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 4 | 0 | 100% | 0 | 0 | 0 | 0
PS5-61-12 - EITS 33kV Bld. Normal Auxiliary DP - PS5-61-IG-0008 | [5 empty] | - |  | 92% | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 25 | 23 | 2 | 92% | 0 | 0 | 0
PS5-61-13 - Power Distribution Board Office Building - PS5-61-IG-0020 | 5 | No | E | N/A |  | - |  | 0% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0 | 0
PS5-61-14 - Power Distribution Board Workshop & Warehouse - PS5-61-IG-0009 | 4 | No | E | N/A |  | - |  | 0% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0 | 0
PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | 2 | Yes | E | N/A | 2026-11-10 | - |  | 47% | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 64 | 30 | 34 | 47% | 0 | 0 | 0 | 0
PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | 2 | Yes | E | N/A | 2026-11-10 | - |  | 52% | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 67 | 35 | 32 | 52% | 0 | 0 | 0 | 0
PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | 2 | Yes | E | N/A | 2026-10-08 | - | Full | 100% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 4 | 0 | 100% | 0 | 0 | 0 | 0
PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | 2 | Yes | E | N/A | 2026-09-19 | - | Full | 100% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 4 | 0 | 100% | 0 | 0 | 0 | 0
PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | 4 | No | E | N/A |  | - |  | 0% | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 20 | 0 | 20 | 0% | 0 | 0 | 0 | 0
PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | 1.1 | Yes | E | N/A | 2026-09-19 | - | Partial | 26% | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 19 | 5 | 14 | 26% | 0 | 0 | 0 | 0
PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | 1.1 | Yes | E | N/A | Clash with ducting | - |  | 35% | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 17 | 6 | 11 | 35% | 0 | 0 | 0 | 0
PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | 2 | No | E | N/A | 2026-10-30 | - |  | 18% | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 22 | 4 | 18 | 18% | 0 | 0 | 0 | 0
PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | 2 | No | E | N/A | 2026-10-30 | - |  | 50% | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 24 | 12 | 12 | 50% | 0 | 0 | 0 | 0
PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | 1.1 | Yes | E | N/A | 2026-09-19 | - | Partial | 41% | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 39 | 16 | 23 | 41% | 0 | 0 | 0 | 0
PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | 1.1 | Yes | E | N/A | Clash with ducting | - |  | 26% | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 19 | 5 | 14 | 26% | 0 | 0 | 0 | 0
PS5-62-12 - EITS 33kV Bld. Emergency L&SP DP - PS5-05-IG-0003 | [5 empty] | - |  | 96% | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 26 | 25 | 1 | 96% | 0 | 0 | 0
PS5-62-13 - EITS 33kV Bld. Normal L&SP DP - PS5-61-IG-0003 | [5 empty] | - |  | 97% | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 34 | 33 | 1 | 97% | 0 | 0 | 0
PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | 5 | No | E | N/A |  | - |  | 3% | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 30 | 1 | 29 | 3% | 0 | 0 | 0 | 0
PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | 5 | No | E | N/A |  | - |  | 0% | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 46 | 0 | 46 | 0% | 0 | 0 | 0 | 0
PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | 5 | No | E | N/A |  | - |  | 0% | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0 | 0
PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | 5 | No | E | N/A |  | - |  | 0% | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0 | 0
PS5-62-18 - Workshop & Warehouse Normal L&SP DB - PS5-61-IG-0004 | 5 | No | E | N/A |  | - |  | 0% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0 | 0
PS5-62-19 - Workshop & Warehouse Emergency L&SP DB - PS5-05-IG-0101 | 5 | No | E | N/A |  | - |  | 0% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0 | 0
PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | 5 | No | E | N/A |  | - |  | 0% | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 10 | 0 | 10 | 0% | 0 | 0 | 0 | 0
PS5-63-01 - Electrical Earthing | 1 | Yes | E | N/A | 2026-09-16 | - | Partial | 54% | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 68 | 37 | 31 | 54% | 0 | 40 | 0 | 0 |  | 18 ITRs for lightning, 22 ITRs for grounding cannot be closed due to material issues.
PS5-63-02 - Electrical Earthing - Office and Facilities building | 4 | No | E | N/A |  | - |  | 0% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0 | 0
PS5-63-03 - Electrical Earthing - Generator Building | 1 | Yes | E | N/A | 2026-08-24 | - | Partial | 50% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 2 | 2 | 50% | 0 | 2 | 0 | 0
PS5-63-04 - Electrical Earthing - EITS Building | [5 empty] | - |  | 100% | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 28 | 28 | 0 | 100% | 0 | 0 | 0
PS5-63-05 - Electrical Earthing - Guard Hut A & B | 4 | No | E | N/A |  | - |  | 0% | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 8 | 0 | 8 | 0% | 0 | 0 | 0 | 0
PS5-63-06 - Electrical Earthing - Guard House | 4 | No | E | N/A |  | - |  | 0% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0 | 0
PS5-63-07 - Electrical Earthing - Workshop & Warehouse | 4 | No | E | N/A |  | - |  | 0% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0 | 0
PS5-71-01 - CFO Storage Tank Feed Heater | 2 | No | E,I,M,P | 2026-10-03 00:00:00 | 2026-10-16 | Full |  | 93% | 0 | 14 | 0 | 48 | 2 | 30 | 0 | 0 | 0 | - | [14 empty] | 94 | 87 | 7 | 93% | 0 | 0 | 0 | 0 | 0
PS5-71-02 - CFO Allocation Metering Package | 2 | No | E,I,M,P | 2026-10-03 00:00:00 | 2026-10-08 | full | Full | 100% | 0 | 1 | 0 | 4 | 2 | 10 | 0 | 0 | 0 | - | [14 empty] | 17 | 17 | 0 | 100% | 0 | 0 | 0 | 0
PS5-71-03 - CFO Allocation Metering Package (UCP) | [5 empty] | - |  | 80% | 0 | 11 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 15 | 12 | 3 | 80% | 0 | 0 | 0
PS5-71-04 - CFO Storage Tank | 2 | No | E,I,M,P | 2026-10-04 00:00:00 | TBC | Full |  | 84% | 0 | 22 | 0 | 58 | 2 | 47 | 0 | 0 | 0 | - | [14 empty] | 129 | 109 | 20 | 84% | 0 | 0 | 0 | 0
PS5-71-05 - CFO Transfer Pump A/B | 2 | No | E,I,M,P | 2026-10-05 00:00:00 | 2026-10-23 | full |  | 91% | 0 | 10 | 0 | 35 | 5 | 14 | 0 | 0 | 0 | - | [14 empty] | 64 | 58 | 6 | 91% | 0 | 0 | 0 | 0
PS5-71-06 - Crude Fuel Separation Module | 1.1 | No | E,I,M,P | 2026-09-05 00:00:00 | HOLD/meterial issue | - |  | 58% | 0 | 2 | 0 | 34 | 4 | 22 | 0 | 0 | 0 | - | [14 empty] | 62 | 36 | 26 | 58% | 0 | 0 | 22 | 0
PS5-71-07 - Crude Fuel Separation Module (UCP) | 1.1 | No | E,I,T | N/A | HOLD/meterial issue | - |  | 63% | 0 | 64 | 0 | 44 | 0 | 0 | 0 | 4 | 4 | 100% | [14 empty] | 112 | 71 | 41 | 63% | 0 | 0 | 54 | 0
PS5-71-08 - CFO Pre-Pressure Modules | 1.1 | No | E,I,M,P | 2026-08-31 00:00:00 | 2026-09-15 | Full | Partial | 95% | 0 | 25 | 0 | 31 | 2 | 15 | 0 | 0 | 0 | - | [14 empty] | 73 | 69 | 4 | 95% | 0 | 0 | 3 | 0
PS5-71-09 - CFO Pre-Pressure Modules (UCP) | 1.1 | No | E,I,T | N/A | 2026-10-14 | - | Full | 100% | 0 | 8 | 0 | 11 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 21 | 21 | 0 | 100% | 0 | 0 | 0 | 0
PS5-71-12 - CFO Service Tank | 2 | No | E,I,M,P | 2026-10-06 00:00:00 | 2026-10-30 | - |  | 85% | 0 | 24 | 0 | 69 | 1 | 31 | 0 | 0 | 0 | - | [14 empty] | 125 | 106 | 19 | 85% | 0 | 0 | 0 | 0
PS5-71-13 - CFO Service Pump A/B | 2 | No | E,I,M,P | 2026-10-06 00:00:00 | 2026-10-23 | full |  | 89% | 0 | 10 | 0 | 27 | 5 | 14 | 0 | 0 | 0 | - | [14 empty] | 56 | 50 | 6 | 89% | 0 | 0 | 0 | 0
PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | 2 | No | E,I,M,P | 2026-10-07 00:00:00 | 2026-10-07 | Full | Full | 100% | 0 | 7 | 0 | 4 | 5 | 9 | 0 | 0 | 0 | - | [14 empty] | 25 | 25 | 0 | 100% | 0 | 0 | 0 | 0
PS5-71-15 - Diesel Fuel Storage Tank | 2 | Yes | E,I,M,P | 2026-10-10 00:00:00 | 2026-11-05 | - |  | 82% | 0 | 8 | 0 | 27 | 1 | 20 | 0 | 0 | 0 | - | [14 empty] | 56 | 46 | 10 | 82% | 0 | 0 | 0 | 0 | 0
PS5-71-16 - Diesel Fuel Supply Pump A/B | 2 | Yes | E,I,M,P | 2026-10-07 00:00:00 | 2026-09-28 | Full | Full | 100% | 0 | 8 | 0 | 10 | 6 | 9 | 0 | 0 | 0 | - | [14 empty] | 33 | 33 | 0 | 100% | 0 | 0 | 0 | 0
PS5-71-17 - Diesel Fuel Distribution Header | 2 | Yes | I,P | 2026-10-07 00:00:00 | 2026-09-25 | Full | partial | 94% | 0 | 0 | 0 | 13 | 0 | 18 | 0 | 0 | 0 | - | [14 empty] | 31 | 29 | 2 | 94% | 0 | 0 | 0 | 0
PS5-71-18 - Diesel Separator Module | 1 | Yes | E,I,M,P | Complete | 2026-09-05 | Full | Partial | 92% | 0 | 3 | 0 | 28 | 2 | 20 | 0 | 0 | 0 | - | [14 empty] | 53 | 49 | 4 | 92% | 0 | 0 | 4 | 0
PS5-71-19 - Diesel Separator Module (UCP) | 1 | Yes | E,I,T | N/A | 2026-11-04 | - |  | 78% | 0 | 16 | 0 | 17 | 0 | 0 | 0 | 4 | 4 | 100% | [14 empty] | 37 | 29 | 8 | 78% | 0 | 0 | 8 | 0
PS5-71-20 - Diesel Fuel Day Tank | 1 | Yes | E,I,M,P | 2026-08-20 00:00:00 | 2026-08-29 | Full | Partial | 89% | 0 | 4 | 0 | 30 | 1 | 20 | 0 | 0 | 0 | - | [14 empty] | 55 | 49 | 6 | 89% | 0 | 0 | 6 | 0
PS5-71-21 - Diesel Transfer Pump A/B | 1 | Yes | E,I,M,P | 2026-08-19 00:00:00 | 2026-08-29 | Full | Partial | 93% | 0 | 10 | 0 | 25 | 6 | 14 | 0 | 0 | 0 | - | [14 empty] | 55 | 51 | 4 | 93% | 0 | 2 | 3 | 0
PS5-71-22 - Diesel Fuel Pre Pressure Module | 1 | Yes | E,I,M,P | 2026-08-20 00:00:00 | 2026-08-29 | DONE(full) | Full | 100% | 0 | 13 | 0 | 23 | 1 | 29 | 0 | 0 | 0 | - | [14 empty] | 66 | 66 | 0 | 100% | 0 | 0 | 0 | 0
PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 1 | Yes | E,I,T | N/A | 2026-08-28 | - | Partial | 92% | 0 | 8 | 0 | 15 | 0 | 0 | 0 | 2 | 2 | 100% | [14 empty] | 25 | 23 | 2 | 92% | 0 | 0 | 4 | 0
PS5-74-01 - N2 Generation Skid | 2 | Yes | E,I,M,P | complete | 2026-09-23 | Full | Full | 100% | 0 | 3 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | - | [14 empty] | 7 | 7 | 0 | 100% | 0 | 0 | 0 | 0 | 0
PS5-74-02 - N2 Generation Skid (UCP) | 2 | Yes | E,I | N/A | 2026-09-23 | - | Partial | 70% | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 10 | 7 | 3 | 70% | 0 | 0 | 0 | 0
PS5-74-03 - Nitrogen Receiver | 2 | Yes | I,M,P | 2026-10-08 00:00:00 | 2026-09-23 | Full | Full | 100% | 0 | 0 | 0 | 3 | 1 | 16 | 0 | 0 | 0 | - | [14 empty] | 20 | 20 | 0 | 100% | 0 | 0 | 0 | 0
PS5-74-04 - Nitrogen Distribution Header | 2 | Yes | I,P | 2026-10-08 00:00:00 | 2026-10-05 | Full | Full | 100% | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | - | [14 empty] | 16 | 16 | 0 | 100% | 0 | 0 | 0 | 0
PS5-75-01 - DRA Injection Package | 3 | No | E,I,M,P | 2026-11-01 00:00:00 |  | - |  | 60% | 0 | 7 | 0 | 7 | 1 | 15 | 0 | 0 | 0 | - | [14 empty] | 30 | 18 | 12 | 60% | 0 | 0 | 0 | 0
PS5-75-02 - Biocide Injection Package | 3 | Yes | E,I,M,P | 2026-09-16 00:00:00 | 2026-10-14 | Full | Full | 100% | 0 | 5 | 0 | 3 | 2 | 14 | 0 | 0 | 0 | - | [14 empty] | 24 | 24 | 0 | 100% | 0 | 0 | 0 | 0
PS5-75-03 - Corrosion Inhibitor Injection Package | 3 | Yes | E,I,M,P | 2026-09-17 00:00:00 | 2026-10-14 | Full | Full | 100% | 0 | 5 | 0 | 3 | 2 | 15 | 0 | 0 | 0 | - | [14 empty] | 25 | 25 | 0 | 100% | 0 | 0 | 0 | 0
PS5-78-01 - Lifting and handling equipment | 3 | Partially | E,M | 2026-09-18 00:00:00 |  | Partial | Partial | 77% | 0 | 8 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | - | [14 empty] | 22 | 17 | 5 | 77% | 0 | 0 | 0 | 0
PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | 3 | Yes | E,I,M | complete | 2026-11-12 | - |  | 75% | 0 | 67 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 69 | 52 | 17 | 75% | 0 | 0 | 0 | 0
PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | 3 | Yes | E,I,M | complete | 2026-11-12 | - |  | 79% | 0 | 69 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 71 | 56 | 15 | 79% | 0 | 0 | 0 | 0
PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | 3 | Yes | E,I,M | complete | 2026-11-14 | - |  | 43% | 0 | 67 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 69 | 30 | 39 | 43% | 0 | 0 | 0 | 0
PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | 3 | Yes | E,I,M | complete | 2026-11-14 | - |  | 42% | 0 | 63 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 65 | 27 | 38 | 42% | 0 | 0 | 0 | 0
PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | 3 | Yes | E,I,M | complete | 2026-11-16 | - |  | 33% | 0 | 65 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 67 | 22 | 45 | 33% | 0 | 0 | 0 | 0
PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | 3 | Yes | E,I,M | complete | 2026-11-16 | - |  | 37% | 0 | 73 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 75 | 28 | 47 | 37% | 0 | 0 | 0 | 0
PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | 3 | Yes | E,I,M | complete | 2026-11-16 | - |  | 73% | 0 | 73 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 75 | 55 | 20 | 73% | 0 | 0 | 0 | 0
PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | 3 | Yes | E,I,M | complete | 2026-11-17 | - |  | 61% | 0 | 73 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 75 | 46 | 29 | 61% | 0 | 0 | 0 | 0
PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | 3 | Yes | E,I,M | complete | 2026-11-17 | - |  | 44% | 0 | 73 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 75 | 33 | 42 | 44% | 0 | 0 | 0 | 0
PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | 3 | Yes | E,I,M | complete | 2026-11-17 | - |  | 62% | 0 | 69 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 71 | 44 | 27 | 62% | 0 | 0 | 0 | 0
PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | 3 | Yes | E,I,M | complete | 2026-11-18 | - |  | 35% | 0 | 69 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 71 | 25 | 46 | 35% | 0 | 0 | 0 | 0
PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | 3 | Yes | E,I,M | complete | 2026-11-18 | - |  | 47% | 0 | 79 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 81 | 38 | 43 | 47% | 0 | 0 | 0 | 0
PS5-82-01 - Sanitary Sewage Collection | 4 | No | P | 2026-11-11 00:00:00 | 2026-10-13 | full |  | 100% | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | - | [14 empty] | 50 | 50 | 0 | 100% | 0 | 0 | 0 | 0
PS5-82-02 - Sewage Treatment Plant Package | 4 | No | E,I,M,P | 2026-11-12 00:00:00 |  | - |  | 50% | 0 | 2 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | - | [14 empty] | 6 | 3 | 3 | 50% | 0 | 0 | 0 | 0
PS5-82-03 - Sewage Treatment Plant Package (UCP) | 4 | No | I | N/A |  | - |  | 0% | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 2 | 0 | 2 | 0% | 0 | 0 | 0 | 0
PS5-82-04 - Sewage Treatment Plant Discharge Piping | 4 | No | P | 2026-11-13 00:00:00 |  | - |  | 88% | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | - | [14 empty] | 8 | 7 | 1 | 88% | 0 | 0 | 0 | 0
PS5-82-05 - Office and Facilities building | 5 | No | B,E | 2026-12-31 00:00:00 |  | - |  | 8% | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 12 | 1 | 11 | 8% | 0 | 0 | 0 | 0
PS5-82-06 - Guard House Building | 5 | No | B,E | 2026-12-21 00:00:00 |  | - |  | 8% | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 12 | 1 | 11 | 8% | 0 | 0 | 0 | 0
PS5-82-07 - Guard Huts | 5 | No | B | 2026-12-11 00:00:00 |  | - |  | 0% | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0 | 0
PS5-83-01 - EITS Building | 2 | Yes | E,M | complete | 2026-09-19 | Full | Full | 100% | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | - | [14 empty] | 3 | 3 | 0 | 100% | 0 | 0 | 0 | 0
PS5-84-01 - Generator Building | 2 | Yes | B,E | 2026-10-10 00:00:00 | 2026-11-05 | - |  | 45% | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 5 | 6 | 45% | 0 | 0 | 0 | 0
PS5-84-02 - Workshop & Warehouse | 5 | No | B | 2026-12-16 00:00:00 |  | - |  | 11% | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 1 | 8 | 11% | 0 | 0 | 0 | 0
PS5-84-03 - Shelters | 4 | No | B | 2026-10-21 00:00:00 | 2026-09-16 | Full |  | 100% | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 4 | 0 | 100% | 0 | 0 | 0 | 0
PS5-86-01 - Shelters | 4 | No | B | 2026-10-23 00:00:00 | 2026-09-16 | Full |  | 100% | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 4 | 0 | 100% | 0 | 0 | 0 | 0
PS5-91-01 - Multicore cables & JB | 1 | Yes | I | N/A | 2026-09-01 | - | Full | 100% | 0 | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 128 | 128 | 0 | 100% | 0 | 0 | 0 | 0
PS5-99-01 - Area Completion for Building area | 4 | No | B,E | 2026-11-15 00:00:00 |  | - |  | 0% | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0 | 0
PS5-99-02 - Area Completion for Utility area | 3 | No | B,E | 2026-11-01 00:00:00 |  | - |  | 33% | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 3 | 1 | 2 | 33% | 0 | 0 | 0 | 0
PS5-99-03 - Area Completion for Power Distribution area | 2 | No | B,E | 2026-10-10 00:00:00 | 2026-11-05 | - |  | 33% | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 3 | 1 | 2 | 33% | 0 | 0 | 0 | 0
PS5-99-04 - Area Completion for Process area | 2 | No | B,E | 2026-10-10 00:00:00 | 2026-11-05 | - |  | 0% | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 0 | 0
PS5-99-05 - Area Completion for CFO area | 2 | No | B,E | 2026-10-10 00:00:00 | 2026-11-05 | - |  | 33% | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 3 | 1 | 2 | 33% | 0 | 0 | 0 | 0
PS5-99-06 - Area Completion for Power Generation area | 2 | No | B,E | 2026-10-10 00:00:00 | 2026-11-05 | RE WALKDOWN | RE WALKDOWN | 67% | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 3 | 2 | 1 | 67% | 0 | 0 | 0 | 0

## SIDMAP (hidden)
PS5-01-01 - Fire Water Jockey Pump A/B | PS5-01-01
PS5-01-02 - Fire Water Pump A | PS5-01-02
PS5-01-03 - Fire Water Pump B | PS5-01-03
PS5-01-04 - Fire Water Pump Mini Flow Recycle | PS5-01-04
PS5-01-05 - Foam Skid | PS5-01-05
PS5-01-06 - Foam Concentrate Distribution | PS5-01-06
PS5-01-07 - Fire Water Ring Main & Distribution | PS5-01-07
PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | PS5-01-08
PS5-01-09 - Inergen for EITS Building | PS5-01-09
PS5-01-10 - Water Mist Package | PS5-01-10
PS5-01-11 - Inergen for Power Gen Building | PS5-01-11
PS5-02-01 - Miscellaneous Safety equipment | PS5-02-01
PS5-02-02 - Portable Fire Fighting Equipments | PS5-02-02
PS5-03-01 - FZ-01 - Process Area | PS5-03-01
PS5-03-03 - FZ-03 - Buildings Area | PS5-03-03
PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | PS5-03-04
PS5-03-06 - FZ-06 - Transformer Area | PS5-03-06
PS5-03-07 - FZ-07 - Pretreatment Area | PS5-03-07
PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08
PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | PS5-03-09
PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | PS5-03-10
PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | PS5-03-11
PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | PS5-03-12
PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | PS5-03-13
PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | PS5-03-14
PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | PS5-03-15
PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | PS5-03-16
PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | PS5-03-17
PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | PS5-03-18
PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | PS5-03-19
PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | PS5-03-20
PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | PS5-03-21
PS5-03-22 - FZ-G1 - Guard House | PS5-03-22
PS5-03-23 - FZ-E1 to E3 - EITS Building | PS5-03-23
PS5-03-24 - FZ - Office and Facilities Building | PS5-03-24
PS5-03-25 - FZ - Workshop & Warehouse | PS5-03-25
PS5-04-01 - Office Building PCS System | PS5-04-01
PS5-04-02 - Office Building SIS/FGS System | PS5-04-02
PS5-04-03 - 33kV ICSS System | PS5-04-03
PS5-04-04 - 33kV PCS System | PS5-04-04
PS5-04-05 - 33kV SIS/FGS System | PS5-04-05
PS5-05-01 - Emergency Diesel Generator Package | PS5-05-01
PS5-05-02 - Emergency Diesel Generator Package (UCP) | PS5-05-02
PS5-06-01 - AC UPS - EITS Building | PS5-06-01
PS5-06-02 - AC UPS - Power Generator Building | PS5-06-02
PS5-06-03 - AC UPS - Office & Facilities Building | PS5-06-03
PS5-06-04 - AC UPS - Guard House | PS5-06-04
PS5-06-05 - AC UPS - Workshop & Warehouse | PS5-06-05
PS5-08-01 | PS5-08-01
PS5-08-01a - PAGA (Required for SU) | PS5-08-01a
PS5-08-01b - PAGA (Not required for SU) | PS5-08-01b
PS5-08-03 - Telephone | PS5-08-03
PS5-08-04 - Hotline | PS5-08-04
PS5-08-07 - Multi-Channel Voice Recorder | PS5-08-07
PS5-08-11 - Corporate LAN (SIE) | PS5-08-11
PS5-08-12 - Corporate Wireless LAN (SIE) | PS5-08-12
PS5-08-13 - Safety Data Network (SII SP3 SAF) | PS5-08-13
PS5-08-14 - Industrial Data Network (SII SP1) | PS5-08-14
PS5-08-15 - Security Data Network (SII SP3 SEC) | PS5-08-15
PS5-08-23 - VHF Trunk Radio System | PS5-08-23
PS5-08-34 - Satphone | PS5-08-34
PS5-08-35 - Optical Transport Network | PS5-08-35
PS5-08-36 - Pipeline FO Cable & EPRS | PS5-08-36
PS5-08-51 - Entertainment | PS5-08-51
PS5-08-52a - Process & Security CCTV (Required for SU) | PS5-08-52a
PS5-08-52b - Process & Security CCTV (Not required for SU) | PS5-08-52b
PS5-08-55 - Videoconference | PS5-08-55
PS5-08-61 - Meteocean | PS5-08-61
PS5-08-71 - Structured Cabling (CAT6) | PS5-08-71
PS5-08-72 - Structured Cabling (FO) | PS5-08-72
PS5-08-81 - Guard tour | PS5-08-81
PS5-08-82 - Key Management | PS5-08-82
PS5-08-83 - Perimeter & Pipeline intrusion detection system | PS5-08-83
PS5-08-85 | PS5-08-85
PS5-08-85a - Access Control, POB & e-Mustering (Required for SU) | PS5-08-85a
PS5-08-85b - Access Control, POB & e-Mustering (Not required for SU) | PS5-08-85b
PS5-08-86 - Integrated Security Management System | PS5-08-86
PS5-08-92 - Telecom Mast | PS5-08-92
PS5-08-93 - Telecom Monitoring System | PS5-08-93
PS5-09-01 - HVAC for Office and Facilities building | PS5-09-01
PS5-09-02 - HVAC for Guard House | PS5-09-02
PS5-09-03 - HVAC for Generator Building | PS5-09-03
PS5-09-04 - HVAC for Workshop & Warehouse | PS5-09-04
PS5-09-05 - HVAC for EITS Building | PS5-09-05
PS5-0H-01 - HIPPS | PS5-0H-01
PS5-25-01 - Export Pipeline Pig Receiver | PS5-25-01
PS5-25-02 - Crude Oil Export Pump A | PS5-25-02
PS5-25-03 - Crude Oil Export Pump B | PS5-25-03
PS5-25-04 - Crude Oil Export Pump C | PS5-25-04
PS5-25-05 - Crude Oil Export Pumps Bypass | PS5-25-05
PS5-25-06 - Crude Oil Export Pumps Discharge | PS5-25-06
PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07
PS5-28-01 - Closed Drain Header 1 | PS5-28-01
PS5-28-02 - Closed Drain Header 2 | PS5-28-02
PS5-28-03 - Closed Drain Drum and Pump 01 | PS5-28-03
PS5-28-04 - Closed Drain Drum and Pump 02 | PS5-28-04
PS5-28-05 - HP Relief Header | PS5-28-05
PS5-28-06 - Relief Drum and Pump | PS5-28-06
PS5-28-07 - Open Drains (OD2) | PS5-28-07
PS5-28-08 - Open Drain Sump and Pumps | PS5-28-08
PS5-28-09 - Observation Basin | PS5-28-09
PS5-28-10 - Oil Skimmer Package | PS5-28-10
PS5-28-11 - Open Drain Interceptor | PS5-28-11
PS5-28-12 - Open Drains (OD3) | PS5-28-12
PS5-28-13 - Seal Oil Drain Drum & Pump A | PS5-28-13
PS5-28-14 - Seal Oil Drain Drum & Pump B | PS5-28-14
PS5-28-15 - Seal Oil Drain Drum & Pump C | PS5-28-15
PS5-28-16 - LP Relief Header | PS5-28-16
PS5-28-17 - Reinjection Pump | PS5-28-17
PS5-50-01 - Water Well Submersible Pumps (3100) | PS5-50-01
PS5-50-02 - Water Well Submersible Pumps (3200) | PS5-50-02
PS5-50-03 - Water Pre-Treatment Package | PS5-50-03
PS5-53-01 - Utility Water / Storage Tank | PS5-53-01
PS5-53-02 - Water Distribution Pump A/B | PS5-53-02
PS5-53-03 - Water Softener Package | PS5-53-03
PS5-53-04 - Water Treatment Purification Package | PS5-53-04
PS5-53-05 - Water Distribution Header | PS5-53-05
PS5-53-06 - Water Distribution Consumers | PS5-53-06
PS5-60-01 - Power Generation Package A | PS5-60-01
PS5-60-02 - Power Gen Package A (UCP) | PS5-60-02
PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | PS5-60-03
PS5-60-04 - Power Generation Package B | PS5-60-04
PS5-60-05 - Power Gen Package B (UCP) | PS5-60-05
PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | PS5-60-06
PS5-60-07 - Power Generation Package C | PS5-60-07
PS5-60-08 - Power Gen Package C (UCP) | PS5-60-08
PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | PS5-60-09
PS5-60-10 - Power Generation Package D | PS5-60-10
PS5-60-11 - Power Gen Package D (UCP) | PS5-60-11
PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | PS5-60-12
PS5-60-13 - Power Generation Package E | PS5-60-13
PS5-60-14 - Power Gen Package E (UCP) | PS5-60-14
PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | PS5-60-15
PS5-60-16 - Power Generation Package F | PS5-60-16
PS5-60-17 - Power Gen Package F (UCP) | PS5-60-17
PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | PS5-60-18
PS5-60-19 - Power Generation Package G | PS5-60-19
PS5-60-20 - Power Gen Package G (UCP) | PS5-60-20
PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | PS5-60-21
PS5-60-22 - Power Gen Master UCP | PS5-60-22
PS5-60-23 - Instrument Air Distribution lines | PS5-60-23
PS5-60-24 - Cooling Water Tank & Pump | PS5-60-24
PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | PS5-60-25
PS5-60-26 - Instrument Air Compressor Skid | PS5-60-26
PS5-60-27 - Compressed Air Starting Skid | PS5-60-27
PS5-60-28 - Air Receiver A & Air Regulator A | PS5-60-28
PS5-60-29 - Air Receiver B & Air Regulator B | PS5-60-29
PS5-60-30 - Air Receiver C & Air Regulator C | PS5-60-30
PS5-60-31 - Air Receiver D & Air Regulator D | PS5-60-31
PS5-60-32 - Air Receiver E & Air Regulator E | PS5-60-32
PS5-60-33 - Air Receiver F & Air Regulator F | PS5-60-33
PS5-60-34 - Air Receiver G & Air Regulator G | PS5-60-34
PS5-60-35 - Injector Tip Cooling Module A | PS5-60-35
PS5-60-36 - Injector Tip Cooling Module B | PS5-60-36
PS5-60-37 - Injector Tip Cooling Module C | PS5-60-37
PS5-60-38 - Injector Tip Cooling Module D | PS5-60-38
PS5-60-39 - Injector Tip Cooling Module E | PS5-60-39
PS5-60-40 - Injector Tip Cooling Module F | PS5-60-40
PS5-60-41 - Injector Tip Cooling Module G | PS5-60-41
PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | PS5-60-42
PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | PS5-60-43
PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | PS5-60-44
PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | PS5-60-45
PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | PS5-60-46
PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | PS5-60-47
PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | PS5-60-48
PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | PS5-60-49
PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | PS5-60-50
PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | PS5-60-51
PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | PS5-60-52
PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | PS5-60-53
PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | PS5-60-54
PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | PS5-60-55
PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | PS5-60-56
PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | PS5-60-57
PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | PS5-60-58
PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | PS5-60-59
PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | PS5-60-60
PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | PS5-60-61
PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | PS5-60-62
PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | PS5-60-63
PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | PS5-60-64
PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | PS5-60-65
PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | PS5-60-66
PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | PS5-60-67
PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | PS5-60-68
PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | PS5-60-69
PS5-60-70 - Engine A Cooling system | PS5-60-70
PS5-60-71 - Engine B Cooling system | PS5-60-71
PS5-60-72 - Engine C Cooling system | PS5-60-72
PS5-60-73 - Engine D Cooling system | PS5-60-73
PS5-60-74 - Engine E Cooling system | PS5-60-74
PS5-60-75 - Engine F Cooling system | PS5-60-75
PS5-60-76 - Engine G Cooling system | PS5-60-76
PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | PS5-61-01
PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | PS5-61-02
PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | PS5-61-03
PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | PS5-61-04
PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | PS5-61-05
PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | PS5-61-06
PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | PS5-61-07
PS5-61-08 - Electrical Control System | PS5-61-08
PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | PS5-61-09
PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | PS5-61-10
PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | PS5-61-11
PS5-61-12 - EITS 33kV Bld. Normal Auxiliary DP - PS5-61-IG-0008 | PS5-61-12
PS5-61-13 - Power Distribution Board Office Building - PS5-61-IG-0020 | PS5-61-13
PS5-61-14 - Power Distribution Board Workshop & Warehouse - PS5-61-IG-0009 | PS5-61-14
PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | PS5-62-01
PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | PS5-62-02
PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | PS5-62-03
PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | PS5-62-04
PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | PS5-62-05
PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | PS5-62-06
PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | PS5-62-07
PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | PS5-62-08
PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | PS5-62-09
PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | PS5-62-10
PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | PS5-62-11
PS5-62-12 - EITS 33kV Bld. Emergency L&SP DP - PS5-05-IG-0003 | PS5-62-12
PS5-62-13 - EITS 33kV Bld. Normal L&SP DP - PS5-61-IG-0003 | PS5-62-13
PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | PS5-62-14
PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | PS5-62-15
PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | PS5-62-16
PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | PS5-62-17
PS5-62-18 - Workshop & Warehouse Normal L&SP DB - PS5-61-IG-0004 | PS5-62-18
PS5-62-19 - Workshop & Warehouse Emergency L&SP DB - PS5-05-IG-0101 | PS5-62-19
PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | PS5-62-20
PS5-63-01 - Electrical Earthing | PS5-63-01
PS5-63-02 - Electrical Earthing - Office and Facilities building | PS5-63-02
PS5-63-03 - Electrical Earthing - Generator Building | PS5-63-03
PS5-63-04 - Electrical Earthing - EITS Building | PS5-63-04
PS5-63-05 - Electrical Earthing - Guard Hut A & B | PS5-63-05
PS5-63-06 - Electrical Earthing - Guard House | PS5-63-06
PS5-63-07 - Electrical Earthing - Workshop & Warehouse | PS5-63-07
PS5-71-01 - CFO Storage Tank Feed Heater | PS5-71-01
PS5-71-02 - CFO Allocation Metering Package | PS5-71-02
PS5-71-03 - CFO Allocation Metering Package (UCP) | PS5-71-03
PS5-71-04 - CFO Storage Tank | PS5-71-04
PS5-71-05 - CFO Transfer Pump A/B | PS5-71-05
PS5-71-06 - Crude Fuel Separation Module | PS5-71-06
PS5-71-07 - Crude Fuel Separation Module (UCP) | PS5-71-07
PS5-71-08 - CFO Pre-Pressure Modules | PS5-71-08
PS5-71-09 - CFO Pre-Pressure Modules (UCP) | PS5-71-09
PS5-71-12 - CFO Service Tank | PS5-71-12
PS5-71-13 - CFO Service Pump A/B | PS5-71-13
PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | PS5-71-14
PS5-71-15 - Diesel Fuel Storage Tank | PS5-71-15
PS5-71-16 - Diesel Fuel Supply Pump A/B | PS5-71-16
PS5-71-17 - Diesel Fuel Distribution Header | PS5-71-17
PS5-71-18 - Diesel Separator Module | PS5-71-18
PS5-71-19 - Diesel Separator Module (UCP) | PS5-71-19
PS5-71-20 - Diesel Fuel Day Tank | PS5-71-20
PS5-71-21 - Diesel Transfer Pump A/B | PS5-71-21
PS5-71-22 - Diesel Fuel Pre Pressure Module | PS5-71-22
PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | PS5-71-23
PS5-74-01 - N2 Generation Skid | PS5-74-01
PS5-74-02 - N2 Generation Skid (UCP) | PS5-74-02
PS5-74-03 - Nitrogen Receiver | PS5-74-03
PS5-74-04 - Nitrogen Distribution Header | PS5-74-04
PS5-75-01 - DRA Injection Package | PS5-75-01
PS5-75-02 - Biocide Injection Package | PS5-75-02
PS5-75-03 - Corrosion Inhibitor Injection Package | PS5-75-03
PS5-78-01 - Lifting and handling equipment | PS5-78-01
PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | PS5-79-01
PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | PS5-79-02
PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | PS5-79-03
PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | PS5-79-04
PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | PS5-79-05
PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | PS5-79-06
PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | PS5-79-07
PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | PS5-79-08
PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | PS5-79-09
PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | PS5-79-10
PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | PS5-79-11
PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | PS5-79-12
PS5-82-01 - Sanitary Sewage Collection | PS5-82-01
PS5-82-02 - Sewage Treatment Plant Package | PS5-82-02
PS5-82-03 - Sewage Treatment Plant Package (UCP) | PS5-82-03
PS5-82-04 - Sewage Treatment Plant Discharge Piping | PS5-82-04
PS5-82-05 - Office and Facilities building | PS5-82-05
PS5-82-06 - Guard House Building | PS5-82-06
PS5-82-07 - Guard Huts | PS5-82-07
PS5-83-01 - EITS Building | PS5-83-01
PS5-84-01 - Generator Building | PS5-84-01
PS5-84-02 - Workshop & Warehouse | PS5-84-02
PS5-84-03 - Shelters | PS5-84-03
PS5-86-01 - Shelters | PS5-86-01
PS5-91-01 - Multicore cables & JB | PS5-91-01
PS5-99-01 - Area Completion for Building area | PS5-99-01
PS5-99-02 - Area Completion for Utility area | PS5-99-02
PS5-99-03 - Area Completion for Power Distribution area | PS5-99-03
PS5-99-04 - Area Completion for Process area | PS5-99-04
PS5-99-05 - Area Completion for CFO area | PS5-99-05
PS5-99-06 - Area Completion for Power Generation area | PS5-99-06