## 8 · EIT CABLES
PS5 COMPLETION PLATFORM ¦ CABLES - 4870 cable(s)
# | DISC | CABLE TAG | FROM TAG | FROM DESC | FROM LOC | TO TAG | TO DESC | TO LOC | PULLING | RFI# | EIT DT | RFC DT | PUNCH
1 | Electrical | PS5-01-BE-0001 -CL01 | PS5-05-IG-0004 | Outdoor Emergency Lighting DB - Field - (South Side) | Near Export pump area | PS5-01-BE-0001 | Power Supply JB ( Deluge skid MOV's ) | Near Deluge skid | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2 | Electrical | PS5-01-FCV- 0003A-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-01-FCV- 0003A | Flow Control Valve | FIRE WATER PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
3 | Electrical | PS5-01-FCV- 0003B-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-01-FCV- 0003B | Flow Control Valve | FIRE WATER PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
4 | Electrical | PS5-01-FCV- 0004A-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-01-FCV- 0004A | Flow Control Valve | FIRE WATER PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
5 | Electrical | PS5-01-FCV- 0004B-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-01-FCV- 0004B | Flow Control Valve | FIRE WATER PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
6 | Electrical | PS5-01-FIT- 0003A-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-01-FIT- 0003A | Electromagnetic Flow Ind Transmitter | FIRE WATER PUMP AREA | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-05-0219 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
7 | Electrical | PS5-01-FIT- 0003B-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-01-FIT- 0003B | Electromagnetic Flow Ind Transmitter | FIRE WATER PUMP AREA | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-05-0219 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
8 | Electrical | PS5-01-FIT- 0004A-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-01-FIT- 0004A | Electromagnetic Flow Ind Transmitter | FIRE WATER PUMP AREA | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-05-0219 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
9 | Electrical | PS5-01-FIT- 0004B-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-01-FIT- 0004B | Electromagnetic Flow Ind Transmitter | FIRE WATER PUMP AREA | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-05-0219 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
10 | Electrical | PS5-01-IE- 0001A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-01-IE-0001A | Foam Package Pump Control Panel A | Foam Package | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
11 | Electrical | PS5-01-IE- 0001B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-01-IE-0001B | Foam Package Pump Control Panel B | Foam Package | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
12 | Electrical | PS5-01-IE- 0002A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-01-IE-0002A | Jockey Pump Control Panel A | Field_Fire Water Pump Area | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-05-0219 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
13 | Electrical | PS5-01-IE- 0002B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-01-IE-0002B | Jockey Pump Control Panel B | Field_Fire Water Pump Area | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-05-0219 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
14 | Electrical | PS5-01-IE- 0009A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-01-IE-0009A | Fire Water pump LCP A | Field_Fire Water Pump Area | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-05-0219 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
15 | Electrical | PS5-01-IE- 0009B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-01-IE-0009B | Fire Water pump LCP B | Field_Fire Water Pump Area | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-05-0219 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
16 | Electrical | PS5-01-IG-0001 -CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-01-IG-0001 | Water Mist system Distribution board | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
17 | Electrical | PS5-01-LA-0001 -CL01 | PS5-06-IG- 0001A | AC UPS Distribution Board (A) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-01-LA-0001 | HIPPS (OPPS) CABINET | EITS Building
18 | Electrical | PS5-01-LA-0001 -CL02 | PS5-06-IG- 0001B | AC UPS Distribution Board (B) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-01-LA-0001 | HIPPS (OPPS) CABINET | EITS Building
19 | Electrical | PS5-01-LA-0001 -CL03 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-01-LA-0001 | HIPPS (OPPS) CABINET | EITS Building
20 | Electrical | PS5-01-LB-0004 -CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-01-LB-0004 | Gaseous package system skid - control panel | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
21 | Electrical | PS5-01-LB-0004 -CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-01-LB-0004 | Gaseous package system skid - control panel | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
22 | Electrical | PS5-01-LB-0004 -CL03 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-01-LB-0004 | Gaseous package system skid - control panel | Generator Electrical Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
23 | Electrical | PS5-01-MOV- 8701-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-01-MOV- 8701 | Motor Operated Valve | FOAM PACKAGE |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
24 | Electrical | PS5-02-SWSI- 0001-CL01 | PS5-05-IG-0006 | Outdoor Emergency Lighting DB - Field - (North Side) | Near EDG package | PS5-02-SWSI- 0001 | Illuminated Windsock | Near Workshop | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
25 | Electrical | PS5-02-SWSI- 0003-CL01 | PS5-05-IG-0006 | Outdoor Emergency Lighting DB - Field - (North Side) | Near EDG package | PS5-02-SWSI- 0003 | Illuminated Windsock | On Piperack Near E- House |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
26 | Electrical | PS5-03-GDLHP- 0137-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-03-GDLHP- 0137 | Liquid Hydrocarbon Detector | CFO Storage Tank Area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
27 | Electrical | PS5-03-GDLHP- 0142-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-03-GDLHP- 0142 | Liquid Hydrocarbon Detector | CFO Storage Tank Area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
28 | Electrical | PS5-03-GDLHP- 0143-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-03-GDLHP- 0143 | Liquid Hydrocarbon Detector | Export Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
29 | Electrical | PS5-03-GDLHP- 0144-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-03-GDLHP- 0144 | Liquid Hydrocarbon Detector | Export Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
30 | Electrical | PS5-03-GDLHP- 0146-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-03-GDLHP- 0146 | Liquid Hydrocarbon Detector | LAUNCHER/RECEIVE R Area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
31 | Electrical | PS5-03-GDLHP- 0147-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-03-GDLHP- 0147 | Liquid Hydrocarbon Detector | Export Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
32 | Electrical | PS5-03-GDLHP- 0149-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-03-GDLHP- 0149 | Liquid Hydrocarbon Detector | Export Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
33 | Electrical | PS5-03-GDLHP- 0150-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-03-GDLHP- 0150 | Liquid Hydrocarbon Detector | Export Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
34 | Electrical | PS5-03-GDLHP- 0401-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-03-GDLHP- 0401 | Liquid Hydrocarbon Detector | Diesel Fuel Storage Area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
35 | Electrical | PS5-03-SEA- 0002-CL01 | PS5-06-IG-0006 | AC UPS DB - Guard House | Guard House | PS5-03-SEA- 0002 | LFAP - Guard House | Guard House |  |  | 2026-09-25 00:00:00 | 2026-09-25 00:00:00
36 | Electrical | PS5-03-SEA- 0003-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-03-SEA- 0003 | LFAP Panel - Power Generator building | Generator electrical building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
37 | Electrical | PS5-05-BE-0001 -CG01 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
38 | Electrical | PS5-05-BE-0001 -CL01 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
39 | Electrical | PS5-05-BE-0001 -CL02 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
40 | Electrical | PS5-05-BE-0001 -CL03 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
41 | Electrical | PS5-05-BE-0001 -CL04 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
42 | Electrical | PS5-05-BE-0001 -CL05 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
43 | Electrical | PS5-05-BE-0001 -CL06 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
44 | Electrical | PS5-05-BE-0001 -CL07 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
45 | Electrical | PS5-05-BE-0001 -CL08 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
46 | Electrical | PS5-05-BE-0001 -CL09 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
47 | Electrical | PS5-05-BE-0001 -CL10 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
48 | Electrical | PS5-05-BE-0001 -CL11 | PS5-05-DG-8100 | Emergency Diesel Engine Generator - Field | EDG Package | PS5-05-BE-0001 | EDG Power JB | Near EDG | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
49 | Electrical | PS5-05-IE-8100- CD01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
50 | Electrical | PS5-05-IE-8100- CD02 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
51 | Electrical | PS5-05-IE-8100- CD03 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
52 | Electrical | PS5-05-IE-8100- CD04 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
53 | Electrical | PS5-05-IE-8100- CD05 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
54 | Electrical | PS5-05-IE-8100- CD06 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
55 | Electrical | PS5-05-IE-8100- CD07 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
56 | Electrical | PS5-05-IE-8100- CD08 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-30 00:00:00 | CPP-RFI-68-331-05-0391 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
57 | Electrical | PS5-05-IE-8100- CD09 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
58 | Electrical | PS5-05-IE-8100- CD10 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-30 00:00:00 | CPP-RFI-68-331-05-0391 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
59 | Electrical | PS5-05-IE-8100- CD11 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
60 | Electrical | PS5-05-IE-8100- CD12 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-30 00:00:00 | CPP-RFI-68-331-05-0391 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
61 | Electrical | PS5-05-IE-8100- CD13 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-30 00:00:00 | CPP-RFI-68-331-05-0391 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
62 | Electrical | PS5-05-IE-8100- CD14 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-30 00:00:00 | CPP-RFI-68-331-05-0391 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
63 | Electrical | PS5-05-IE-8100- CD15 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-30 00:00:00 | CPP-RFI-68-331-05-0391 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
64 | Electrical | PS5-05-IE-8100- CD16 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-30 00:00:00 | CPP-RFI-68-331-05-0391 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
65 | Electrical | PS5-05-IE-8100- CD17 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-30 00:00:00 | CPP-RFI-68-331-05-0391 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
66 | Electrical | PS5-05-IE-8100- CD18 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
67 | Electrical | PS5-05-IE-8100- CD19 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
68 | Electrical | PS5-05-IE-8100- CD20 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
69 | Electrical | PS5-05-IE-8100- CD21 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-30 00:00:00 | CPP-RFI-68-331-05-0391 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
70 | Electrical | PS5-05-IE-8100- CD22 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
71 | Electrical | PS5-05-IE-8100- | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical
72 | Electrical | PS5-05-IE-8100- CD24 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
73 | Electrical | PS5-05-IE-8100- CD25 | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
74 | Electrical | PS5-05-IE-8100- CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
75 | Electrical | PS5-05-IE-8100- CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-05-IE-8100 | Unit Control Panel | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
76 | Electrical | PS5-05-IG-0004 -CD01 | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | PS5-05-IG-0004 | Outdoor Emergency Lighting DB - Field - (South Side) | Near Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
77 | Electrical | PS5-05-IG-0004 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-05-IG-0004 | Outdoor Emergency Lighting DB - Field - (South Side) | Near Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
78 | Electrical | PS5-05-IG-0006 -CD01 | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | PS5-05-IG-0006 | Outdoor Emergency Lighting DB - Field - (North Side) | Near EDG package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
79 | Electrical | PS5-05-IG-0006 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-05-IG-0006 | Outdoor Emergency Lighting DB - Field - (North Side) | Near EDG package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
80 | Electrical | PS5-05-IG-0009 -CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IG-0009 | EDG - Power Distribution Panel | EDG Skid | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
81 | Electrical | PS5-05-IG-0009 -CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-05-IG-0009 | EDG - Power Distribution Panel | EDG Skid | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
82 | Electrical | PS5-05-IG-0025 -CD01 | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | PS5-05-IG-0025 | Indoor Emergency L&SP DB - Generator Building | Generator Building | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-07-07 00:00:00 | 2026-07-07 00:00:00
83 | Electrical | PS5-05-IG-0025 -CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IG-0025 | Indoor Emergency L&SP DB - Generator Building | Generator Building | 2026-06-04 00:00:00 | CPP-RFI-68-33/1-05-0309 | 2026-07-07 00:00:00 | 2026-07-07 00:00:00
84 | Electrical | PS5-05-IG-0026 -CD01 | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | PS5-05-IG-0026 | Indoor Emergency L&SP DB - Generator Electrical Building | Generator Electrical Building | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
85 | Electrical | PS5-05-IG-0026 -CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-05-IG-0026 | Indoor Emergency L&SP DB - Generator Electrical Building | Generator Electrical Building | 2026-06-04 00:00:00 | CPP-RFI-68-33/1-05-0309 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
86 | Electrical | PS5-06-GB- 0003-CG01 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-GB-0003 | SMC Battery cubicle | Generator Electrical Building |  |  | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
87 | Electrical | PS5-06-GB- 0003-CL01 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-GB-0003 | SMC Battery cubicle | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
88 | Electrical | PS5-06-GB- 0003-CL02 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-GB-0003 | SMC Battery cubicle | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
89 | Electrical | PS5-06-GB- 0003-CL03 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-GB-0003 | SMC Battery cubicle | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
90 | Electrical | PS5-06-GB- 0003-CL04 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-GB-0003 | SMC Battery cubicle | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
91 | Electrical | PS5-06-GB- 0003-CL05 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-GB-0003 | SMC Battery cubicle | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
92 | Electrical | PS5-06-GB- 0003-CL06 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-GB-0003 | SMC Battery cubicle | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
93 | Electrical | PS5-06-GU- 0003A-CD01 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
94 | Electrical | PS5-06-GU- 0003A-CD02 | PS5-06-GB-0003 | SMC Battery cubicle | Generator Electrical Building | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
95 | Electrical | PS5-06-GU- 0003A-CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
96 | Electrical | PS5-06-GU- 0003B-CD01 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-06-GU- 0003B | AC UPS B - Generator Electrical Building | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
97 | Electrical | PS5-06-GU- 0003B-CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-06-GU- 0003B | AC UPS B - Generator Electrical Building | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
98 | Electrical | PS5-06-GU- 0003C-CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-06-GU- 0003C | AC UPS Bypass - Generator Electrical Building | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
99 | Electrical | PS5-06-GU- 0005-CL01 | PS5-05-IG-0007 | Indoor Emergency L&SP DB - Guard House | Guard House | PS5-06-GU-0005 | AC UPS - Guard House | Indoor Guard house |  |  | 2026-09-20 00:00:00 | 2026-09-20 00:00:00
100 | Electrical | PS5-06-IG- 0004A-CD01 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
101 | Electrical | PS5-06-IG- 0004A-CG01 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building |  |  | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
102 | Electrical | PS5-06-IG- 0004A-CL01 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
103 | Electrical | PS5-06-IG- 0004A-CL02 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
104 | Electrical | PS5-06-IG- 0004A-CL03 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
105 | Electrical | PS5-06-IG- 0004A-CL04 | PS5-06-GU- 0003A | AC UPS A - Generator Electrical Building | Generator Electrical Building | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
106 | Electrical | PS5-06-IG- 0004B-CD01 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
107 | Electrical | PS5-06-IG- 0004B-CG01 | PS5-06-GU- 0003B | AC UPS B - Generator Electrical Building | Generator Electrical Building | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building |  |  | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
108 | Electrical | PS5-06-IG- 0004B-CL01 | PS5-06-GU- 0003B | AC UPS B - Generator Electrical Building | Generator Electrical Building | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
109 | Electrical | PS5-06-IG- 0004B-CL02 | PS5-06-GU- 0003B | AC UPS B - Generator Electrical Building | Generator Electrical Building | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
110 | Electrical | PS5-06-IG- 0004B-CL03 | PS5-06-GU- 0003B | AC UPS B - Generator Electrical Building | Generator Electrical Building | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
111 | Electrical | PS5-06-IG- 0004B-CL04 | PS5-06-GU- 0003B | AC UPS B - Generator Electrical Building | Generator Electrical Building | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | 2026-05-25 00:00:00 | CPP-RFI-68-33/1-05-0298 | 2026-06-27 00:00:00 | 2026-06-27 00:00:00
112 | Electrical | PS5-08-01FB- 0901-CS01 | PS5-08-13CB- 1001 | TELECOM SII SP3 SAF Cabinet | EITS Building | PS5-08-01FB- 0901 | PAGA Flashing Beacon | Power generator building area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
113 | Electrical | PS5-08-01FB- 0902-CS01 | PS5-08-01FB- 0901 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0902 | PAGA Flashing Beacon | Power generator building area | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312
114 | Electrical | PS5-08-01FB- 0903-CS01 | PS5-08-01FB- 0902 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0903 | PAGA Flashing Beacon | Power generator building area
115 | Electrical | PS5-08-01FB- 0904-CS01 | PS5-08-01FB- 0903 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0904 | PAGA Flashing Beacon | Power generator building area | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312
116 | Electrical | PS5-08-01FB- 0905-CS01 | PS5-08-01FB- 0904 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0905 | PAGA Flashing Beacon | Power generator building area
117 | Electrical | PS5-08-01FB- 0906-CS01 | PS5-08-01FB- 0905 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0906 | PAGA Flashing Beacon | Power generator building area
118 | Electrical | PS5-08-01FB- 0907-CS01 | PS5-08-01FB- 0906 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0907 | PAGA Flashing Beacon | Power generator building area
119 | Electrical | PS5-08-01FB- 0908-CS01 | PS5-08-01FB- 0907 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0908 | PAGA Flashing Beacon | Power generator building area
120 | Electrical | PS5-08-01FB- 0909-CS01 | PS5-08-01FB- 0908 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0909 | PAGA Flashing Beacon | Power generator building area
121 | Electrical | PS5-08-01FB- 0910-CS01 | PS5-08-01FB- 0909 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0910 | PAGA Flashing Beacon | Power generator building area
122 | Electrical | PS5-08-01FB- 0911-CS01 | PS5-08-01FB- 0910 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0911 | PAGA Flashing Beacon | Power generator building area
123 | Electrical | PS5-08-01FB- 0912-CS01 | PS5-08-01FB- 0911 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0912 | PAGA Flashing Beacon | Power generator building area
124 | Electrical | PS5-08-01FB- 0913-CS01 | PS5-08-01FB- 0912 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 0913 | PAGA Flashing Beacon | Power generator building area | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0210
125 | Electrical | PS5-08-01FB- 0913-CS02 | PS5-08-01FB- 0913 | PAGA Flashing Beacon | Power generator building area | PS5-08-13CB- 1001 | TELECOM SII SP3 SAF Cabinet | EITS Building | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260
126 | Electrical | PS5-08-01FB- 1001-CS01 | PS5-08-13CB- 1001 | TELECOM SII SP3 SAF Cabinet | EITS Building | PS5-08-01FB- 1001 | PAGA Flashing Beacon | Power generator building area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
127 | Electrical | PS5-08-01FB- 1002-CS01 | PS5-08-01FB- 1001 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1002 | PAGA Flashing Beacon | Power generator building area
128 | Electrical | PS5-08-01FB- 1003-CS01 | PS5-08-01FB- 1002 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1003 | PAGA Flashing Beacon | Power generator building area
129 | Electrical | PS5-08-01FB- 1004-CS01 | PS5-08-01FB- 1003 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1004 | PAGA Flashing Beacon | Power generator building area
130 | Electrical | PS5-08-01FB- 1005-CS01 | PS5-08-01FB- 1004 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1005 | PAGA Flashing Beacon | Power generator building area
131 | Electrical | PS5-08-01FB- 1006-CS01 | PS5-08-01FB- 1005 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1006 | PAGA Flashing Beacon | Power generator building area
132 | Electrical | PS5-08-01FB- 1007-CS01 | PS5-08-01FB- 1006 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1007 | PAGA Flashing Beacon | Power generator building area | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312
133 | Electrical | PS5-08-01FB- 1008-CS01 | PS5-08-01FB- 1007 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1008 | PAGA Flashing Beacon | Power generator building area
134 | Electrical | PS5-08-01FB- 1009-CS01 | PS5-08-01FB- 1008 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1009 | PAGA Flashing Beacon | Power generator building area
135 | Electrical | PS5-08-01FB- 1010-CS01 | PS5-08-01FB- 1009 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1010 | PAGA Flashing Beacon | Power generator building area | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312
136 | Electrical | PS5-08-01FB- 1011-CS01 | PS5-08-01FB- 1010 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1011 | PAGA Flashing Beacon | Power generator building area
137 | Electrical | PS5-08-01FB- 1012-CS01 | PS5-08-01FB- 1011 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1012 | PAGA Flashing Beacon | Power generator building area
138 | Electrical | PS5-08-01FB- 1013-CS01 | PS5-08-01FB- 1012 | PAGA Flashing Beacon | Power generator building area | PS5-08-01FB- 1013 | PAGA Flashing Beacon | Power generator building area
139 | Electrical | PS5-08-01FB- 1013-CS02 | PS5-08-01FB- 1013 | PAGA Flashing Beacon | Power generator building area | PS5-08-13CB- 1001 | TELECOM SII SP3 SAF Cabinet | EITS Building | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260
140 | Electrical | PS5-08-01FB- 1101-CS01 | PS5-08-13CB- 1001 | TELECOM SII SP3 SAF Cabinet | EITS Building | PS5-08-01FB- 1101 | PAGA Flashing Beacon (Safe Area) | Field | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260
141 | Electrical | PS5-08-01FB- 1102-CS01 | PS5-08-01FB- 1101 | PAGA Flashing Beacon (Safe Area) | Field | PS5-08-01FB- 1102 | PAGA Flashing Beacon (Safe Area) | Field | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347
142 | Electrical | PS5-08-01FB- 1103-CS01 | PS5-08-01FB- 1102 | PAGA Flashing Beacon (Safe Area) | Field | PS5-08-01FB- 1103 | PAGA Flashing Beacon (Safe Area) | Field | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347
143 | Electrical | PS5-08-01FB- 1104-CS01 | PS5-08-01FB- 1103 | PAGA Flashing Beacon (Safe Area) | Field | PS5-08-01FB- 1104 | PAGA Flashing Beacon (Safe Area) | Field
144 | Electrical | PS5-08-01FB- 1105-CS01 | PS5-08-01FB- 1104 | PAGA Flashing Beacon (Safe Area) | Field | PS5-08-01FB- 1105 | PAGA Flashing Beacon (Safe Area) | Field | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312
145 | Electrical | PS5-08-01FB- 1106-CS01 | PS5-08-01FB- 1105 | PAGA Flashing Beacon (Safe Area) | Field | PS5-08-01FB- 1106 | PAGA Flashing Beacon (Safe Area) | Field | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347
146 | Electrical | PS5-08-01FB- 1106-CS02 | PS5-08-01FB- 1106 | PAGA Flashing Beacon (Safe Area) | Field | PS5-08-13CB- 1001 | TELECOM SII SP3 SAF Cabinet | EITS Building | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264
147 | Electrical | PS5-08-03FB- 0001-CS01 | PS5-08-11CB- 1001 | TELECOM SIE Cabinet | EITS Building | PS5-08-03FB- 0001 | TELEPHONE WITH BEACON/SOUNDER | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
148 | Electrical | PS5-08-03FB- 0002-CS01 | PS5-08-11CB- 1001 | TELECOM SIE Cabinet | EITS Building | PS5-08-03FB- 0002 | TELEPHONE WITH BEACON/SOUNDER | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
149 | Electrical | PS5-08-03FB- 0003-CS01 | PS5-08-11CB- 1201 | TELECOM SIE Cabinet | Office Building | PS5-08-03FB- 0003 | TELEPHONE WITH BEACON/SOUNDER | Field
150 | Electrical | PS5-08-03FB- 0004-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-03FB- 0004 | TELEPHONE WITH BEACON/SOUNDER | Field
151 | Electrical | PS5-08-03FB- 0101-CS01 | PS5-08-11CB- 1001 | TELECOM SIE Cabinet | EITS Building | PS5-08-03FB- 0101 | TELEPHONE WITH BEACON/SOUNDER | Field
152 | Electrical | PS5-08-03FB- 0102-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-03FB- 0102 | TELEPHONE WITH BEACON /SOUNDER | Field
153 | Electrical | PS5-08-03FB- 0103-CS01 | PS5-08-11CB- 1001 | TELECOM SIE Cabinet | EITS Building | PS5-08-03FB- 0103 | TELEPHONE WITH BEACON/SOUNDER | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
154 | Electrical | PS5-08-03FB- 1903-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-03FB- 1903 | TELEPHONE WITH BEACON/SOUNDER | Field | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347
155 | Electrical | PS5-08-03FB- 1904-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-03FB- 1904 | TELEPHONE WITH BEACON/SOUNDER | Field
156 | Electrical | PS5-08-11CB- 1501-CL01 | PS5-06-IG-0006 | AC UPS DB - Guard House | Guard House | PS5-08-11CB- 1501 | TELECOM SIE Cabinet | Guard House Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
157 | Electrical | PS5-08-11CB- 1901-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
158 | Electrical | PS5-08-11CB- 1901-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
159 | Electrical | PS5-08-11CB- 1901-CL03 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
160 | Electrical | PS5-08-12BT- 0001-CS01 | PS5-08-11CB- 1201 | TELECOM SIE Cabinet | Office Building | PS5-08-12BT- 0001 | WAP JUNCTION BOX-1 | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
161 | Electrical | PS5-08-12BT- 0104-CS01 | PS5-08-11CB- 1001 | TELECOM SIE Cabinet | EITS Building | PS5-08-12BT- 0104 | WAP JUNCTION BOX-4 | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
162 | Electrical | PS5-08-12BT- 0105-CS01 | PS5-08-11CB- 1001 | TELECOM SIE Cabinet | EITS Building | PS5-08-12BT- 0105 | WAP JUNCTION BOX-5 | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
163 | Electrical | PS5-08-12BT- 0106-CS01 | PS5-08-11CB- 1001 | TELECOM SIE Cabinet | EITS Building | PS5-08-12BT- 0106 | WAP JUNCTION BOX-6 | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
164 | Electrical | PS5-08-12BT- 0107-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-12BT- 0107 | WAP JUNCTION BOX-7 | Field
165 | Electrical | PS5-08-12BT- 0108-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-12BT- 0108 | WAP JUNCTION BOX-8 | Field
166 | Electrical | PS5-08-12BT- 0109-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-12BT- 0109 | WAP JUNCTION BOX-9 | Field
167 | Electrical | PS5-08-12BT- 1903-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-12BT- 1903 | WAP JUNCTION BOX-11 | Power generator building area
168 | Electrical | PS5-08-12BT- 1904-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-12BT- 1904 | WAP JUNCTION BOX-13 | Power generator building area
169 | Electrical | PS5-08-15CP- 0001-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-15CP- 0001 | Control Panel-1 | Field
170 | Electrical | PS5-08-15CP- 0002-CS01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-08-15CP- 0002 | Control Panel-2 | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
171 | Electrical | PS5-08-15CP- 0003-CS01 | PS5-08-11CB- 1201 | TELECOM SIE Cabinet | Office Building | PS5-08-15CP- 0003 | Control Panel-3 | Field
172 | Electrical | PS5-08-15CP- 0004-CS01 | PS5-08-11CB- 1201 | TELECOM SIE Cabinet | Office Building | PS5-08-15CP- 0004 | Control Panel-4 | Field
173 | Electrical | PS5-08-15CP- 0005-CS01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-08-15CP- 0005 | Control Panel-5 | Field
174 | Electrical | PS5-08-15CP- 0006-CS01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-08-15CP- 0006 | Control Panel-6 | Field
175 | Electrical | PS5-08-15CP- 0007-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-15CP- 0007 | Control Panel-7 | Field
176 | Electrical | PS5-08-15CP- 0008-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-15CP- 0008 | Control Panel-8 | Field
177 | Electrical | PS5-08-52BT- 0131-CS01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-08-52BT- 0131 | JUNCTION BOX PTZ CAMERA-5 | Field | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | #N/A | #N/A
178 | Electrical | PS5-08-52BT- 0132-CS01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-08-52BT- 0132 | JUNCTION BOX PTZ CAMERA-6 | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
179 | Electrical | PS5-08-52BT- 0133-CS01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-08-52BT- 0133 | JUNCTION BOX PTZ CAMERA-7 | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
180 | Electrical | PS5-08-52BT- 0134-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-52BT- 0134 | JUNCTION BOX PTZ CAMERA-8 | Field | 2026-04-30 00:00:00 | CPP-RFI-68-331-05-0238
181 | Electrical | PS5-08-52BT- 0135-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-52BT- 0135 | JUNCTION BOX PTZ CAMERA-9 | Power generator building area | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226
182 | Electrical | PS5-08-52BT- 0136-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-52BT- 0136 | JUNCTION BOX PTZ CAMERA-10 | Power generator building area | 30-April-20206 | CPP-RFI-68-331-05-0239
183 | Electrical | PS5-08-52BT- 0137-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-52BT- 0137 | JUNCTION BOX PTZ CAMERA-11 | Power generator building area | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329
184 | Electrical | PS5-08-52BT- 0138-CS01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-08-52BT- 0138 | JUNCTION BOX PTZ CAMERA-12 | Field | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260
185 | Electrical | PS5-08-52BT- 0139-CS01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-08-52BT- 0139 | JUNCTION BOX PTZ CAMERA-13 | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
186 | Electrical | PS5-08-52BT- 0140-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-52BT- 0140 | JUNCTION BOX PTZ CAMERA-14 | Power generator building area | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226
187 | Electrical | PS5-08-52BT- 0931-CS01 | PS5-08-11CB- 1201 | TELECOM SIE Cabinet | Office Building | PS5-08-52BT- 0931 | JUNCTION BOX PTZ CAMERA-2 | Field
188 | Electrical | PS5-08-52CM- 0031-CS01 | PS5-08-15CP- 0002 | Control Panel-2 | Field | PS5-08-52CM- 0031 | CCTV CAMERA | Field
189 | Electrical | PS5-08-52CM- 0032-CS01 | PS5-08-15CP- 0006 | Control Panel-6 | Field | PS5-08-52CM- 0032 | CCTV CAMERA | Field
190 | Electrical | PS5-08-52CM- 0033-CS01 | PS5-08-15CP- 0008 | Control Panel-8 | Field | PS5-08-52CM- 0033 | CCTV CAMERA | field
191 | Electrical | PS5-08-52CM- 0131-CS01 | PS5-08-52BT- 0131 | JUNCTION BOX PTZ CAMERA-5 | Field | PS5-08-52CM- 0131 | CCTV CAMERA | Field
192 | Electrical | PS5-08-52CM- 0132-CS01 | PS5-08-52BT- 0132 | JUNCTION BOX PTZ CAMERA-6 | Field | PS5-08-52CM- 0132 | CCTV CAMERA | Field
193 | Electrical | PS5-08-52CM- 0133-CS01 | PS5-08-52BT- 0133 | JUNCTION BOX PTZ CAMERA-7 | Field | PS5-08-52CM- 0133 | CCTV CAMERA | Field
194 | Electrical | PS5-08-52CM- 0134-CS01 | PS5-08-52BT- 0134 | JUNCTION BOX PTZ CAMERA-8 | Field | PS5-08-52CM- 0134 | CCTV CAMERA | Field
195 | Electrical | PS5-08-52CM- 0135-CS01 | PS5-08-52BT- 0135 | JUNCTION BOX PTZ CAMERA-9 | Power generator building area | PS5-08-52CM- 0135 | CCTV CAMERA | Power generator building area
196 | Electrical | PS5-08-52CM- 0136-CS01 | PS5-08-52BT- 0136 | JUNCTION BOX PTZ CAMERA-10 | Power generator building area | PS5-08-52CM- 0136 | CCTV CAMERA | Power generator building area
197 | Electrical | PS5-08-52CM- 0137-CS01 | PS5-08-52BT- 0137 | JUNCTION BOX PTZ CAMERA-11 | Power generator building area | PS5-08-52CM- 0137 | CCTV CAMERA | Power generator building area
198 | Electrical | PS5-08-52CM- 0138-CS01 | PS5-08-52BT- 0138 | JUNCTION BOX PTZ CAMERA-12 | Field | PS5-08-52CM- 0138 | CCTV CAMERA | Field
199 | Electrical | PS5-08-52CM- 0139-CS01 | PS5-08-52BT- 0139 | JUNCTION BOX PTZ CAMERA-13 | Field | PS5-08-52CM- 0139 | CCTV CAMERA | Field
200 | Electrical | PS5-08-52CM- 0140-CS01 | PS5-08-52BT- 0140 | JUNCTION BOX PTZ CAMERA-14 | Power generator building area | PS5-08-52CM- 0140 | CCTV CAMERA | Power generator building area
201 | Electrical | PS5-08-52CM- 0931-CS01 | PS5-08-52BT- 0931 | JUNCTION BOX PTZ CAMERA-2 | Field | PS5-08-52CM- 0931 | CCTV CAMERA | Field
202 | Electrical | PS5-08-52TK- 0031-CS01 | PS5-08-15CP- 0002 | Control Panel-2 | Field | PS5-08-52TK- 0031 | CCTV CAMERA Water Tank | Field
203 | Electrical | PS5-08-52TK- 0032-CS01 | PS5-08-15CP- 0006 | Control Panel-6 | Field | PS5-08-52TK- 0032 | CCTV CAMERA Water Tank | Field
204 | Electrical | PS5-08-52TK- 0033-CS01 | PS5-08-15CP- 0008 | Control Panel-8 | Field | PS5-08-52TK- 0033 | CCTV CAMERA Water Tank | Field
205 | Electrical | PS5-08-52TK- 0131-CS01 | PS5-08-52BT- 0131 | JUNCTION BOX PTZ CAMERA-5 | Field | PS5-08-52TK- 0131 | CCTV CAMERA Water Tank | Field
206 | Electrical | PS5-08-52TK- 0132-CS01 | PS5-08-52BT- 0132 | JUNCTION BOX PTZ CAMERA-6 | Field | PS5-08-52TK- 0132 | CCTV CAMERA Water Tank | Field
207 | Electrical | PS5-08-52TK- 0133-CS01 | PS5-08-52BT- 0133 | JUNCTION BOX PTZ CAMERA-7 | Field | PS5-08-52TK- 0133 | CCTV CAMERA Water Tank | Field
208 | Electrical | PS5-08-52TK- 0134-CS01 | PS5-08-52BT- 0134 | JUNCTION BOX PTZ CAMERA-8 | Field | PS5-08-52TK- 0134 | CCTV CAMERA Water Tank | Field
209 | Electrical | PS5-08-52TK- 0135-CS01 | PS5-08-52BT- 0135 | JUNCTION BOX PTZ CAMERA-9 | Power generator building area | PS5-08-52TK- 0135 | CCTV CAMERA Water Tank | Power generator building area
210 | Electrical | PS5-08-52TK- 0136-CS01 | PS5-08-52BT- 0136 | JUNCTION BOX PTZ CAMERA-10 | Power generator building area | PS5-08-52TK- 0136 | CCTV CAMERA Water Tank | Power generator building area
211 | Electrical | PS5-08-52TK- 0137-CS01 | PS5-08-52BT- 0137 | JUNCTION BOX PTZ CAMERA-11 | Power generator building area | PS5-08-52TK- 0137 | CCTV CAMERA Water Tank | Power generator building area
212 | Electrical | PS5-08-52TK- 0138-CS01 | PS5-08-52BT- 0138 | JUNCTION BOX PTZ CAMERA-12 | Field | PS5-08-52TK- 0138 | CCTV CAMERA Water Tank | Field
213 | Electrical | PS5-08-52TK- 0139-CS01 | PS5-08-52BT- 0139 | JUNCTION BOX PTZ CAMERA-13 | Field | PS5-08-52TK- 0139 | CCTV CAMERA Water Tank | Field
214 | Electrical | PS5-08-52TK- 0140-CS01 | PS5-08-52BT- 0140 | JUNCTION BOX PTZ CAMERA-14 | Power generator building area | PS5-08-52TK- 0140 | CCTV CAMERA Water Tank | Power generator building area
215 | Electrical | PS5-08-52TK- 0931-CS01 | PS5-08-52BT- 0931 | JUNCTION BOX PTZ CAMERA-2 | Field | PS5-08-52TK- 0931 | CCTV CAMERA Water Tank | Field
216 | Electrical | PS5-08-61BT- 0002-CS01 | PS5-08-14CB- 1201 | TELECOM SIE Cabinet | Office Building | PS5-08-61BT- 0002 | JB Meteocean - 2 | Field
217 | Electrical | PS5-08-85CP- 0024-CS01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-08-85CP- 0024 | CONTROL PANEL POB-1 | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
218 | Electrical | PS5-08-85CP- 0025-CS01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-08-85CP- 0025 | CONTROL PANEL POB-2 | Field | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215
219 | Electrical | PS5-08-85CP- 1201-CS01 | PS5-08-11CB- 1201 | TELECOM SIE Cabinet | Office Building | PS5-08-85CP- 1201 | CONTROL PANEL POB-1 | Office Building |  |  | #N/A | #N/A
220 | Electrical | PS5-08-85CP- 1202-CS01 | PS5-08-11CB- 1201 | TELECOM SIE Cabinet | Office Building | PS5-08-85CP- 1202 | CONTROL PANEL POB-2 | Office Building |  |  | #N/A | #N/A
221 | Electrical | PS5-08-85CP- 1501-CS01 | PS5-08-11CB- 1501 | TELECOM SIE Cabinet | Guard House Building | PS5-08-85CP- 1501 | ACS CONTROLLER ENCLOSURE | Guard House
222 | Electrical | PS5-08-85CP- 1601-CS01 | PS5-08-11CB- 1601 | TELECOM SIE Cabinet | Workshop & warehouse | PS5-08-85CP- 1601 | ACS CONTROLLER ENCLOSURE | Workshop & Warehouse |  |  | #N/A | #N/A
223 | Electrical | PS5-08-85CP- 1901-CS01 | PS5-08-11CB- 1901 | TELECOM SIE Cabinet | Generator Electrical Building | PS5-08-85CP- 1901 | ACS CONTROLLER ENCLOSURE | Generator Electrical Building
224 | Electrical | PS5-08-85LA- 1601-CS01 | PS5-08-11CB- 1601 | TELECOM SIE Cabinet | Workshop & warehouse | PS5-82-MTL- 0001 | Turnstile | Field
225 | Electrical | PS5-08-85LA- 1602-CS01 | PS5-08-11CB- 1601 | TELECOM SIE Cabinet | Workshop & warehouse | PS5-82-MBA- 0001 | Vehicle Barrier | Field
226 | Electrical | PS5-08-85LA- 1603-CS01 | PS5-08-11CB- 1601 | TELECOM SIE Cabinet | Workshop & warehouse | PS5-82-MBA- 0002 | Vehicle Barrier | Field
227 | Electrical | PS5-08-85LA- 1604-CS01 | PS5-08-11CB- 1601 | TELECOM SIE Cabinet | Workshop & warehouse | PS5-82-MBA- 0003 | Vehicle Barrier | Field
228 | Electrical | PS5-09-LB-0008 -CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-09-LB-0008 | HVAC UCP | Generator Electrical Buidling |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
229 | Electrical | PS5-09-LB-0008 -CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-09-LB-0008 | HVAC UCP | Generator Electrical Buidling |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
230 | Electrical | PS5-09-LB-7001 -CL01 | PS5-05-IG-0007 | Indoor Emergency L&SP DB - Guard House | Guard House | PS5-09-LB-7001 | HVAC UCP - Guard House | Guard House |  |  | 2026-10-21 00:00:00 | 2026-10-21 00:00:00
231 | Electrical | PS5-25-DM- 3100A-CD01 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
232 | Electrical | PS5-25-DM- 3100A-CG01 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
233 | Electrical | PS5-25-DM- 3100A-CG02 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
234 | Electrical | PS5-25-DM- 3100A-CH01 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
235 | Electrical | PS5-25-DM- 3100A-CH02 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
236 | Electrical | PS5-25-DM- 3100A-CH03 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
237 | Electrical | PS5-25-DM- 3100A-CH04 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
238 | Electrical | PS5-25-DM- 3100A-CH05 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
239 | Electrical | PS5-25-DM- 3100A-CH06 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
240 | Electrical | PS5-25-DM- 3100A-CL01 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
241 | Electrical | PS5-25-DM- 3100A-CL02 | PS5-61-IG-0014 | Outdoor Power DB - Field(North) | Near EITS | PS5-25-DM- 3100A | Crude Oil Export Pump A | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
242 | Electrical | PS5-25-DM- 3100B-CD01 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
243 | Electrical | PS5-25-DM- 3100B-CG01 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
244 | Electrical | PS5-25-DM- 3100B-CG02 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
245 | Electrical | PS5-25-DM- 3100B-CH01 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
246 | Electrical | PS5-25-DM- 3100B-CH02 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
247 | Electrical | PS5-25-DM- 3100B-CH03 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
248 | Electrical | PS5-25-DM- 3100B-CH04 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
249 | Electrical | PS5-25-DM- 3100B-CH05 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
250 | Electrical | PS5-25-DM- 3100B-CH06 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
251 | Electrical | PS5-25-DM- 3100B-CL01 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
252 | Electrical | PS5-25-DM- 3100B-CL02 | PS5-61-IG-0014 | Outdoor Power DB - Field(North) | Near EITS | PS5-25-DM- 3100B | Crude Oil Export Pump B | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
253 | Electrical | PS5-25-DM- 3100C-CD01 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
254 | Electrical | PS5-25-DM- 3100C-CG01 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
255 | Electrical | PS5-25-DM- 3100C-CG02 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
256 | Electrical | PS5-25-DM- 3100C-CH01 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
257 | Electrical | PS5-25-DM- 3100C-CH02 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
258 | Electrical | PS5-25-DM- 3100C-CH03 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
259 | Electrical | PS5-25-DM- 3100C-CH04 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
260 | Electrical | PS5-25-DM- 3100C-CH05 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
261 | Electrical | PS5-25-DM- 3100C-CH06 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0216 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
262 | Electrical | PS5-25-DM- 3100C-CL01 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
263 | Electrical | PS5-25-DM- 3100C-CL02 | PS5-61-IG-0014 | Outdoor Power DB - Field(North) | Near EITS | PS5-25-DM- 3100C | Crude Oil Export Pump C | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
264 | Electrical | PS5-25-DM- 3200A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 3200A | Crude Oil Export Pump A -Lube OilPump 1 Motor | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
265 | Electrical | PS5-25-DM- 3200B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 3200B | Crude Oil Export Pump A -Lube OilPump 2 Motor | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
266 | Electrical | PS5-25-DM- 3300A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 3300A | Crude Oil Export Pump B -Lube OilPump 1 Motor | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
267 | Electrical | PS5-25-DM- 3300B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 3300B | Crude Oil Export Pump B -Lube OilPump 2 Motor | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
268 | Electrical | PS5-25-DM- 3400A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 3400A | Crude Oil Export Pump C -Lube OilPump 1 Motor | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
269 | Electrical | PS5-25-DM- 3400B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 3400B | Crude Oil Export Pump C -Lube OilPump 2 Motor | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
270 | Electrical | PS5-25-DM- 6400A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 6400A | Crude Oil Export Pump A -Lube Oil Heat Exchanger Fan Motor 1 | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
271 | Electrical | PS5-25-DM- 6400B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 6400B | Crude Oil Export Pump A -Lube Oil Heat Exchanger Fan Motor 2 | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
272 | Electrical | PS5-25-DM- 6500A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 6500A | Crude Oil Export Pump B -Lube Oil Heat Exchanger Fan Motor 1 | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
273 | Electrical | PS5-25-DM- 6500B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 6500B | Crude Oil Export Pump B -Lube Oil Heat Exchanger Fan Motor 2 | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
274 | Electrical | PS5-25-DM- 6600A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 6600A | Crude Oil Export Pump C -Lube Oil Heat Exchanger Fan Motor 1 | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
275 | Electrical | PS5-25-DM- 6600B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-DM- 6600B | Crude Oil Export Pump C -Lube Oil Heat Exchanger Fan Motor 2 | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
276 | Electrical | PS5-25-ESDV- 0021-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-ESDV- 0021 | Emergency Shutdown Valve | EXPORT PUMP AREA | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
277 | Electrical | PS5-25-ESDV- 0023-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-ESDV- 0023 | Emergency Shutdown Valve | EXPORT PUMP AREA | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
278 | Electrical | PS5-25-FCV- 0003A-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-FCV- 0003A | Flow Control Valve | Export Pump Area | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
279 | Electrical | PS5-25-FCV- 0003B-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-FCV- 0003B | Flow Control Valve | Export Pump Area | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
280 | Electrical | PS5-25-FCV- 0003C-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-FCV- 0003C | Flow Control Valve | Export Pump Area | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
281 | Electrical | PS5-25-FCV- 0004-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-FCV- 0004 | Flow Control Valve | LAUNCHER/RECEIVE R AREA |  |  | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
282 | Electrical | PS5-25-FIT- 0001-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-25-FIT-0001 | Ultrasonic Flow Ind Transmitter | LAUNCHER/RECEIVE R AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
283 | Electrical | PS5-25-FIT- 0003A-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-25-FIT- 0003A | Ultrasonic Flow Ind Transmitter | Field_EXPORT PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
284 | Electrical | PS5-25-FIT- 0003B-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-25-FIT- 0003B | Ultrasonic Flow Ind Transmitter | Field_EXPORT PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
285 | Electrical | PS5-25-FIT- 0003C-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-25-FIT- 0003C | Ultrasonic Flow Ind Transmitter | Field_EXPORT PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
286 | Electrical | PS5-25-FIT- 0004-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-25-FIT-0004 | Ultrasonic Flow Ind Transmitter | LAUNCHER/RECEIVE R AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
287 | Electrical | PS5-25-HE- 2100-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-HE-2100 | Crude Oil Export Pump A -Lube Oil System Oil Reservoir Heater | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
288 | Electrical | PS5-25-HE- 2100-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-HE-2100 | Crude Oil Export Pump A -Lube Oil System Oil Reservoir Heater | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
289 | Electrical | PS5-25-HE- 2200-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-HE-2200 | Crude Oil Export Pump B -Lube Oil System Oil Reservoir Heater | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
290 | Electrical | PS5-25-HE- 2200-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-HE-2200 | Crude Oil Export Pump B -Lube Oil System Oil Reservoir Heater | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
291 | Electrical | PS5-25-HE- 2300-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-HE-2300 | Crude Oil Exp Pump C - Lube Oil System Oil Reservoir Heater | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
292 | Electrical | PS5-25-HE- 2300-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-HE-2300 | Crude Oil Exp Pump C - Lube Oil System Oil Reservoir Heater | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
293 | Electrical | PS5-25-IE-0001- CL01 | PS5-06-IG- 0001A | AC UPS Distribution Board (A) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-25-IE-0001 | VTMS Cabinet for Export Pump cabinet | EITS Building
294 | Electrical | PS5-25-IE-0001- CL02 | PS5-06-IG- 0001B | AC UPS Distribution Board (B) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-25-IE-0001 | VTMS Cabinet for Export Pump cabinet | EITS Building
295 | Electrical | PS5-25-IE-0001- CL03 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-25-IE-0001 | VTMS Cabinet for Export Pump cabinet | EITS Building
296 | Electrical | PS5-25-IES- 3100A-CD01 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-IES- 3100A | Crude Oil Export Pump A -LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
297 | Electrical | PS5-25-IES- 3100B-CD01 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-IES- 3100B | Crude Oil Export Pump B -LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
298 | Electrical | PS5-25-IES- 3100C-CD01 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-25-IES- 3100C | Crude Oil Export Pump C -LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
299 | Electrical | PS5-25-IES- 3200A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 3200A | Crude Oil Export Pump A -Lube OilPump 1 Motor- LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
300 | Electrical | PS5-25-IES- 3200B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 3200B | Crude Oil Export Pump A -Lube OilPump 2 Motor- LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
301 | Electrical | PS5-25-IES- 3300A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 3300A | Crude Oil Export Pump B -Lube OilPump 1 Motor- LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
302 | Electrical | PS5-25-IES- 3300B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 3300B | Crude Oil Export Pump B -Lube OilPump 2 Motor- LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
303 | Electrical | PS5-25-IES- 3400A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 3400A | Crude Oil Export Pump C -Lube OilPump 1 Motor- LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
304 | Electrical | PS5-25-IES- 3400B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 3400B | Crude Oil Export Pump C -Lube OilPump 2 Motor- LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
305 | Electrical | PS5-25-IES- 6400A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 6400A | Crude Oil Export Pump A -Lube Oil Heat Exchanger Fan Motor 1-LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
306 | Electrical | PS5-25-IES- 6400B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 6400B | Crude Oil Export Pump A -Lube Oil Heat Exchanger Fan Motor 2-LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
307 | Electrical | PS5-25-IES- 6500A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 6500A | Crude Oil Export Pump B -Lube Oil Heat Exchanger Fan Motor 1-LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
308 | Electrical | PS5-25-IES- 6500B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 6500B | Crude Oil Export Pump B -Lube Oil Heat Exchanger Fan Motor 2-LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
309 | Electrical | PS5-25-IES- 6600A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 6600A | Crude Oil Export Pump C -Lube Oil Heat Exchanger Fan Motor 1-LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
310 | Electrical | PS5-25-IES- 6600B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-IES- 6600B | Crude Oil Export Pump C -Lube Oil Heat Exchanger Fan Motor 2-LCS | Export Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
311 | Electrical | PS5-25-MOV- 0001-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-MOV- 0001 | Motor Operated Valve | LAUNCHER/RECEIVE R AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
312 | Electrical | PS5-25-MOV- 0002-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-MOV- 0002 | Motor Operated Valve | LAUNCHER/RECEIVE R AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
313 | Electrical | PS5-25-MOV- 0003-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-MOV- 0003 | Motor Operated Valve | LAUNCHER/RECEIVE R AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
314 | Electrical | PS5-25-MOV- 0008-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-MOV- 0008 | Motor Operated Valve | LAUNCHER/RECEIVE R AREA | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
315 | Electrical | PS5-25-MOV- 0011-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-MOV- 0011 | Motor Operated Valve | LAUNCHER/RECEIVE R AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
316 | Electrical | PS5-25-MOV- 0012-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-MOV- 0012 | Motor Operated Valve | LAUNCHER/RECEIVE R AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
317 | Electrical | PS5-25-MOV- 0025-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-MOV- 0025 | Motor Operated Valve | LAUNCHER/RECEIVE R AREA | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
318 | Electrical | PS5-25-MOV- 0026-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-MOV- 0026 | Motor Operated Valve | LAUNCHER/RECEIVE R AREA | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
319 | Electrical | PS5-25-MOV- 0027-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-MOV- 0027 | Motor Operated Valve | LAUNCHER/RECEIVE R AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
320 | Electrical | PS5-25-MOV- 0028-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-MOV- 0028 | Motor Operated Valve | LAUNCHER/RECEIVE R AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
321 | Electrical | PS5-25-SDV- 0022-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0022 | Shutdown Valve | LAUNCHER/RECEIVE R AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
322 | Electrical | PS5-25-SDV- 0035A-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0035A | Shutdown Valve | EXPORT PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
323 | Electrical | PS5-25-SDV- 0035B-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0035B | Shutdown Valve | EXPORT PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
324 | Electrical | PS5-25-SDV- 0035C-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0035C | Shutdown Valve | EXPORT PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
325 | Electrical | PS5-25-SDV- 0036A-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0036A | Shutdown Valve | EXPORT PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
326 | Electrical | PS5-25-SDV- 0036B-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0036B | Shutdown Valve | EXPORT PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
327 | Electrical | PS5-25-SDV- 0036C-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0036C | Shutdown Valve | EXPORT PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
328 | Electrical | PS5-25-SDV- 0046-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0046 | Shutdown Valve | LAUNCHER/RECEIVE R AREA | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
329 | Electrical | PS5-25-SDV- 0052-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0052 | Shutdown Valve | EXPORT PUMP AREA | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
330 | Electrical | PS5-25-SDV- 0054A-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0054A | Shutdown Valve | EXPORT PUMP AREA | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
331 | Electrical | PS5-25-SDV- 0054B-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0054B | Shutdown Valve | EXPORT PUMP AREA | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
332 | Electrical | PS5-25-SDV- 0054C-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-25-SDV- 0054C | Shutdown Valve | EXPORT PUMP AREA | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
333 | Electrical | PS5-25-UD- 3100A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-25-UD- 3100A | 5 pin 32A plug and socket for Oil Purifier Control Panel | Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
334 | Electrical | PS5-25-XV-0053 -CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-XV-0053 | On / Off Valve | LAUNCHER/RECEIVE R AREA | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0210 | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
335 | Electrical | PS5-25-XV-0070 -CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-25-XV-0070 | On / Off Valve | LAUNCHER/RECEIVE R AREA |  |  | 2026-08-31 00:00:00 | 2026-08-31 00:00:00
336 | Electrical | PS5-26-LA-0001 -CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-26-LA-0001 | UCP for PS5 Crude Fuel Oil Consumption Meter for Power Gen Package | EITS Building
337 | Electrical | PS5-26-LA-0001 -CL02 | PS5-06-IG- 0001A | AC UPS Distribution Board (A) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-26-LA-0001 | UCP for PS5 Crude Fuel Oil Consumption Meter for Power Gen Package | EITS Building
338 | Electrical | PS5-26-LA-0001 -CL03 | PS5-06-IG- 0001B | AC UPS Distribution Board (B) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-26-LA-0001 | UCP for PS5 Crude Fuel Oil Consumption Meter for Power Gen Package | EITS Building
339 | Electrical | PS5-28-BE- 0002A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-BE- 0002A | Reinjection Pump A Electrical Junction box | Reinjection Pump | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
340 | Electrical | PS5-28-BE- 0002A-CL02 | PS5-61-IG-0007 | Outdoor Normal Lighting DB - Field - (North Side) | Near EDG package | PS5-28-BE- 0002A | Reinjection Pump A Electrical Junction box | Reinjection Pump | 2026-04-30 00:00:00 | CPP-RFI-68-331-05-0238 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
341 | Electrical | PS5-28-BE- 0002B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-BE- 0002B | Reinjection Pump B Electrical Junction box | Reinjection Pump | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
342 | Electrical | PS5-28-BE- 0002B-CL02 | PS5-61-IG-0007 | Outdoor Normal Lighting DB - Field - (North Side) | Near EDG package | PS5-28-BE- 0002B | Reinjection Pump B Electrical Junction box | Reinjection Pump | 2026-04-30 00:00:00 | CPP-RFI-68-331-05-0238 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
343 | Electrical | PS5-28-DM- 31100-CL01 | PS5-28-ISO- 2008 | Socket Outlet - Oil Skimmer package | Near Observation Basin | PS5-28-DM- 31100 | Oil Skimmer Motor | Oil Skimmer Package |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
344 | Electrical | PS5-28-DM- 3300-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3300 | Relief Drum Pump | Relief Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-21 00:00:00 | 2026-09-21 00:00:00
345 | Electrical | PS5-28-DM- 3400-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3400 | Closed Drain Drum 01 Pump Motor | Closed Drain Drum Area | 2026-04-30 00:00:00 | CPP-RFI-68-331-05-0238 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
346 | Electrical | PS5-28-DM- 3500-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3500 | Oily Water Sump Pump | Oily Water Sump Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
347 | Electrical | PS5-28-DM- 3600A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3600A | Open Drain Sump Pump A | Oily Water Sump Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
348 | Electrical | PS5-28-DM- 3600A-CL02 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3600A | Open Drain Sump Pump A | Oily Water Sump Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
349 | Electrical | PS5-28-DM- 3600B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3600B | Open Drain Sump Pump B | Oily Water Sump Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
350 | Electrical | PS5-28-DM- 3600B-CL02 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3600B | Open Drain Sump Pump B | Oily Water Sump Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
351 | Electrical | PS5-28-DM- 3700A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3700A | Closed Drain Drum 02 Pump Motor A | Near CRO Gen Area | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
352 | Electrical | PS5-28-DM- 3700B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3700B | Closed Drain Drum 02 Pump Motor B | Closed Drain Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
353 | Electrical | PS5-28-DM- 3800A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3800A | Seal Oil Drain Drum Pump A | Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-21 00:00:00 | 2026-09-21 00:00:00
354 | Electrical | PS5-28-DM- 3800B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3800B | Seal Oil Drain Drum Pump B | Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-21 00:00:00 | 2026-09-21 00:00:00
355 | Electrical | PS5-28-DM- 3800C-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3800C | Seal Oil Drain Drum Pump C | Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
356 | Electrical | PS5-28-DM- 3900A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3900A | Reinjection Pump A | Closed Drain Drum Area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
357 | Electrical | PS5-28-DM- 3900B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-DM- 3900B | Reinjection Pump B | Closed Drain Drum Area | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
358 | Electrical | PS5-28-HE- 2100-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-HE-2100 | Closed Drain Drum 01 Heater | Closed Drain Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
359 | Electrical | PS5-28-HE- 2100-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-HE-2100 | Closed Drain Drum 01 Heater | Closed Drain Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
360 | Electrical | PS5-28-HE- 2100-CL02 | PS5-61-IG-0007 | Outdoor Normal Lighting DB - Field - (North Side) | Near EDG package | PS5-28-HE-2100 | Closed Drain Drum 01 Heater | Closed Drain Drum Area | 2026-04-30 00:00:00 | CPP-RFI-68-331-05-0238 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
361 | Electrical | PS5-28-HE- 2200-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-HE-2200 | Closed Drain Drum 02 Heater | Closed Drain Drum Area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
362 | Electrical | PS5-28-HE- 2200-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-HE-2200 | Closed Drain Drum 02 Heater | Closed Drain Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
363 | Electrical | PS5-28-HE- 2200-CL02 | PS5-61-IG-0007 | Outdoor Normal Lighting DB - Field - (North Side) | Near EDG package | PS5-28-HE-2200 | Closed Drain Drum 02 Heater | Closed Drain Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
364 | Electrical | PS5-28-IES- 2008-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES-2008 | Oil Skimmer Package - LCS | Near Oil skimmer package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
365 | Electrical | PS5-28-IES- 3300-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES-3300 | Relief Drum Pump-LCS | Relief Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-21 00:00:00 | 2026-09-21 00:00:00
366 | Electrical | PS5-28-IES- 3400-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES-3400 | Closed Drain Drum 01 Pump Motor-LCS | Closed Drain Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
367 | Electrical | PS5-28-IES- 3500-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES-3500 | Oily Water Sump Pump- LCS | Oily Water Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
368 | Electrical | PS5-28-IES- 3600A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES- 3600A | Open Drain Sump Pump A-LCS | Oily Water Area | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
369 | Electrical | PS5-28-IES- 3600B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES- 3600B | Open Drain Sump Pump B-LCS | Oily Water Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
370 | Electrical | PS5-28-IES- 3700A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES- 3700A | Closed Drain Drum 02 Pump Motor A-LCS | Near CRO Gen Area | 30-April-20206 | CPP-RFI-68-331-05-0239 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
371 | Electrical | PS5-28-IES- 3700B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES- 3700B | Closed Drain Drum 02 Pump Motor B-LCS | Closed Drain Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
372 | Electrical | PS5-28-IES- 3800A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES- 3800A | Seal Oil Drain Drum Pump A -LCS | Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-21 00:00:00 | 2026-09-21 00:00:00
373 | Electrical | PS5-28-IES- 3800B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES- 3800B | Seal Oil Drain Drum Pump B-LCS | Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-21 00:00:00 | 2026-09-21 00:00:00
374 | Electrical | PS5-28-IES- 3800C-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES- 3800C | Seal Oil Drain Drum Pump C-LCS | Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
375 | Electrical | PS5-28-IES- 3900A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES- 3900A | Reinjection Pump A-LCS | Closed Drain Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
376 | Electrical | PS5-28-IES- 3900B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-IES- 3900B | Reinjection Pump B-LCS | Closed Drain Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
377 | Electrical | PS5-28-ISO- 2008-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-28-ISO- 2008 | Socket Outlet - Oil Skimmer package | Near Observation Basin | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
378 | Electrical | PS5-28-LB-8200 -CL01 | PS5-61-IG-0007 | Outdoor Normal Lighting DB - Field - (North Side) | Near EDG package | PS5-28-LB-8200 | Open Drain Interceptor Panel | OPERATION AND M AINTENANCE AREA | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
379 | Electrical | PS5-28-SDV- 0045-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-28-SDV- 0045 | Shutdown Valve | LAUNCHER/RECEIVE R AREA |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
380 | Electrical | PS5-28-SDV- 0053A-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-28-SDV- 0053A | Shutdown Valve | EXPORT PUMP AREA | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-09-21 00:00:00 | 2026-09-21 00:00:00
381 | Electrical | PS5-28-SDV- 0053B-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-28-SDV- 0053B | Shutdown Valve | EXPORT PUMP AREA | 30-April-20206 | CPP-RFI-68-331-05-0239 | 2026-09-21 00:00:00 | 2026-09-21 00:00:00
382 | Electrical | PS5-28-SDV- 0053C-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-28-SDV- 0053C | Shutdown Valve | EXPORT PUMP AREA | 2026-04-30 00:00:00 | CPP-RFI-68-331-05-0238 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
383 | Electrical | PS5-50-IE-0001- CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-50-IE-0001 | Water Well Submersible Pump Control Panel A | Near Submerssiblre pump | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
384 | Electrical | PS5-50-IE-0002- CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-50-IE-0002 | Water Well Submersible Pump Control Panel B | Near Submerssiblre pump | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
385 | Electrical | PS5-53-DM- 3100A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-53-DM- 3100A | Water Distribution Pump A | Water Treatment Package Area | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-07-0220 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
386 | Electrical | PS5-53-DM- 3100B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-53-DM- 3100B | Water Distribution Pump B | Water Treatment Package Area | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-07-0220 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
387 | Electrical | PS5-53-IES- 3100A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-53-IES- 3100A | Water Distribution Pump A-LCS | Water Treatment Package Area | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-07-0220 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
388 | Electrical | PS5-53-IES- 3100B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-53-IES- 3100B | Water Distribution Pump B-LCS | Water Treatment Package Area | 2026-04-16 00:00:00 | CPP-RFI-68-33/1-07-0220 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
389 | Electrical | PS5-53-IN-0001 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-53-IN-0001 | Water Treatment Package MCC | Water Treatment Pre Package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
390 | Electrical | PS5-53-IN-0001 -CL02 | PS5-06-IG- 0001A | AC UPS Distribution Board (A) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-53-IN-0001 | Water Treatment Package MCC | Water Treatment Pre Package | 2026-05-24 00:00:00 | CPP-RFI-68-331-05-0295 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
391 | Electrical | PS5-53-IN-0001 -CL03 | PS5-06-IG- 0001B | AC UPS Distribution Board (B) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-53-IN-0001 | Water Treatment Package MCC | Water Treatment Pre Package | 2026-05-24 00:00:00 | CPP-RFI-68-331-05-0295 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
392 | Electrical | PS5-60-BE-0001 -CL01 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE-0001 | Compressed air skid Battery Charger - JB | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
393 | Electrical | PS5-60-BE-0001 -CL02 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE-0001 | Compressed air skid Battery Charger - JB | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
394 | Electrical | PS5-60-BE-0001 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical | PS5-60-BE-0001 | Compressed air skid Battery Charger - JB | Generator Building
395 | Electrical | PS5-60-BE-0001 -CL04 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-BE-0001 | Compressed air skid Battery Charger - JB | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
396 | Electrical | PS5-60-BE-0002 -CL01 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE-0002 | Compressed air Instru. skid Battery Charger - JB | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
397 | Electrical | PS5-60-BE-0002 -CL02 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE-0002 | Compressed air Instru. skid Battery Charger - JB | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
398 | Electrical | PS5-60-BE-0002 -CL03 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE-0002 | Compressed air Instru. skid Battery Charger - JB | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
399 | Electrical | PS5-60-BE-0002 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical | PS5-60-BE-0002 | Compressed air Instru. skid Battery Charger - JB | Generator Building
400 | Electrical | PS5-60-BE-0002 -CL05 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-BE-0002 | Compressed air Instru. skid Battery Charger - JB | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
401 | Electrical | PS5-60-BE- 0003A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0003A | JWH- Generator set-1 (A) - JW power connection JB | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
402 | Electrical | PS5-60-BE- 0003B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0003B | JWH- Generator set-1 (B) - JW power connection JB | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
403 | Electrical | PS5-60-BE- 0003C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0003C | JWH- Generator set-1 (C) - JW power connection JB | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
404 | Electrical | PS5-60-BE- 0003D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0003D | JWH- Generator set-1 (D) - JW power connection JB | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
405 | Electrical | PS5-60-BE- 0003E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0003E | JWH- Generator set-1 (E) - JW power connection JB | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
406 | Electrical | PS5-60-BE- 0003F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0003F | JWH- Generator set-1 (F) - JW power connection JB | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
407 | Electrical | PS5-60-BE- 0003G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0003G | JWH- Generator set-1 (G) - JW power connection JB | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
408 | Electrical | PS5-60-BE- 0004A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0004A | Lube oil separator (heater) - JB | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
409 | Electrical | PS5-60-BE- 0004B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0004B | Lube oil separator (heater) - JB | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
410 | Electrical | PS5-60-BE- 0004C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0004C | Lube oil separator (heater) - JB | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
411 | Electrical | PS5-60-BE- 0004D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0004D | Lube oil separator (heater) - JB | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
412 | Electrical | PS5-60-BE- 0004E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0004E | Lube oil separator (heater) - JB | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
413 | Electrical | PS5-60-BE- 0004F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0004F | Lube oil separator (heater) - JB | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
414 | Electrical | PS5-60-BE- 0004G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0004G | Lube oil separator (heater) - JB | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
415 | Electrical | PS5-60-BE- 0005A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0005A | CRO Gen Pre-Lube and Barring Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
416 | Electrical | PS5-60-BE- 0005B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0005B | CRO Gen Pre-Lube and Barring Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
417 | Electrical | PS5-60-BE- 0005C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0005C | CRO Gen Pre-Lube and Barring Junction Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
418 | Electrical | PS5-60-BE- 0005D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0005D | CRO Gen Pre-Lube and Barring Junction Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
419 | Electrical | PS5-60-BE- 0005E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0005E | CRO Gen Pre-Lube and Barring Junction Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
420 | Electrical | PS5-60-BE- 0005F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0005F | CRO Gen Pre-Lube and Barring Junction Box | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
421 | Electrical | PS5-60-BE- 0005G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0005G | CRO Gen Pre-Lube and Barring Junction Box | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
422 | Electrical | PS5-60-BE- 0007A-CL01 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BE- 0007A | FCU- fuel conditioning module Generator set-1 (A) Trace heater Power JB-3 | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
423 | Electrical | PS5-60-BE- 0007A-CL02 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BE- 0007A | FCU- fuel conditioning module Generator set-1 (A) Trace heater Power JB-3 | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
424 | Electrical | PS5-60-BE- 0007A-CL03 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BE- 0007A | FCU- fuel conditioning module Generator set-1 (A) Trace heater Power JB-3 | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
425 | Electrical | PS5-60-BE- 0007B-CL01 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BE- 0007B | FCU- fuel conditioning module Generator set-2 (B) Trace heater Power JB-3 | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
426 | Electrical | PS5-60-BE- 0007B-CL02 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BE- 0007B | FCU- fuel conditioning module Generator set-2 (B) Trace heater Power JB-3 | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
427 | Electrical | PS5-60-BE- 0007B-CL03 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BE- 0007B | FCU- fuel conditioning module Generator set-2 (B) Trace heater Power JB-3 | Generator Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
428 | Electrical | PS5-60-BE- 0007C-CL01 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BE- 0007C | FCU- fuel conditioning module Generator set-3 (C) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
429 | Electrical | PS5-60-BE- 0007C-CL02 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BE- 0007C | FCU- fuel conditioning module Generator set-3 (C) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
430 | Electrical | PS5-60-BE- 0007C-CL03 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BE- 0007C | FCU- fuel conditioning module Generator set-3 (C) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
431 | Electrical | PS5-60-BE- 0007D-CL01 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BE- 0007D | FCU- fuel conditioning module Generator set-4 (D) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
432 | Electrical | PS5-60-BE- 0007D-CL02 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BE- 0007D | FCU- fuel conditioning module Generator set-4 (D) Trace heater Power JB-3 | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
433 | Electrical | PS5-60-BE- 0007D-CL03 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BE- 0007D | FCU- fuel conditioning module Generator set-4 (D) Trace heater Power JB-3 | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
434 | Electrical | PS5-60-BE- 0007E-CL01 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BE- 0007E | FCU- fuel conditioning module Generator set-5 (E) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
435 | Electrical | PS5-60-BE- 0007E-CL02 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BE- 0007E | FCU- fuel conditioning module Generator set-5 (E) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
436 | Electrical | PS5-60-BE- 0007E-CL03 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BE- 0007E | FCU- fuel conditioning module Generator set-5 (E) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
437 | Electrical | PS5-60-BE- 0007F-CL01 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BE- 0007F | FCU- fuel conditioning module Generator set-6 (6) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
438 | Electrical | PS5-60-BE- 0007F-CL02 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BE- 0007F | FCU- fuel conditioning module Generator set-6 (6) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
439 | Electrical | PS5-60-BE- 0007F-CL03 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BE- 0007F | FCU- fuel conditioning module Generator set-6 (6) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
440 | Electrical | PS5-60-BE- 0007G-CL01 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BE- 0007G | FCU- fuel conditioning module Generator set-7 (G) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
441 | Electrical | PS5-60-BE- 0007G-CL02 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BE- 0007G | FCU- fuel conditioning module Generator set-7 (G) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
442 | Electrical | PS5-60-BE- 0007G-CL03 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BE- 0007G | FCU- fuel conditioning module Generator set-7 (G) Trace heater Power JB-3 | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
443 | Electrical | PS5-60-BE- 0011A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011A | CRO Generator- PowerJB | Near Generator Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
444 | Electrical | PS5-60-BE- 0011A-CL02 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011A | CRO Generator- PowerJB | Near Generator Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
445 | Electrical | PS5-60-BE- 0011A-CL03 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011A | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
446 | Electrical | PS5-60-BE- 0011A-CL04 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011A | CRO Generator- PowerJB | Near Generator Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
447 | Electrical | PS5-60-BE- 0011A-CL05 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011A | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
448 | Electrical | PS5-60-BE- 0011A-CL06 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011A | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
449 | Electrical | PS5-60-BE- 0011B-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
450 | Electrical | PS5-60-BE- 0011B-CL02 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
451 | Electrical | PS5-60-BE- 0011B-CL03 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
452 | Electrical | PS5-60-BE- 0011B-CL04 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
453 | Electrical | PS5-60-BE- 0011B-CL05 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
454 | Electrical | PS5-60-BE- 0011B-CL06 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0011B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
455 | Electrical | PS5-60-BE- 0012A-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012A | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
456 | Electrical | PS5-60-BE- 0012A-CL02 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012A | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
457 | Electrical | PS5-60-BE- 0012A-CL03 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012A | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
458 | Electrical | PS5-60-BE- 0012A-CL04 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012A | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
459 | Electrical | PS5-60-BE- 0012A-CL05 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012A | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
460 | Electrical | PS5-60-BE- 0012A-CL06 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012A | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
461 | Electrical | PS5-60-BE- 0012B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
462 | Electrical | PS5-60-BE- 0012B-CL02 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
463 | Electrical | PS5-60-BE- 0012B-CL03 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
464 | Electrical | PS5-60-BE- 0012B-CL04 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
465 | Electrical | PS5-60-BE- 0012B-CL05 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012B | CRO Generator- PowerJB | Near Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
466 | Electrical | PS5-60-BE- 0012B-CL06 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0012B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
467 | Electrical | PS5-60-BE- 0013A-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
468 | Electrical | PS5-60-BE- 0013A-CL02 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
469 | Electrical | PS5-60-BE- 0013A-CL03 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
470 | Electrical | PS5-60-BE- 0013A-CL04 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
471 | Electrical | PS5-60-BE- 0013A-CL05 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
472 | Electrical | PS5-60-BE- 0013A-CL06 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
473 | Electrical | PS5-60-BE- 0013B-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
474 | Electrical | PS5-60-BE- 0013B-CL02 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
475 | Electrical | PS5-60-BE- 0013B-CL03 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
476 | Electrical | PS5-60-BE- 0013B-CL04 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
477 | Electrical | PS5-60-BE- 0013B-CL05 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
478 | Electrical | PS5-60-BE- 0013B-CL06 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0013B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
479 | Electrical | PS5-60-BE- 0014A-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
480 | Electrical | PS5-60-BE- 0014A-CL02 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
481 | Electrical | PS5-60-BE- 0014A-CL03 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
482 | Electrical | PS5-60-BE- 0014A-CL04 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
483 | Electrical | PS5-60-BE- 0014A-CL05 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
484 | Electrical | PS5-60-BE- 0014A-CL06 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
485 | Electrical | PS5-60-BE- 0014B-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
486 | Electrical | PS5-60-BE- 0014B-CL02 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
487 | Electrical | PS5-60-BE- 0014B-CL03 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
488 | Electrical | PS5-60-BE- 0014B-CL04 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
489 | Electrical | PS5-60-BE- 0014B-CL05 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
490 | Electrical | PS5-60-BE- 0014B-CL06 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0014B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
491 | Electrical | PS5-60-BE- 0015A-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
492 | Electrical | PS5-60-BE- 0015A-CL02 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
493 | Electrical | PS5-60-BE- 0015A-CL03 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
494 | Electrical | PS5-60-BE- 0015A-CL04 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
495 | Electrical | PS5-60-BE- 0015A-CL05 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
496 | Electrical | PS5-60-BE- 0015A-CL06 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
497 | Electrical | PS5-60-BE- 0015B-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
498 | Electrical | PS5-60-BE- 0015B-CL02 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
499 | Electrical | PS5-60-BE- 0015B-CL03 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
500 | Electrical | PS5-60-BE- 0015B-CL04 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
501 | Electrical | PS5-60-BE- 0015B-CL05 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
502 | Electrical | PS5-60-BE- 0015B-CL06 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0015B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
503 | Electrical | PS5-60-BE- 0016A-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016A | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
504 | Electrical | PS5-60-BE- 0016A-CL02 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016A | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
505 | Electrical | PS5-60-BE- 0016A-CL03 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016A | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
506 | Electrical | PS5-60-BE- 0016A-CL04 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016A | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
507 | Electrical | PS5-60-BE- 0016A-CL05 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016A | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
508 | Electrical | PS5-60-BE- 0016A-CL06 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016A | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
509 | Electrical | PS5-60-BE- 0016B-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016B | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
510 | Electrical | PS5-60-BE- 0016B-CL02 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016B | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
511 | Electrical | PS5-60-BE- 0016B-CL03 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016B | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
512 | Electrical | PS5-60-BE- 0016B-CL04 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016B | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
513 | Electrical | PS5-60-BE- 0016B-CL05 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016B | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
514 | Electrical | PS5-60-BE- 0016B-CL06 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0016B | CRO Generator- Control JB | Near Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
515 | Electrical | PS5-60-BE- 0017A-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
516 | Electrical | PS5-60-BE- 0017A-CL02 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
517 | Electrical | PS5-60-BE- 0017A-CL03 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
518 | Electrical | PS5-60-BE- 0017A-CL04 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
519 | Electrical | PS5-60-BE- 0017A-CL05 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
520 | Electrical | PS5-60-BE- 0017A-CL06 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017A | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
521 | Electrical | PS5-60-BE- 0017B-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
522 | Electrical | PS5-60-BE- 0017B-CL02 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
523 | Electrical | PS5-60-BE- 0017B-CL03 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
524 | Electrical | PS5-60-BE- 0017B-CL04 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
525 | Electrical | PS5-60-BE- 0017B-CL05 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
526 | Electrical | PS5-60-BE- 0017B-CL06 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0017B | CRO Generator- PowerJB | Near Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
527 | Electrical | PS5-60-BE- 0021A-CL01 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0021A | Chimney (1) Aviation Lights - JB | Generator Building | 2026-06-04 00:00:00 | CPP-RFI-68-33/1-05-0309 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
528 | Electrical | PS5-60-BE- 0021B-CL01 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0021B | Chimney (2) Aviation Lights - JB | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
529 | Electrical | PS5-60-BE- 0024A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0024A | Tip Cooling Pump motor - Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
530 | Electrical | PS5-60-BE- 0024A-CL02 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0024A | Tip Cooling Pump motor - Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
531 | Electrical | PS5-60-BE- 0024B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0024B | Tip Cooling Pump motor - Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
532 | Electrical | PS5-60-BE- 0024B-CL02 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0024B | Tip Cooling Pump motor - Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
533 | Electrical | PS5-60-BE- 0024C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0024C | Tip Cooling Pump motor - Junction Box | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
534 | Electrical | PS5-60-BE- 0024C-CL02 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0024C | Tip Cooling Pump motor - Junction Box | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
535 | Electrical | PS5-60-BE- 0024D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0024D | Tip Cooling Pump motor - Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
536 | Electrical | PS5-60-BE- 0024D-CL02 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0024D | Tip Cooling Pump motor - Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
537 | Electrical | PS5-60-BE- 0024E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0024E | Tip Cooling Pump motor - Junction Box | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
538 | Electrical | PS5-60-BE- 0024E-CL02 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0024E | Tip Cooling Pump motor - Junction Box | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
539 | Electrical | PS5-60-BE- 0024F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0024F | Tip Cooling Pump motor - Junction Box | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
540 | Electrical | PS5-60-BE- 0024F-CL02 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0024F | Tip Cooling Pump motor - Junction Box | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
541 | Electrical | PS5-60-BE- 0024G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0024G | Tip Cooling Pump motor - Junction Box | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
542 | Electrical | PS5-60-BE- 0024G-CL02 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0024G | Tip Cooling Pump motor - Junction Box | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
543 | Electrical | PS5-60-BE- 0025A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0025A | Junction Box - Injector Tip Cooling Radiator (A)- OIL cooler | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
544 | Electrical | PS5-60-BE- 0025B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0025B | Junction Box - Injector Tip Cooling Radiator (B)- OIL cooler | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
545 | Electrical | PS5-60-BE- 0025C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0025C | Junction Box - Injector Tip Cooling Radiator (C)- OIL cooler | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
546 | Electrical | PS5-60-BE- 0025D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0025D | Junction Box - njector Tip Cooling Radiator (D)- OIL cooler | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
547 | Electrical | PS5-60-BE- 0025E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0025E | Junction Box - Injector Tip Cooling Radiator (E)- OIL cooler | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
548 | Electrical | PS5-60-BE- 0025F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0025F | Junction Box - Injector Tip Cooling Radiator (F)- OIL cooler | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
549 | Electrical | PS5-60-BE- 0025G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0025G | Junction Box - Injector Tip Cooling Radiator (G)- OIL cooler | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
550 | Electrical | PS5-60-BE- 0026A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0026A | CW Module - Junction Box | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
551 | Electrical | PS5-60-BE- 0026A-CL02 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0026A | CW Module - Junction Box | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
552 | Electrical | PS5-60-BE- 0026B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0026B | CW Module - Junction Box | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
553 | Electrical | PS5-60-BE- 0026B-CL02 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0026B | CW Module - Junction Box | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
554 | Electrical | PS5-60-BE- 0026C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0026C | CW Module - Junction Box | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
555 | Electrical | PS5-60-BE- 0026C-CL02 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0026C | CW Module - Junction Box | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
556 | Electrical | PS5-60-BE- 0026D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0026D | CW Module - Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
557 | Electrical | PS5-60-BE- 0026D-CL02 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0026D | CW Module - Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
558 | Electrical | PS5-60-BE- 0026E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0026E | CW Module - Junction Box | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
559 | Electrical | PS5-60-BE- 0026E-CL02 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BE- 0026E | CW Module - Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
560 | Electrical | PS5-60-BE- 0026F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0026F | CW Module - Junction Box | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
561 | Electrical | PS5-60-BE- 0026F-CL02 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BE- 0026F | CW Module - Junction Box | Generator Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
562 | Electrical | PS5-60-BE- 0026G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0026G | CW Module - Junction Box | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
563 | Electrical | PS5-60-BE- 0026G-CL02 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BE- 0026G | CW Module - Junction Box | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
564 | Electrical | PS5-60-BE- 0027A-CL01 | PS5-60-BE- 0007A | FCU- fuel conditioning module Generator set-1 (A) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0027A | Duplex fuel filter Element -1 trace heating Generator Set-1 (A) | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
565 | Electrical | PS5-60-BE- 0027B-CL01 | PS5-60-BE- 0007B | FCU- fuel conditioning module Generator set-2 (B) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0027B | Duplex fuel filter Element -1 trace heating Generator Set-1 (B) | Generator Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
566 | Electrical | PS5-60-BE- 0027C-CL01 | PS5-60-BE- 0007C | FCU- fuel conditioning module Generator set-3 (C) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0027C | Duplex fuel filter Element -1 trace heating Generator Set-1 (C) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
567 | Electrical | PS5-60-BE- 0027D-CL01 | PS5-60-BE- 0007D | FCU- fuel conditioning module Generator set-4 (D) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0027D | Duplex fuel filter Element -1 trace heating Generator Set-1 (D) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
568 | Electrical | PS5-60-BE- 0027E-CL01 | PS5-60-BE- 0007E | FCU- fuel conditioning module Generator set-5 (E) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0027E | Duplex fuel filter Element -1 trace heating Generator Set-1 (E) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
569 | Electrical | PS5-60-BE- 0027F-CL01 | PS5-60-BE- 0007F | FCU- fuel conditioning module Generator set-6 (6) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0027F | Duplex fuel filter Element -1 trace heating Generator Set-6 (F) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
570 | Electrical | PS5-60-BE- 0027G-CL01 | PS5-60-BE- 0007G | FCU- fuel conditioning module Generator set-7 (G) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0027G | Duplex fuel filter Element -1 trace heating Generator Set-7 (G) | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
571 | Electrical | PS5-60-BE- 0028A-CL01 | PS5-60-BE- 0007A | FCU- fuel conditioning module Generator set-1 (A) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0028A | Duplex fuel filter Element -2 trace heating Generator Set-1 (A) | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
572 | Electrical | PS5-60-BE- 0028B-CL01 | PS5-60-BE- 0007B | FCU- fuel conditioning module Generator set-2 (B) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0028B | Duplex fuel filter Element -2 trace heating Generator Set-2 (B) | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
573 | Electrical | PS5-60-BE- 0028C-CL01 | PS5-60-BE- 0007C | FCU- fuel conditioning module Generator set-3 (C) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0028C | Duplex fuel filter Element -2 trace heating Generator Set-3 (C) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
574 | Electrical | PS5-60-BE- 0028D-CL01 | PS5-60-BE- 0007D | FCU- fuel conditioning module Generator set-4 (D) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0028D | Duplex fuel filter Element -2 trace heating Generator Set-4 (D) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
575 | Electrical | PS5-60-BE- 0028E-CL01 | PS5-60-BE- 0007E | FCU- fuel conditioning module Generator set-5 (E) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0028E | Duplex fuel filter Element -2 trace heating Generator Set-5 (E) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
576 | Electrical | PS5-60-BE- 0028F-CL01 | PS5-60-BE- 0007F | FCU- fuel conditioning module Generator set-6 (6) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0028F | Duplex fuel filter Element -2 trace heating Generator Set-6 (F) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
577 | Electrical | PS5-60-BE- 0028G-CL01 | PS5-60-BE- 0007G | FCU- fuel conditioning module Generator set-7 (G) Trace heater Power JB-3 | Generator Building | PS5-60-BE- 0028G | Duplex fuel filter Element -2 trace heating Generator Set-7 (G) | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
578 | Electrical | PS5-60-BI- 0005A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI- 0005A | NER (A) Space Heater - Control Junction Box | Generator Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
579 | Electrical | PS5-60-BI- 0005B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BI- 0005B | NER (B) Space Heater - Control Junction Box | Generator Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
580 | Electrical | PS5-60-BI- 0005C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI-0005C | NER (C) Space Heater - Control Junction Box | Generator Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
581 | Electrical | PS5-60-BI- 0005D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI- 0005D | NER (D) Space Heater - Control Junction Box | Generator Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
582 | Electrical | PS5-60-BI- 0005E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BI-0005E | NER (E) Space Heater - Control Junction Box | Generator Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
583 | Electrical | PS5-60-BI- 0005F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI-0005F | NER (F) Space Heater - Control Junction Box | Generator Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
584 | Electrical | PS5-60-BI- 0005G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BI- 0005G | NER (G) Space Heater - Control Junction Box | Generator Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
585 | Electrical | PS5-60-BI- 0006A-CL01 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
586 | Electrical | PS5-60-BI- 0006A-CL02 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
587 | Electrical | PS5-60-BI- 0006A-CL03 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
588 | Electrical | PS5-60-BI- 0006A-CL04 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
589 | Electrical | PS5-60-BI- 0006A-CL05 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
590 | Electrical | PS5-60-BI- 0006A-CL06 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
591 | Electrical | PS5-60-BI- 0006A-CL07 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
592 | Electrical | PS5-60-BI- 0006A-CL08 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
593 | Electrical | PS5-60-BI- 0006A-CL09 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
594 | Electrical | PS5-60-BI- 0006A-CL10 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
595 | Electrical | PS5-60-BI- 0006A-CL11 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0006A | FCU- fuel conditioning module Generator set-1 (A) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
596 | Electrical | PS5-60-BI- 0006B-CL01 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
597 | Electrical | PS5-60-BI- 0006B-CL02 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
598 | Electrical | PS5-60-BI- 0006B-CL03 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
599 | Electrical | PS5-60-BI- 0006B-CL04 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
600 | Electrical | PS5-60-BI- 0006B-CL05 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
601 | Electrical | PS5-60-BI- 0006B-CL06 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
602 | Electrical | PS5-60-BI- 0006B-CL07 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
603 | Electrical | PS5-60-BI- 0006B-CL08 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
604 | Electrical | PS5-60-BI- 0006B-CL09 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
605 | Electrical | PS5-60-BI- 0006B-CL10 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
606 | Electrical | PS5-60-BI- 0006B-CL11 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0006B | FCU- fuel conditioning module Generator set-2 (B) control junction box- Exe | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
607 | Electrical | PS5-60-BI- 0006C-CL01 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
608 | Electrical | PS5-60-BI- 0006C-CL02 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
609 | Electrical | PS5-60-BI- 0006C-CL03 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
610 | Electrical | PS5-60-BI- 0006C-CL04 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
611 | Electrical | PS5-60-BI- 0006C-CL05 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
612 | Electrical | PS5-60-BI- 0006C-CL06 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
613 | Electrical | PS5-60-BI- 0006C-CL07 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
614 | Electrical | PS5-60-BI- 0006C-CL08 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
615 | Electrical | PS5-60-BI- 0006C-CL09 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
616 | Electrical | PS5-60-BI- 0006C-CL10 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
617 | Electrical | PS5-60-BI- 0006C-CL11 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0006C | FCU- fuel conditioning module Generator set-3 (C) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
618 | Electrical | PS5-60-BI- 0006D-CL01 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
619 | Electrical | PS5-60-BI- 0006D-CL02 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
620 | Electrical | PS5-60-BI- 0006D-CL03 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
621 | Electrical | PS5-60-BI- 0006D-CL04 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
622 | Electrical | PS5-60-BI- 0006D-CL05 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
623 | Electrical | PS5-60-BI- 0006D-CL06 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
624 | Electrical | PS5-60-BI- 0006D-CL07 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
625 | Electrical | PS5-60-BI- 0006D-CL08 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
626 | Electrical | PS5-60-BI- 0006D-CL09 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
627 | Electrical | PS5-60-BI- 0006D-CL10 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
628 | Electrical | PS5-60-BI- 0006D-CL11 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0006D | FCU- fuel conditioning module Generator set-4 (D) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
629 | Electrical | PS5-60-BI- 0006E-CL01 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
630 | Electrical | PS5-60-BI- 0006E-CL02 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
631 | Electrical | PS5-60-BI- 0006E-CL03 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
632 | Electrical | PS5-60-BI- 0006E-CL04 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
633 | Electrical | PS5-60-BI- 0006E-CL05 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
634 | Electrical | PS5-60-BI- 0006E-CL06 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
635 | Electrical | PS5-60-BI- 0006E-CL07 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
636 | Electrical | PS5-60-BI- 0006E-CL08 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
637 | Electrical | PS5-60-BI- 0006E-CL09 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
638 | Electrical | PS5-60-BI- 0006E-CL10 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
639 | Electrical | PS5-60-BI- 0006E-CL11 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0006E | FCU- fuel conditioning module Generator set-5 (E) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
640 | Electrical | PS5-60-BI- 0006F-CL01 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
641 | Electrical | PS5-60-BI- 0006F-CL02 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
642 | Electrical | PS5-60-BI- 0006F-CL03 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
643 | Electrical | PS5-60-BI- 0006F-CL04 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
644 | Electrical | PS5-60-BI- 0006F-CL05 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
645 | Electrical | PS5-60-BI- 0006F-CL06 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
646 | Electrical | PS5-60-BI- 0006F-CL07 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
647 | Electrical | PS5-60-BI- 0006F-CL08 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
648 | Electrical | PS5-60-BI- 0006F-CL09 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
649 | Electrical | PS5-60-BI- 0006F-CL10 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
650 | Electrical | PS5-60-BI- 0006F-CL11 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0006F | FCU- fuel conditioning module Generator set-6 (F) control junction box- Exe | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
651 | Electrical | PS5-60-BI- 0006G-CL01 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
652 | Electrical | PS5-60-BI- 0006G-CL02 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
653 | Electrical | PS5-60-BI- 0006G-CL03 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
654 | Electrical | PS5-60-BI- 0006G-CL04 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
655 | Electrical | PS5-60-BI- 0006G-CL05 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
656 | Electrical | PS5-60-BI- 0006G-CL06 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
657 | Electrical | PS5-60-BI- 0006G-CL07 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
658 | Electrical | PS5-60-BI- 0006G-CL08 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
659 | Electrical | PS5-60-BI- 0006G-CL09 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
660 | Electrical | PS5-60-BI- 0006G-CL10 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
661 | Electrical | PS5-60-BI- 0006G-CL11 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0006G | FCU- fuel conditioning module Generator set-7 (G) control junction box- Exe | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
662 | Electrical | PS5-60-BI- 0015A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
663 | Electrical | PS5-60-BI- 0015A-CL02 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
664 | Electrical | PS5-60-BI- 0015A-CL03 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
665 | Electrical | PS5-60-BI- 0015B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
666 | Electrical | PS5-60-BI- 0015B-CL02 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
667 | Electrical | PS5-60-BI- 0015B-CL03 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
668 | Electrical | PS5-60-BI- 0015C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
669 | Electrical | PS5-60-BI- 0015C-CL02 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
670 | Electrical | PS5-60-BI- 0015C-CL03 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
671 | Electrical | PS5-60-BI- 0015D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
672 | Electrical | PS5-60-BI- 0015D-CL02 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
673 | Electrical | PS5-60-BI- 0015D-CL03 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
674 | Electrical | PS5-60-BI- 0015E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
675 | Electrical | PS5-60-BI- 0015E-CL02 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
676 | Electrical | PS5-60-BI- 0015E-CL03 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
677 | Electrical | PS5-60-BI- 0015F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
678 | Electrical | PS5-60-BI- 0015F-CL02 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
679 | Electrical | PS5-60-BI- 0015F-CL03 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
680 | Electrical | PS5-60-BI- 0015G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
681 | Electrical | PS5-60-BI- 0015G-CL02 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
682 | Electrical | PS5-60-BI- 0015G-CL03 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
683 | Electrical | PS5-60-BI- 0017A-CL01 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-BI- 0017A | FCU- fuel conditioning module Generator set-1 (A) control junction box- EX-i | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
684 | Electrical | PS5-60-BI- 0017B-CL01 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-BI- 0017B | FCU- fuel conditioning module Generator set-2 (B) control junction box- EX-i | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
685 | Electrical | PS5-60-BI- 0017C-CL01 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-BI-0017C | FCU- fuel conditioning module Generator set-3 (C) control junction box- EX-i | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
686 | Electrical | PS5-60-BI- 0017D-CL01 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-BI- 0017D | FCU- fuel conditioning module Generator set-4 (D) control junction box- EX-i | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
687 | Electrical | PS5-60-BI- 0017E-CL01 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-BI-0017E | FCU- fuel conditioning module Generator set-5 (E) control junction box- EX-i | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
688 | Electrical | PS5-60-BI- 0017F-CL01 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-BI-0017F | FCU- fuel conditioning module Generator set-6 (F) control junction box- EX-i | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
689 | Electrical | PS5-60-BI- 0017G-CL01 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-BI- 0017G | FCU- fuel conditioning module Generator set-7 (G) control junction box- EX-i | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
690 | Electrical | PS5-60-DD- 62800B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY | Generator Electrical | PS5-60-DD- 62800B | Eletrical barring device | Generator Building
691 | Electrical | PS5-60-DD- 62800D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical | PS5-60-DD- 62800D | Eletrical barring device | Generator Building
692 | Electrical | PS5-60-DD- 62800F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY | Generator Electrical | PS5-60-DD- 62800F | Eletrical barring device | Generator Building
693 | Electrical | PS5-60-DM- 3300-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-60-DM- 3300 | Cooling Water Pump | Deluge skid Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
694 | Electrical | PS5-60-DM- 3400-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-60-DM- 3400 | Cooling Water Return Pump | Closed Drain Drum Power Gen | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
695 | Electrical | PS5-60-EA- 2900A-CL01 | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | PS5-60-EA- 2900A | DIESEL OIL COOLER A | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
696 | Electrical | PS5-60-EA- 2900B-CL01 | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | PS5-60-EA- 2900B | DIESEL OIL COOLER B | Generator Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
697 | Electrical | PS5-60-EA- 2900C-CL01 | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building | PS5-60-EA- 2900C | DIESEL OIL COOLER C | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
698 | Electrical | PS5-60-EA- 2900D-CL01 | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building | PS5-60-EA- 2900D | DIESEL OIL COOLER D | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
699 | Electrical | PS5-60-EA- 2900E-CL01 | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building | PS5-60-EA- 2900E | DIESEL OIL COOLER E | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
700 | Electrical | PS5-60-EA- 2900F-CL01 | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building | PS5-60-EA- 2900F | DIESEL OIL COOLER F | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
701 | Electrical | PS5-60-EA- 2900G-CL01 | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building | PS5-60-EA- 2900G | DIESEL OIL COOLER G | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
702 | Electrical | PS5-60-IE- 0002A-CD01 | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002A | Local Display Panel (LDP) for Generator Set A | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
703 | Electrical | PS5-60-IE- 0002A-CD02 | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002A | Local Display Panel (LDP) for Generator Set A | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
704 | Electrical | PS5-60-IE- 0002A-CD03 | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002A | Local Display Panel (LDP) for Generator Set A | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
705 | Electrical | PS5-60-IE- 0002A-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0002A | Local Display Panel (LDP) for Generator Set A | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
706 | Electrical | PS5-60-IE- 0002A-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0002A | Local Display Panel (LDP) for Generator Set A | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
707 | Electrical | PS5-60-IE- 0002A-CL03 | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002A | Local Display Panel (LDP) for Generator Set A | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
708 | Electrical | PS5-60-IE- 0002B-CD01 | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002B | Local Display Panel (LDP) for Generator Set B | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
709 | Electrical | PS5-60-IE- 0002B-CD02 | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002B | Local Display Panel (LDP) for Generator Set B | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
710 | Electrical | PS5-60-IE- 0002B-CD03 | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002B | Local Display Panel (LDP) for Generator Set B | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
711 | Electrical | PS5-60-IE- 0002B-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0002B | Local Display Panel (LDP) for Generator Set B | Generator Building | 2026-06-04 00:00:00 | CPP-RFI-68-33/1-05-0309 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
712 | Electrical | PS5-60-IE- 0002B-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0002B | Local Display Panel (LDP) for Generator Set B | Generator Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
713 | Electrical | PS5-60-IE- 0002B-CL03 | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002B | Local Display Panel (LDP) for Generator Set B | Generator Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
714 | Electrical | PS5-60-IE- 0002C-CD01 | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002C | Local Display Panel (LDP) for Generator Set C | Generator Building | 2026-07-02 00:00:00 | CPP-RFI-68-331-05-0399 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
715 | Electrical | PS5-60-IE- 0002C-CD02 | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002C | Local Display Panel (LDP) for Generator Set C | Generator Building | 2026-07-02 00:00:00 | CPP-RFI-68-331-05-0399 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
716 | Electrical | PS5-60-IE- 0002C-CD03 | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002C | Local Display Panel (LDP) for Generator Set C | Generator Building | 2026-07-02 00:00:00 | CPP-RFI-68-331-05-0399 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
717 | Electrical | PS5-60-IE- 0002C-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0002C | Local Display Panel (LDP) for Generator Set C | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
718 | Electrical | PS5-60-IE- 0002C-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0002C | Local Display Panel (LDP) for Generator Set C | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
719 | Electrical | PS5-60-IE- 0002C-CL03 | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002C | Local Display Panel (LDP) for Generator Set C | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
720 | Electrical | PS5-60-IE- 0002D-CD01 | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0002D | Local Display Panel (LDP) for Generator Set D | Generator Building | 2026-07-02 00:00:00 | CPP-RFI-68-331-05-0399 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
721 | Electrical | PS5-60-IE- 0002D-CD02 | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0002D | Local Display Panel (LDP) for Generator Set D | Generator Building | 2026-07-02 00:00:00 | CPP-RFI-68-331-05-0399 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
722 | Electrical | PS5-60-IE- 0002D-CD03 | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0002D | Local Display Panel (LDP) for Generator Set D | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
723 | Electrical | PS5-60-IE- 0002D-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE- 0002D | Local Display Panel (LDP) for Generator Set D | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
724 | Electrical | PS5-60-IE- 0002D-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE- 0002D | Local Display Panel (LDP) for Generator Set D | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
725 | Electrical | PS5-60-IE- 0002D-CL03 | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0002D | Local Display Panel (LDP) for Generator Set D | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
726 | Electrical | PS5-60-IE- 0002E-CD01 | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002E | Local Display Panel (LDP) for Generator Set E | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
727 | Electrical | PS5-60-IE- 0002E-CD02 | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002E | Local Display Panel (LDP) for Generator Set E | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
728 | Electrical | PS5-60-IE- 0002E-CD03 | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002E | Local Display Panel (LDP) for Generator Set E | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
729 | Electrical | PS5-60-IE- 0002E-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0002E | Local Display Panel (LDP) for Generator Set E | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
730 | Electrical | PS5-60-IE- 0002E-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0002E | Local Display Panel (LDP) for Generator Set E | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
731 | Electrical | PS5-60-IE- 0002E-CL03 | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002E | Local Display Panel (LDP) for Generator Set E | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
732 | Electrical | PS5-60-IE- 0002F-CD01 | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002F | Local Display Panel (LDP) for Generator Set F | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
733 | Electrical | PS5-60-IE- 0002F-CD02 | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002F | Local Display Panel (LDP) for Generator Set F | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
734 | Electrical | PS5-60-IE- 0002F-CD03 | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002F | Local Display Panel (LDP) for Generator Set F | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
735 | Electrical | PS5-60-IE- 0002F-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0002F | Local Display Panel (LDP) for Generator Set F | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
736 | Electrical | PS5-60-IE- 0002F-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0002F | Local Display Panel (LDP) for Generator Set F | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
737 | Electrical | PS5-60-IE- 0002F-CL03 | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0002F | Local Display Panel (LDP) for Generator Set F | Generator Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
738 | Electrical | PS5-60-IE- 0002G-CD01 | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0002G | Local Display Panel (LDP) for Generator Set G | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
739 | Electrical | PS5-60-IE- 0002G-CD02 | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0002G | Local Display Panel (LDP) for Generator Set G | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
740 | Electrical | PS5-60-IE- 0002G-CD03 | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0002G | Local Display Panel (LDP) for Generator Set G | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
741 | Electrical | PS5-60-IE- 0002G-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE- 0002G | Local Display Panel (LDP) for Generator Set G | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
742 | Electrical | PS5-60-IE- 0002G-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE- 0002G | Local Display Panel (LDP) for Generator Set G | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
743 | Electrical | PS5-60-IE- 0002G-CL03 | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0002G | Local Display Panel (LDP) for Generator Set G | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
744 | Electrical | PS5-60-IE- 0003A-CD01 | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003A | Generator control panel | Generator Electrical
745 | Electrical | PS5-60-IE- 0003A-CD02 | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
746 | Electrical | PS5-60-IE- 0003A-CD03 | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
747 | Electrical | PS5-60-IE- 0003A-CD04 | PS5-60-BI- 0005A | NER (A) Space Heater - Control Junction Box | Generator Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
748 | Electrical | PS5-60-IE- 0003A-CD05 | PS5-60-BI- 0015A | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
749 | Electrical | PS5-60-IE- 0003A-CD06 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
750 | Electrical | PS5-60-IE- 0003A-CD07 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003A | Generator control panel | Generator Electrical
751 | Electrical | PS5-60-IE- 0003A-CD08 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
752 | Electrical | PS5-60-IE- 0003A-CD09 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003A | Generator control panel | Generator Electrical
753 | Electrical | PS5-60-IE- 0003A-CD10 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003A | Generator control panel | Generator Electrical
754 | Electrical | PS5-60-IE- 0003A-CD11 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003A | Generator control panel | Generator Electrical
755 | Electrical | PS5-60-IE- 0003A-CD12 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
756 | Electrical | PS5-60-IE- 0003A-CD13 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003A | Generator control panel | Generator Electrical
757 | Electrical | PS5-60-IE- 0003A-CD14 | PS5-60-IE-0002A | Local Display Panel (LDP) for Generator Set A | Generator Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
758 | Electrical | PS5-60-IE- 0003A-CD15 | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
759 | Electrical | PS5-60-IE- 0003A-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
760 | Electrical | PS5-60-IE- 0003A-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
761 | Electrical | PS5-60-IE- 0003B-CD01 | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003B | Generator control panel | Generator Electrical
762 | Electrical | PS5-60-IE- 0003B-CD02 | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
763 | Electrical | PS5-60-IE- 0003B-CD03 | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
764 | Electrical | PS5-60-IE- 0003B-CD04 | PS5-60-BI- 0005B | NER (B) Space Heater - Control Junction Box | Generator Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
765 | Electrical | PS5-60-IE- 0003B-CD05 | PS5-60-BI- 0015B | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
766 | Electrical | PS5-60-IE- 0003B-CD06 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
767 | Electrical | PS5-60-IE- 0003B-CD07 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003B | Generator control panel | Generator Electrical
768 | Electrical | PS5-60-IE- 0003B-CD08 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
769 | Electrical | PS5-60-IE- 0003B-CD09 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003B | Generator control panel | Generator Electrical
770 | Electrical | PS5-60-IE- 0003B-CD10 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003B | Generator control panel | Generator Electrical
771 | Electrical | PS5-60-IE- 0003B-CD11 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003B | Generator control panel | Generator Electrical
772 | Electrical | PS5-60-IE- 0003B-CD12 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
773 | Electrical | PS5-60-IE- 0003B-CD13 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003B | Generator control panel | Generator Electrical
774 | Electrical | PS5-60-IE- 0003B-CD14 | PS5-60-IE-0002B | Local Display Panel (LDP) for Generator Set B | Generator Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
775 | Electrical | PS5-60-IE- 0003B-CD15 | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
776 | Electrical | PS5-60-IE- 0003B-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
777 | Electrical | PS5-60-IE- 0003B-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
778 | Electrical | PS5-60-IE- 0003C-CD01 | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003C | Generator control panel | Generator Electrical
779 | Electrical | PS5-60-IE- 0003C-CD02 | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
780 | Electrical | PS5-60-IE- 0003C-CD03 | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
781 | Electrical | PS5-60-IE- 0003C-CD04 | PS5-60-BI-0005C | NER (C) Space Heater - Control Junction Box | Generator Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
782 | Electrical | PS5-60-IE- 0003C-CD05 | PS5-60-BI-0015C | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
783 | Electrical | PS5-60-IE- 0003C-CD06 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
784 | Electrical | PS5-60-IE- 0003C-CD07 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003C | Generator control panel | Generator Electrical
785 | Electrical | PS5-60-IE- 0003C-CD08 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
786 | Electrical | PS5-60-IE- 0003C-CD09 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003C | Generator control panel | Generator Electrical
787 | Electrical | PS5-60-IE- 0003C-CD10 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003C | Generator control panel | Generator Electrical
788 | Electrical | PS5-60-IE- 0003C-CD11 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003C | Generator control panel | Generator Electrical
789 | Electrical | PS5-60-IE- 0003C-CD12 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
790 | Electrical | PS5-60-IE- 0003C-CD13 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003C | Generator control panel | Generator Electrical
791 | Electrical | PS5-60-IE- 0003C-CD14 | PS5-60-IE-0002C | Local Display Panel (LDP) for Generator Set C | Generator Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
792 | Electrical | PS5-60-IE- 0003C-CD15 | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
793 | Electrical | PS5-60-IE- 0003C-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
794 | Electrical | PS5-60-IE- 0003C-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
795 | Electrical | PS5-60-IE- 0003D-CD01 | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0003D | Generator control panel | Generator Electrical
796 | Electrical | PS5-60-IE- 0003D-CD02 | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
797 | Electrical | PS5-60-IE- 0003D-CD03 | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
798 | Electrical | PS5-60-IE- 0003D-CD04 | PS5-60-BI- 0005D | NER (D) Space Heater - Control Junction Box | Generator Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
799 | Electrical | PS5-60-IE- 0003D-CD05 | PS5-60-BI- 0015D | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
800 | Electrical | PS5-60-IE- 0003D-CD06 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
801 | Electrical | PS5-60-IE- 0003D-CD07 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003D | Generator control panel | Generator Electrical
802 | Electrical | PS5-60-IE- 0003D-CD08 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
803 | Electrical | PS5-60-IE- 0003D-CD09 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003D | Generator control panel | Generator Electrical
804 | Electrical | PS5-60-IE- 0003D-CD10 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003D | Generator control panel | Generator Electrical
805 | Electrical | PS5-60-IE- 0003D-CD11 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003D | Generator control panel | Generator Electrical
806 | Electrical | PS5-60-IE- 0003D-CD12 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
807 | Electrical | PS5-60-IE- 0003D-CD13 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003D | Generator control panel | Generator Electrical
808 | Electrical | PS5-60-IE- 0003D-CD14 | PS5-60-IE- 0002D | Local Display Panel (LDP) for Generator Set D | Generator Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
809 | Electrical | PS5-60-IE- 0003D-CD15 | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
810 | Electrical | PS5-60-IE- 0003D-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
811 | Electrical | PS5-60-IE- 0003D-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
812 | Electrical | PS5-60-IE- 0003E-CD01 | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003E | Generator control panel | Generator Electrical
813 | Electrical | PS5-60-IE- 0003E-CD02 | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
814 | Electrical | PS5-60-IE- 0003E-CD03 | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
815 | Electrical | PS5-60-IE- 0003E-CD04 | PS5-60-BI-0005E | NER (E) Space Heater - Control Junction Box | Generator Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
816 | Electrical | PS5-60-IE- 0003E-CD05 | PS5-60-BI-0015E | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
817 | Electrical | PS5-60-IE- 0003E-CD06 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
818 | Electrical | PS5-60-IE- 0003E-CD07 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003E | Generator control panel | Generator Electrical
819 | Electrical | PS5-60-IE- 0003E-CD08 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
820 | Electrical | PS5-60-IE- 0003E-CD09 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003E | Generator control panel | Generator Electrical
821 | Electrical | PS5-60-IE- 0003E-CD10 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003E | Generator control panel | Generator Electrical
822 | Electrical | PS5-60-IE- 0003E-CD11 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003E | Generator control panel | Generator Electrical
823 | Electrical | PS5-60-IE- 0003E-CD12 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
824 | Electrical | PS5-60-IE- 0003E-CD13 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003E | Generator control panel | Generator Electrical
825 | Electrical | PS5-60-IE- 0003E-CD14 | PS5-60-IE-0002E | Local Display Panel (LDP) for Generator Set E | Generator Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
826 | Electrical | PS5-60-IE- 0003E-CD15 | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
827 | Electrical | PS5-60-IE- 0003E-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
828 | Electrical | PS5-60-IE- 0003E-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
829 | Electrical | PS5-60-IE- 0003F-CD01 | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003F | Generator control panel | Generator Electrical
830 | Electrical | PS5-60-IE- 0003F-CD02 | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
831 | Electrical | PS5-60-IE- 0003F-CD03 | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
832 | Electrical | PS5-60-IE- 0003F-CD04 | PS5-60-BI-0005F | NER (F) Space Heater - Control Junction Box | Generator Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
833 | Electrical | PS5-60-IE- 0003F-CD05 | PS5-60-BI-0015F | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
834 | Electrical | PS5-60-IE- 0003F-CD06 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
835 | Electrical | PS5-60-IE- 0003F-CD07 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003F | Generator control panel | Generator Electrical
836 | Electrical | PS5-60-IE- 0003F-CD08 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
837 | Electrical | PS5-60-IE- 0003F-CD09 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003F | Generator control panel | Generator Electrical
838 | Electrical | PS5-60-IE- 0003F-CD10 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003F | Generator control panel | Generator Electrical
839 | Electrical | PS5-60-IE- 0003F-CD11 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003F | Generator control panel | Generator Electrical
840 | Electrical | PS5-60-IE- 0003F-CD12 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
841 | Electrical | PS5-60-IE- 0003F-CD13 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0003F | Generator control panel | Generator Electrical
842 | Electrical | PS5-60-IE- 0003F-CD14 | PS5-60-IE-0002F | Local Display Panel (LDP) for Generator Set F | Generator Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
843 | Electrical | PS5-60-IE- 0003F-CD15 | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
844 | Electrical | PS5-60-IE- 0003F-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
845 | Electrical | PS5-60-IE- 0003F-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
846 | Electrical | PS5-60-IE- 0003G-CD01 | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0003G | Generator control panel | Generator Electrical
847 | Electrical | PS5-60-IE- 0003G-CD02 | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
848 | Electrical | PS5-60-IE- 0003G-CD03 | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
849 | Electrical | PS5-60-IE- 0003G-CD04 | PS5-60-BI- 0005G | NER (G) Space Heater - Control Junction Box | Generator Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
850 | Electrical | PS5-60-IE- 0003G-CD05 | PS5-60-BI- 0015G | CRO Generator Space Heater - Control Terminal Box | Generator Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
851 | Electrical | PS5-60-IE- 0003G-CD06 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
852 | Electrical | PS5-60-IE- 0003G-CD07 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003G | Generator control panel | Generator Electrical
853 | Electrical | PS5-60-IE- 0003G-CD08 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
854 | Electrical | PS5-60-IE- 0003G-CD09 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003G | Generator control panel | Generator Electrical
855 | Electrical | PS5-60-IE- 0003G-CD10 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003G | Generator control panel | Generator Electrical
856 | Electrical | PS5-60-IE- 0003G-CD11 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003G | Generator control panel | Generator Electrical
857 | Electrical | PS5-60-IE- 0003G-CD12 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
858 | Electrical | PS5-60-IE- 0003G-CD13 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE- 0003G | Generator control panel | Generator Electrical
859 | Electrical | PS5-60-IE- 0003G-CD14 | PS5-60-IE- 0002G | Local Display Panel (LDP) for Generator Set G | Generator Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
860 | Electrical | PS5-60-IE- 0003G-CD15 | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
861 | Electrical | PS5-60-IE- 0003G-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
862 | Electrical | PS5-60-IE- 0003G-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
863 | Electrical | PS5-60-IE-0004- CD01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
864 | Electrical | PS5-60-IE-0004- CD02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
865 | Electrical | PS5-60-IE-0004- CD14 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
866 | Electrical | PS5-60-IE-0004- CD15 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
867 | Electrical | PS5-60-IE-0004- CD16 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
868 | Electrical | PS5-60-IE-0004- CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
869 | Electrical | PS5-60-IE-0004- CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IE-0004 | Master Control Panel | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
870 | Electrical | PS5-60-IES- 3300-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-60-IES-3300 | Cooling Water Pump-LCS | Deluge skid Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
871 | Electrical | PS5-60-IES- 3400-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-60-IES-3400 | Cooling Water Return Pump-LCS | Closed Drain Drum Power Gen | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
872 | Electrical | PS5-60-IH- 0001A-CG01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
873 | Electrical | PS5-60-IH- 0001A-CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
874 | Electrical | PS5-60-IH- 0001A-CL02 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
875 | Electrical | PS5-60-IH- 0001A-CL03 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
876 | Electrical | PS5-60-IH- 0001A-CL04 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
877 | Electrical | PS5-60-IH- 0001A-CL05 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
878 | Electrical | PS5-60-IH- 0001A-CL06 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
879 | Electrical | PS5-60-IH- 0001B-CG01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
880 | Electrical | PS5-60-IH- 0001B-CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
881 | Electrical | PS5-60-IH- 0001B-CL02 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
882 | Electrical | PS5-60-IH- 0001B-CL03 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
883 | Electrical | PS5-60-IH- 0001B-CL04 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
884 | Electrical | PS5-60-IH- 0001B-CL05 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
885 | Electrical | PS5-60-IH- 0001B-CL06 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
886 | Electrical | PS5-60-IH- 0001C-CG01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
887 | Electrical | PS5-60-IH- 0001C-CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
888 | Electrical | PS5-60-IH- 0001C-CL02 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
889 | Electrical | PS5-60-IH- 0001C-CL03 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
890 | Electrical | PS5-60-IH- 0001C-CL04 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
891 | Electrical | PS5-60-IH- 0001C-CL05 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
892 | Electrical | PS5-60-IH- 0001C-CL06 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
893 | Electrical | PS5-60-IH- 0001D-CG01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
894 | Electrical | PS5-60-IH- 0001D-CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
895 | Electrical | PS5-60-IH- 0001D-CL02 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
896 | Electrical | PS5-60-IH- 0001D-CL03 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
897 | Electrical | PS5-60-IH- 0001D-CL04 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
898 | Electrical | PS5-60-IH- 0001D-CL05 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
899 | Electrical | PS5-60-IH- 0001D-CL06 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
900 | Electrical | PS5-60-IH- 0001E-CG01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
901 | Electrical | PS5-60-IH- 0001E-CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
902 | Electrical | PS5-60-IH- 0001E-CL02 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
903 | Electrical | PS5-60-IH- 0001E-CL03 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
904 | Electrical | PS5-60-IH- 0001E-CL04 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
905 | Electrical | PS5-60-IH- 0001E-CL05 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
906 | Electrical | PS5-60-IH- 0001E-CL06 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
907 | Electrical | PS5-60-IH- 0001F-CG01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
908 | Electrical | PS5-60-IH- 0001F-CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
909 | Electrical | PS5-60-IH- 0001F-CL02 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
910 | Electrical | PS5-60-IH- 0001F-CL03 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
911 | Electrical | PS5-60-IH- 0001F-CL04 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
912 | Electrical | PS5-60-IH- 0001F-CL05 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
913 | Electrical | PS5-60-IH- 0001F-CL06 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
914 | Electrical | PS5-60-IH- 0001G-CG01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
915 | Electrical | PS5-60-IH- 0001G-CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
916 | Electrical | PS5-60-IH- 0001G-CL02 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
917 | Electrical | PS5-60-IH- 0001G-CL03 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
918 | Electrical | PS5-60-IH- 0001G-CL04 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
919 | Electrical | PS5-60-IH- 0001G-CL05 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
920 | Electrical | PS5-60-IH- 0001G-CL06 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
921 | Electrical | PS5-60-IH-0002 -CG01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
922 | Electrical | PS5-60-IH-0002 -CG02 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
923 | Electrical | PS5-60-IH-0002 -CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
924 | Electrical | PS5-60-IH-0002 -CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
925 | Electrical | PS5-60-IH-0002 -CL03 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
926 | Electrical | PS5-60-IH-0002 -CL04 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
927 | Electrical | PS5-60-IH-0002 -CL05 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
928 | Electrical | PS5-60-IH-0002 -CL06 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
929 | Electrical | PS5-60-IH-0002 -CL07 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
930 | Electrical | PS5-60-IH-0002 -CL08 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
931 | Electrical | PS5-60-IH-0002 -CL09 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
932 | Electrical | PS5-60-IH-0002 -CL10 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
933 | Electrical | PS5-60-IJ- 0001A-CH04 | PS5-60-GE- 8100A | Power Generator | Power generator building area | PS5-60-IJ-0001A | Neutral Grounding resistor for Generator set 1 (A) | CRO Generator Area | 2026-03-06 00:00:00 | CPP-RFI-68-33/1-05-168 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
934 | Electrical | PS5-60-IJ- 0001B-CH04 | PS5-60-GE- 8100B | Power Generator | Power generator building area | PS5-60-IJ-0001B | Neutral Grounding resistor for Generator set 2 (B) | CRO Generator Area | 2026-03-06 00:00:00 | CPP-RFI-68-33/1-05-168 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
935 | Electrical | PS5-60-IJ- 0001C-CH04 | PS5-60-GE- 8100C | Power Generator | Power generator building area | PS5-60-IJ-0001C | Neutral Grounding resistor for Generator set 3 (C) | CRO Generator Area | 2026-03-06 00:00:00 | CPP-RFI-68-33/1-05-168 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
936 | Electrical | PS5-60-IJ- 0001D-CH04 | PS5-60-GE- 8100D | Power Generator | Power generator building area | PS5-60-IJ-0001D | Neutral Grounding resistor for Generator set 4 (D) | CRO Generator Area | 2026-03-06 00:00:00 | CPP-RFI-68-33/1-05-168 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
937 | Electrical | PS5-60-IJ-0001E -CH04 | PS5-60-GE- 8100E | Power Generator | Power generator building area | PS5-60-IJ-0001E | Neutral Grounding resistor for Generator set 5 (E) | CRO Generator Area | 2026-03-06 00:00:00 | CPP-RFI-68-33/1-05-168 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
938 | Electrical | PS5-60-IJ-0001F -CH04 | PS5-60-GE- 8100F | Power Generator | Power generator building area | PS5-60-IJ-0001F | Neutral Grounding resistor for Generator set 6 (F) | CRO Generator Area | 2026-03-06 00:00:00 | CPP-RFI-68-33/1-05-168 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
939 | Electrical | PS5-60-IJ- 0001G-CH04 | PS5-60-GE- 8100G | Power Generator | Power generator building area | PS5-60-IJ-0001G | Neutral Grounding resistor for Generator set 7 (G) | CRO Generator Area | 2026-03-06 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
940 | Electrical | PS5-60-IN- 0001A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0001A | Lube oil separator genarator set-1 (A) | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
941 | Electrical | PS5-60-IN- 0001B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-IN- 0001B | Lube oil separator genarator set-2 (B) | Generator Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
942 | Electrical | PS5-60-IN- 0001C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0001C | Lube oil separator genarator set-3 (C) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
943 | Electrical | PS5-60-IN- 0001D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0001D | Lube oil separator genarator set-4 (D) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
944 | Electrical | PS5-60-IN- 0001E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-IN- 0001E | Lube oil separator genarator set-5 (E) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
945 | Electrical | PS5-60-IN- 0001F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0001F | Lube oil separator genarator set-6 (F) | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
946 | Electrical | PS5-60-IN- 0001G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-IN- 0001G | Lube oil separator genarator set-7 (G) | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
947 | Electrical | PS5-60-IN- 0002A-CG01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
948 | Electrical | PS5-60-IN- 0002A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
949 | Electrical | PS5-60-IN- 0002A-CL02 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
950 | Electrical | PS5-60-IN- 0002A-CL03 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002A | Fuel Conditioning Unit Control Panel - Generator Set-1 (A) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
951 | Electrical | PS5-60-IN- 0002B-CG01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
952 | Electrical | PS5-60-IN- 0002B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
953 | Electrical | PS5-60-IN- 0002B-CL02 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
954 | Electrical | PS5-60-IN- 0002B-CL03 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002B | Fuel Conditioning Unit Control Panel - Generator Set-2 (B) | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
955 | Electrical | PS5-60-IN- 0002C-CG01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
956 | Electrical | PS5-60-IN- 0002C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
957 | Electrical | PS5-60-IN- 0002C-CL02 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
958 | Electrical | PS5-60-IN- 0002C-CL03 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002C | Fuel Conditioning Unit Control Panel - Generator Set-3 (C) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
959 | Electrical | PS5-60-IN- 0002D-CG01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
960 | Electrical | PS5-60-IN- 0002D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
961 | Electrical | PS5-60-IN- 0002D-CL02 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
962 | Electrical | PS5-60-IN- 0002D-CL03 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002D | Fuel Conditioning Unit Control Panel - Generator Set-4 (D) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
963 | Electrical | PS5-60-IN- 0002E-CG01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
964 | Electrical | PS5-60-IN- 0002E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
965 | Electrical | PS5-60-IN- 0002E-CL02 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
966 | Electrical | PS5-60-IN- 0002E-CL03 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002E | Fuel Conditioning Unit Control Panel - Generator Set-5 (E) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
967 | Electrical | PS5-60-IN- 0002F-CG01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
968 | Electrical | PS5-60-IN- 0002F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
969 | Electrical | PS5-60-IN- 0002F-CL02 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
970 | Electrical | PS5-60-IN- 0002F-CL03 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002F | Fuel Conditioning Unit Control Panel - Generator Set-6 (F) | Generator Electrical Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
971 | Electrical | PS5-60-IN- 0002G-CG01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
972 | Electrical | PS5-60-IN- 0002G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
973 | Electrical | PS5-60-IN- 0002G-CL02 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
974 | Electrical | PS5-60-IN- 0002G-CL03 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IN- 0002G | Fuel Conditioning Unit Control Panel - Generator Set-7 (G) | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
975 | Electrical | PS5-60-ISO- 62800A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-ISO- 62800A | Socket For Barring Device (Gen. A & Gen. B) | Inside Power Gen. Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
976 | Electrical | PS5-60-ISO- 62800C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-ISO- 62800C | Socket For Barring Device (Gen. C & Gen. D) | Inside Power Gen. Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
977 | Electrical | PS5-60-ISO- 62800E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-ISO- 62800E | Socket For Barring Device (Gen. E & Gen. F) | Inside Power Gen. Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
978 | Electrical | PS5-60-ISO- 62800G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-ISO- 62800G | Socket For Barring Device (Gen. G) | Inside Power Gen. Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
979 | Electrical | PS5-60-IWK- 0001A-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IWK- 0001A | OWS | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
980 | Electrical | PS5-60-IWK- 0001A-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IWK- 0001A | OWS | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
981 | Electrical | PS5-60-IWK- 0001B-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IWK- 0001B | OWS | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
982 | Electrical | PS5-60-IWK- 0001B-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IWK- 0001B | OWS | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
983 | Electrical | PS5-60-IWK- 0001C-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IWK- 0001C | EWS | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
984 | Electrical | PS5-60-IWK- 0001C-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-IWK- 0001C | EWS | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
985 | Electrical | PS5-60-LA- 0002A-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-LA- 0002A | VTMS 1 | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
986 | Electrical | PS5-60-LA- 0002A-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-LA- 0002A | VTMS 1 | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
987 | Electrical | PS5-60-LA- 0002B-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-LA- 0002B | VTMS 2 | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
988 | Electrical | PS5-60-LA- 0002B-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-LA- 0002B | VTMS 2 | Generator Electrical Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
989 | Electrical | PS5-60-LA- 0002C-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-LA- 0002C | VTMS 3 | Generator Electrical Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
990 | Electrical | PS5-60-LA- 0002C-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-LA- 0002C | VTMS 3 | Generator Electrical Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
991 | Electrical | PS5-60-LA-0003 -CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-LA-0003 | RAP | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
992 | Electrical | PS5-60-LA-0003 -CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-LA-0003 | RAP | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
993 | Electrical | PS5-60-MOV- 0005-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-60-MOV- 0005 | Motor Operated Valve | Power generator building area | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
994 | Electrical | PS5-60-MOV- 0006-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-60-MOV- 0006 | Motor Operated Valve | Power generator building area | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
995 | Electrical | PS5-60-MOV- 0011-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-60-MOV- 0011 | Motor Operated Valve | Power generator building area | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
996 | Electrical | PS5-60-MOV- 0012-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-60-MOV- 0012 | Motor Operated Valve | Power generator building area | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
997 | Electrical | PS5-60-SEA- 0001-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-SEA- 0001 | FGS Panel | Generator Electrical Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
998 | Electrical | PS5-60-SEA- 0001-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-60-SEA- 0001 | FGS Panel | Generator Electrical Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
999 | Electrical | PS5-60-VS- 9100A-CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-VS- 9100A | Oil Mist Eliminator- CCV | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1000 | Electrical | PS5-60-VS- 9100B-CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-60-VS- 9100B | Oil Mist Eliminator- CCV | Generator Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1001 | Electrical | PS5-60-VS- 9100C-CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-VS- 9100C | Oil Mist Eliminator- CCV | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1002 | Electrical | PS5-60-VS- 9100D-CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-VS- 9100D | Oil Mist Eliminator- CCV | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1003 | Electrical | PS5-60-VS- 9100E-CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-60-VS- 9100E | Oil Mist Eliminator- CCV | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1004 | Electrical | PS5-60-VS- 9100F-CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-60-VS- 9100F | Oil Mist Eliminator- CCV | Generator Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1005 | Electrical | PS5-60-VS- 9100G-CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-60-VS- 9100G | Oil Mist Eliminator- CCV | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1006 | Electrical | PS5-61-BI-0001 -CL01 | PS5-60-IH- 0001A | GENERATOR A AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-61-BI-0001 | Power Transformer A Auxiliaries- Instrument Junction Box | Generator Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1007 | Electrical | PS5-61-BI-0002 -CL01 | PS5-60-IH- 0001B | GENERATOR B AUXILIARY MCC - Generator Elect.Building | Generator Electrical Building | PS5-61-BI-0002 | Power Transformer B Auxiliaries - Instrument Junction Box | Generator Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1008 | Electrical | PS5-61-BI-0003 -CL01 | PS5-60-IH- 0001C | GENERATOR C AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-61-BI-0003 | Power Transformer C Auxiliaries - Instrument Junction Box | Generator Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1009 | Electrical | PS5-61-BI-0004 -CL01 | PS5-60-IH- 0001D | GENERATOR D AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-61-BI-0004 | Power Transformer D Auxiliaries - Instrument Junction Box | Generator Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1010 | Electrical | PS5-61-BI-0005 -CL01 | PS5-60-IH- 0001E | GENERATOR E AUXILIARYMCC - Generator Elect.Building | Generator Electrical Building | PS5-61-BI-0005 | Power Transformer E - Auxiliaries Instrument Junction Box | Generator Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1011 | Electrical | PS5-61-BI-0006 -CL01 | PS5-60-IH-0001F | GENERATOR F AUXILIARY MCC - Generator Elect. Building | Generator Electrical Building | PS5-61-BI-0006 | Power Transformer F Auxiliaries - Instrument Junction Box | Generator Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1012 | Electrical | PS5-61-BI-0007 -CL01 | PS5-60-IH- 0001G | GENERATOR G AUXILIARY MCC - Generator Electrical Building | Generator Electrical Building | PS5-61-BI-0007 | Power Transformer G Auxiliaries - Instrument Junction Box | Generator Building | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1013 | Electrical | PS5-61-IDH- 3100A-CD01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1014 | Electrical | PS5-61-IDH- 3100A-CD02 | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1015 | Electrical | PS5-61-IDH- 3100A-CD03 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0217 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1016 | Electrical | PS5-61-IDH- 3100A-CH01 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1017 | Electrical | PS5-61-IDH- 3100A-CH02 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1018 | Electrical | PS5-61-IDH- 3100A-CH03 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1019 | Electrical | PS5-61-IDH- 3100A-CH04 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1020 | Electrical | PS5-61-IDH- 3100A-CH05 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1021 | Electrical | PS5-61-IDH- 3100A-CH06 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1022 | Electrical | PS5-61-IDH- 3100A-CH07 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1023 | Electrical | PS5-61-IDH- 3100A-CH08 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1024 | Electrical | PS5-61-IDH- 3100A-CH09 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1025 | Electrical | PS5-61-IDH- 3100A-CH10 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1026 | Electrical | PS5-61-IDH- 3100A-CH11 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1027 | Electrical | PS5-61-IDH- 3100A-CH12 | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1028 | Electrical | PS5-61-IDH- 3100A-CL01 | PS5-06-IG- 0001A | AC UPS Distribution Board (A) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1029 | Electrical | PS5-61-IDH- 3100B-CD01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1030 | Electrical | PS5-61-IDH- 3100B-CD02 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 30-April-20206 | CPP-RFI-68-331-05-0239 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1031 | Electrical | PS5-61-IDH- 3100B-CD03 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0217 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1032 | Electrical | PS5-61-IDH- 3100B-CH01 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1033 | Electrical | PS5-61-IDH- 3100B-CH02 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1034 | Electrical | PS5-61-IDH- 3100B-CH03 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1035 | Electrical | PS5-61-IDH- 3100B-CH04 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1036 | Electrical | PS5-61-IDH- 3100B-CH05 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1037 | Electrical | PS5-61-IDH- 3100B-CH06 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1038 | Electrical | PS5-61-IDH- 3100B-CH07 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1039 | Electrical | PS5-61-IDH- 3100B-CH08 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1040 | Electrical | PS5-61-IDH- 3100B-CH09 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1041 | Electrical | PS5-61-IDH- 3100B-CH10 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1042 | Electrical | PS5-61-IDH- 3100B-CH11 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1043 | Electrical | PS5-61-IDH- 3100B-CH12 | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1044 | Electrical | PS5-61-IDH- 3100B-CL01 | PS5-06-IG- 0001B | AC UPS Distribution Board (B) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1045 | Electrical | PS5-61-IDH- 3100C-CD01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1046 | Electrical | PS5-61-IDH- 3100C-CD02 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1047 | Electrical | PS5-61-IDH- 3100C-CD03 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0217 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1048 | Electrical | PS5-61-IDH- 3100C-CH01 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1049 | Electrical | PS5-61-IDH- 3100C-CH02 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1050 | Electrical | PS5-61-IDH- 3100C-CH03 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1051 | Electrical | PS5-61-IDH- 3100C-CH04 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1052 | Electrical | PS5-61-IDH- 3100C-CH05 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1053 | Electrical | PS5-61-IDH- 3100C-CH06 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1054 | Electrical | PS5-61-IDH- 3100C-CH07 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1055 | Electrical | PS5-61-IDH- 3100C-CH08 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1056 | Electrical | PS5-61-IDH- 3100C-CH09 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1057 | Electrical | PS5-61-IDH- 3100C-CH10 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1058 | Electrical | PS5-61-IDH- 3100C-CH11 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1059 | Electrical | PS5-61-IDH- 3100C-CH12 | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1060 | Electrical | PS5-61-IDH- 3100C-CL01 | PS5-06-IG- 0001B | AC UPS Distribution Board (B) Dual supply loads - 230VAC, 50Hz, 320A, 25KA/1s | EITS Building | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1061 | Electrical | PS5-61-IE-0002- CD01 | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1062 | Electrical | PS5-61-IE-0002- CD02 | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1063 | Electrical | PS5-61-IE-0002- CD03 | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1064 | Electrical | PS5-61-IE-0002- CD04 | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1065 | Electrical | PS5-61-IE-0002- CD05 | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1066 | Electrical | PS5-61-IE-0002- CD06 | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1067 | Electrical | PS5-61-IE-0002- CD41 | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | 2026-05-24 00:00:00 | CPP-RFI-68-331-05-0295 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1068 | Electrical | PS5-61-IE-0002- CD42 | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | 2026-05-24 00:00:00 | CPP-RFI-68-331-05-0295 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1069 | Electrical | PS5-61-IE-0002- CD43 | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1070 | Electrical | PS5-61-IE-0002- CD44 | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1071 | Electrical | PS5-61-IE-0003- CD01 | PS5-82-IN-0001 | MCC for Sewage Treatment Package | Sewage Treatment Pkge -North w | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1072 | Electrical | PS5-61-IE-0003- CD02 | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1073 | Electrical | PS5-61-IE-0003- CD03 | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1074 | Electrical | PS5-61-IE-0003- CD04 | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1075 | Electrical | PS5-61-IG-0006 -CD01 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-61-IG-0006 | Outdoor Normal L&SP DB - Field (South Side) | Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1076 | Electrical | PS5-61-IG-0006 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IG-0006 | Outdoor Normal L&SP DB - Field (South Side) | Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1077 | Electrical | PS5-61-IG-0007 -CD01 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-61-IG-0007 | Outdoor Normal Lighting DB - Field - (North Side) | Near EDG package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1078 | Electrical | PS5-61-IG-0007 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IG-0007 | Outdoor Normal Lighting DB - Field - (North Side) | Near EDG package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1079 | Electrical | PS5-61-IG- 0012A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IG- 0012A | VSD AUX. Distribution board (for VSD TAG PS5- 61-IDH-3100A) | VSD E house (PS5-83 -EHO-0001A) | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1080 | Electrical | PS5-61-IG- 0012B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IG- 0012B | VSD AUX. Distribution board (for VSD TAG PS5- 61-IDH-3100B) | VSD E house (PS5-83 -EHO-0001B) | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1081 | Electrical | PS5-61-IG- 0012C-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IG- 0012C | VSD AUX. Distribution board (for VSD TAG PS5- 61-IDH-3100C) | VSD E house (PS5-83 -EHO-0001C) | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1082 | Electrical | PS5-61-IG-0014 -CD01 | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | PS5-61-IG-0014 | Outdoor Power DB - Field(North) | Near EITS | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1083 | Electrical | PS5-61-IG-0014 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IG-0014 | Outdoor Power DB - Field(North) | Near EITS | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1084 | Electrical | PS5-61-IG-0015 -CD01 | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | PS5-61-IG-0015 | CRO Generator Building Normal L&SP Distribution Board PS-5 | Generator Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1085 | Electrical | PS5-61-IG-0015 -CL01 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IG-0015 | CRO Generator Building Normal L&SP Distribution Board PS-5 | Generator Building |  |  | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1086 | Electrical | PS5-61-IG-0016 -CD01 | PS5-61-IE-0003 | ECS 3 Panelboard | EITS Building | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1087 | Electrical | PS5-61-IG-0016 -CL01 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | 2026-06-17 00:00:00 | CPP-RFI-68-331-05-0347 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1088 | Electrical | PS5-61-IG-0042 -CD01 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
1089 | Electrical | PS5-61-IG-0042 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
1090 | Electrical | PS5-61-IG-0043 -CD01 | PS5-61-IE-0002 | ECS 2 Panelboard | EITS Building | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
1091 | Electrical | PS5-61-IG-0043 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | 30-April-20206 | CPP-RFI-68-331-05-0239 | 2026-07-01 00:00:00 | 2026-07-01 00:00:00
1092 | Electrical | PS5-61-IH-0004 -CG01 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1093 | Electrical | PS5-61-IH-0004 -CG02 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1094 | Electrical | PS5-61-IH-0004 -CG03 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1095 | Electrical | PS5-61-IH-0004 -CG04 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1096 | Electrical | PS5-61-IH-0004 -CL01 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1097 | Electrical | PS5-61-IH-0004 -CL02 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1098 | Electrical | PS5-61-IH-0004 -CL03 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1099 | Electrical | PS5-61-IH-0004 -CL04 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1100 | Electrical | PS5-61-IH-0004 -CL05 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1101 | Electrical | PS5-61-IH-0004 -CL06 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1102 | Electrical | PS5-61-IH-0004 -CL07 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1103 | Electrical | PS5-61-IH-0004 -CL08 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1104 | Electrical | PS5-61-IH-0004 -CL09 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1105 | Electrical | PS5-61-IH-0004 -CL10 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1106 | Electrical | PS5-61-IH-0004 -CL11 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1107 | Electrical | PS5-61-IH-0004 -CL12 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1108 | Electrical | PS5-61-IH-0004 -CL13 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1109 | Electrical | PS5-61-IH-0004 -CL14 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1110 | Electrical | PS5-61-IH-0004 -CL15 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1111 | Electrical | PS5-61-IH-0004 -CL16 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1112 | Electrical | PS5-61-IH-0004 -CL17 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1113 | Electrical | PS5-61-IH-0004 -CL18 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1114 | Electrical | PS5-61-IH-0004 -CL19 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1115 | Electrical | PS5-61-IH-0004 -CL20 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1116 | Electrical | PS5-61-IH-0004 -CL21 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1117 | Electrical | PS5-61-IH-0004 -CL22 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IH-0004 | HVAC MCC - Generator Building | Generator Electrical Building |  |  | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1118 | Electrical | PS5-61-IJ-0001- CD01 | PS5-63-IV-0010 | Earthing Transformer , 3368A, 33 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1119 | Electrical | PS5-61-IJ-0001- CD03 | PS5-63-IV-0011 | Earthing Transformer , 3368A, 33 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1120 | Electrical | PS5-61-IJ-0001- CD04 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1121 | Electrical | PS5-61-IJ-0001- CD05 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1122 | Electrical | PS5-61-IJ-0001- CD06 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1123 | Electrical | PS5-61-IJ-0001- CD07 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1124 | Electrical | PS5-61-IJ-0001- CD24 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1125 | Electrical | PS5-61-IJ-0001- CD25 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1126 | Electrical | PS5-61-IJ-0001- CD26 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1127 | Electrical | PS5-61-IJ-0001- CD27 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1128 | Electrical | PS5-61-IJ-0001- CD28 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1129 | Electrical | PS5-61-IJ-0001- CD29 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1130 | Electrical | PS5-61-IJ-0001- CD30 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1131 | Electrical | PS5-61-IJ-0001- CD31 | PS5-61-IV- 0005A | Distribution Transformer, Office BLD 0.42kV, 1MVA, ONAN , Dyn11, 33 / 0.42 Kv | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1132 | Electrical | PS5-61-IJ-0001- CD32 | PS5-61-IV-0005B | Distribution Transformer, Office BLD 0.42kV, 1MVA, ONAN , Dyn11, 33 / 0.42 Kv | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1133 | Electrical | PS5-61-IJ-0001- CD33 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1134 | Electrical | PS5-61-IJ-0001- CD34 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1135 | Electrical | PS5-61-IJ-0001- CD35 | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1136 | Electrical | PS5-61-IJ-0001- CD36 | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1137 | Electrical | PS5-61-IJ-0001- CD37 | PS5-61-ISR-0101 | 33kV Shunt Reactor - 3.63 MVAr | Transformer area | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-06-10 00:00:00 | CPP-RFI-68-33/1-05-0329 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1138 | Electrical | PS5-61-IJ-0001- CD38 | PS5-61-ISR-0102 | 33kV Shunt Reactor - 7.2 MVAR | Transformer area | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1139 | Electrical | PS5-61-IJ-0001- CD39 | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1140 | Electrical | PS5-61-IJ-0001- CD40 | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1141 | Electrical | PS5-61-IJ-0001- CD41 | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1142 | Electrical | PS5-61-IJ-0001- CD42 | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1143 | Electrical | PS5-61-IJ-0001- | PS5-61-IU- 0001A | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building
1144 | Electrical | PS5-61-IJ-0001- | PS5-61-IU- 0001B | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building
1145 | Electrical | PS5-61-IJ-0001- | PS5-61-IU- 0001C | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building
1146 | Electrical | PS5-61-IJ-0001- | PS5-61-IU- 0001D | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building
1147 | Electrical | PS5-61-IJ-0001- | PS5-61-IU- 0001E | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building
1148 | Electrical | PS5-61-IJ-0001- | PS5-61-IU- 0001F | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building
1149 | Electrical | PS5-61-IJ-0001- | PS5-61-IU- 0001G | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building
1150 | Electrical | PS5-61-IJ-0001- CD61 | PS5-60-IE-0003A | Generator control panel for generator set-1 (A) | Generator Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1151 | Electrical | PS5-61-IJ-0001- CD62 | PS5-60-IE-0003B | Generator control panel for generator set-2 (B) | Generator Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1152 | Electrical | PS5-61-IJ-0001- CD63 | PS5-60-IE-0003C | Generator control panel for generator set-3 (C) | Generator Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1153 | Electrical | PS5-61-IJ-0001- CD64 | PS5-60-IE- 0003D | Generator control panel for generator set- 4 (D) | Generator Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1154 | Electrical | PS5-61-IJ-0001- CD65 | PS5-60-IE-0003E | Generator control panel for generator set- 5 (E) | Generator Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1155 | Electrical | PS5-61-IJ-0001- CD66 | PS5-60-IE-0003F | Generator control panel for generator set- 6 (F) | Generator Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1156 | Electrical | PS5-61-IJ-0001- CD67 | PS5-60-IE- 0003G | Generator control panel for GENERATOR SET- 7 (G) | Generator Electrical Building | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-19 00:00:00 | CPP-RFI-68-331-05-0275 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1157 | Electrical | PS5-61-IJ-0001- CH01 | PS5-61-IU- 0001A | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1158 | Electrical | PS5-61-IJ-0001- CH02 | PS5-61-IU- 0001A | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1159 | Electrical | PS5-61-IJ-0001- CH03 | PS5-61-IU- 0001A | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1160 | Electrical | PS5-61-IJ-0001- CH04 | PS5-61-IU- 0001B | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1161 | Electrical | PS5-61-IJ-0001- CH05 | PS5-61-IU- 0001B | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1162 | Electrical | PS5-61-IJ-0001- CH06 | PS5-61-IU- 0001B | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1163 | Electrical | PS5-61-IJ-0001- CH07 | PS5-61-IU- 0001C | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1164 | Electrical | PS5-61-IJ-0001- CH08 | PS5-61-IU- 0001C | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1165 | Electrical | PS5-61-IJ-0001- CH09 | PS5-61-IU- 0001C | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1166 | Electrical | PS5-61-IJ-0001- CH10 | PS5-61-IU- 0001D | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1167 | Electrical | PS5-61-IJ-0001- CH11 | PS5-61-IU- 0001D | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1168 | Electrical | PS5-61-IJ-0001- CH12 | PS5-61-IU- 0001D | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1169 | Electrical | PS5-61-IJ-0001- CH13 | PS5-61-IU- 0001E | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1170 | Electrical | PS5-61-IJ-0001- CH14 | PS5-61-IU- 0001E | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1171 | Electrical | PS5-61-IJ-0001- CH15 | PS5-61-IU- 0001E | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1172 | Electrical | PS5-61-IJ-0001- CH16 | PS5-61-IU- 0001F | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1173 | Electrical | PS5-61-IJ-0001- CH17 | PS5-61-IU- 0001F | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1174 | Electrical | PS5-61-IJ-0001- CH18 | PS5-61-IU- 0001F | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1175 | Electrical | PS5-61-IJ-0001- CH19 | PS5-61-IU- 0001G | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1176 | Electrical | PS5-61-IJ-0001- CH20 | PS5-61-IU- 0001G | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1177 | Electrical | PS5-61-IJ-0001- CH21 | PS5-61-IU- 0001G | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-03-31 00:00:00 | CPP-RFI-68-33/1-05-0196 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1178 | Electrical | PS5-61-IJ-0001- CL01 | PS5-63-NER- 0010 | NER for Earthing Transformer (PS5-63-IV- 0010) | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1179 | Electrical | PS5-61-IJ-0001- CL02 | PS5-63-NER- 0011 | NER for Earthing Transformer (PS5-63-IV- 0011) | EITS Building (Outdoors) | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1180 | Electrical | PS5-61-IJ-0010- CH01 | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | PS5-61-IJ-0010 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0198 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1181 | Electrical | PS5-61-IJ-0010- CH02 | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | PS5-61-IJ-0010 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0198 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1182 | Electrical | PS5-61-IJ-0010- CH03 | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | PS5-61-IJ-0010 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0198 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1183 | Electrical | PS5-61-IJ-0010- CL01 | PS5-61-NER- 0010 | NER of LLHT Transformer 0.696MVA, Dyn11, 33/1.75-3.35kV | Outside EITS | PS5-61-IJ-0010 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1184 | Electrical | PS5-61-IJ-0011- CH01 | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | PS5-61-IJ-0011 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0198 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1185 | Electrical | PS5-61-IJ-0011- CH02 | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | PS5-61-IJ-0011 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0198 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1186 | Electrical | PS5-61-IJ-0011- CH03 | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | PS5-61-IJ-0011 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0198 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1187 | Electrical | PS5-61-IJ-0011- CL01 | PS5-61-NER- 0011 | NER of LLHT Transformer 1.247MVA, Dyn11, 33/3.2-6kV | Outside EITS | PS5-61-IJ-0011 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1188 | Electrical | PS5-61-IK-0001- CG01 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1189 | Electrical | PS5-61-IK-0001- CG02 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1190 | Electrical | PS5-61-IK-0001- CG03 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1191 | Electrical | PS5-61-IK-0001- CG04 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1192 | Electrical | PS5-61-IK-0001- CL01 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1193 | Electrical | PS5-61-IK-0001- CL02 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1194 | Electrical | PS5-61-IK-0001- CL03 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1195 | Electrical | PS5-61-IK-0001- CL04 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1196 | Electrical | PS5-61-IK-0001- CL05 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1197 | Electrical | PS5-61-IK-0001- CL06 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1198 | Electrical | PS5-61-IK-0001- CL07 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1199 | Electrical | PS5-61-IK-0001- CL08 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1200 | Electrical | PS5-61-IK-0001- CL09 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1201 | Electrical | PS5-61-IK-0001- CL10 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1202 | Electrical | PS5-61-IK-0001- CL11 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1203 | Electrical | PS5-61-IK-0001- CL12 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1204 | Electrical | PS5-61-IK-0001- CL13 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1205 | Electrical | PS5-61-IK-0001- CL14 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1206 | Electrical | PS5-61-IK-0001- CL15 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1207 | Electrical | PS5-61-IK-0001- CL16 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1208 | Electrical | PS5-61-IK-0001- CL17 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1209 | Electrical | PS5-61-IK-0001- CL18 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1210 | Electrical | PS5-61-IK-0001- CL19 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1211 | Electrical | PS5-61-IK-0001- CL20 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1212 | Electrical | PS5-61-IK-0001- CL21 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1213 | Electrical | PS5-61-IK-0001- CL22 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1214 | Electrical | PS5-61-IK-0001- CL23 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1215 | Electrical | PS5-61-IK-0001- CL24 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1216 | Electrical | PS5-61-IK-0001- CL25 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1217 | Electrical | PS5-61-IK-0001- CL26 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1218 | Electrical | PS5-61-IK-0001- CL27 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1219 | Electrical | PS5-61-IK-0001- CL28 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1220 | Electrical | PS5-61-IK-0001- CL29 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1221 | Electrical | PS5-61-IK-0001- CL30 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1222 | Electrical | PS5-61-IK-0001- CL31 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1223 | Electrical | PS5-61-IK-0001- CL32 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1224 | Electrical | PS5-61-IK-0001- CL33 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1225 | Electrical | PS5-61-IK-0001- CL34 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1226 | Electrical | PS5-61-IK-0001- CL35 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1227 | Electrical | PS5-61-IK-0001- CL36 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1228 | Electrical | PS5-61-IK-0001- CL37 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1229 | Electrical | PS5-61-IK-0001- CL38 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1230 | Electrical | PS5-61-IK-0001- CL39 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1231 | Electrical | PS5-61-IK-0001- CL40 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1232 | Electrical | PS5-61-IK-0001- CL41 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1233 | Electrical | PS5-61-IK-0001- CL42 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1234 | Electrical | PS5-61-IK-0001- CL43 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1235 | Electrical | PS5-61-IK-0001- CL44 | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1236 | Electrical | PS5-61-IK-0001- CL45 | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1237 | Electrical | PS5-61-IK-0003- CG01 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1238 | Electrical | PS5-61-IK-0003- CG02 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1239 | Electrical | PS5-61-IK-0003- CG03 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1240 | Electrical | PS5-61-IK-0003- CG04 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1241 | Electrical | PS5-61-IK-0003- CG05 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1242 | Electrical | PS5-61-IK-0003- CG06 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1243 | Electrical | PS5-61-IK-0003- CG07 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1244 | Electrical | PS5-61-IK-0003- CL01 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1245 | Electrical | PS5-61-IK-0003- CL02 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-06-20 00:00:00 | CPP-RFI-68-331-05-0368 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1246 | Electrical | PS5-61-IK-0003- CL04 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1247 | Electrical | PS5-61-IK-0003- CL05 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1248 | Electrical | PS5-61-IK-0003- CL06 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1249 | Electrical | PS5-61-IK-0003- CL07 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1250 | Electrical | PS5-61-IK-0003- CL08 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1251 | Electrical | PS5-61-IK-0003- CL09 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1252 | Electrical | PS5-61-IK-0003- CL10 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1253 | Electrical | PS5-61-IK-0003- CL11 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1254 | Electrical | PS5-61-IK-0003- CL12 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1255 | Electrical | PS5-61-IK-0003- CL13 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1256 | Electrical | PS5-61-IK-0003- CL14 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1257 | Electrical | PS5-61-IK-0003- CL15 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1258 | Electrical | PS5-61-IK-0003- CL16 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1259 | Electrical | PS5-61-IK-0003- CL17 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1260 | Electrical | PS5-61-IK-0003- CL18 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1261 | Electrical | PS5-61-IK-0003- CL19 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1262 | Electrical | PS5-61-IK-0003- CL20 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1263 | Electrical | PS5-61-IK-0003- CL21 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1264 | Electrical | PS5-61-IK-0003- CL22 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1265 | Electrical | PS5-61-IK-0003- CL23 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1266 | Electrical | PS5-61-IK-0003- CL24 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1267 | Electrical | PS5-61-IK-0003- CL25 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1268 | Electrical | PS5-61-IK-0003- CL26 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1269 | Electrical | PS5-61-IK-0003- CL27 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1270 | Electrical | PS5-61-IK-0003- CL28 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1271 | Electrical | PS5-61-IK-0003- CL29 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1272 | Electrical | PS5-61-IK-0003- CL30 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1273 | Electrical | PS5-61-IK-0003- CL31 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1274 | Electrical | PS5-61-IK-0003- CL32 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1275 | Electrical | PS5-61-IK-0003- CL33 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1276 | Electrical | PS5-61-IK-0003- CL34 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1277 | Electrical | PS5-61-IK-0003- CL35 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1278 | Electrical | PS5-61-IK-0003- CL36 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1279 | Electrical | PS5-61-IK-0003- CL37 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1280 | Electrical | PS5-61-IK-0003- CL38 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1281 | Electrical | PS5-61-IK-0003- CL39 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1282 | Electrical | PS5-61-IK-0003- CL40 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1283 | Electrical | PS5-61-IK-0003- CL41 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1284 | Electrical | PS5-61-IK-0003- CL42 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1285 | Electrical | PS5-61-IK-0003- CL43 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1286 | Electrical | PS5-61-IK-0003- CL44 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1287 | Electrical | PS5-61-IK-0003- CL45 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1288 | Electrical | PS5-61-IK-0003- CL46 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1289 | Electrical | PS5-61-IK-0003- CL47 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1290 | Electrical | PS5-61-IK-0003- CL48 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1291 | Electrical | PS5-61-IK-0003- CL49 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1292 | Electrical | PS5-61-IK-0003- CL50 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1293 | Electrical | PS5-61-IK-0003- CL51 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1294 | Electrical | PS5-61-IK-0003- CL52 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1295 | Electrical | PS5-61-IK-0003- CL53 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1296 | Electrical | PS5-61-IK-0003- CL54 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-05-07 00:00:00 | CPP-RFI-68-331-05-0250 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1297 | Electrical | PS5-61-IK-0003- CL55 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-30 00:00:00 | CPP-RFI-68-331-05-0238 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1298 | Electrical | PS5-61-IK-0003- CL56 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-30 00:00:00 | CPP-RFI-68-331-05-0238 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1299 | Electrical | PS5-61-IK-0003- CL57 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1300 | Electrical | PS5-61-IK-0003- CL58 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1301 | Electrical | PS5-61-IK-0003- CL59 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1302 | Electrical | PS5-61-IK-0003- CL60 | PS5-05-BE-0001 | EDG Power JB | Near EDG | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1303 | Electrical | PS5-61-IK-0003- CL61 | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1304 | Electrical | PS5-61-IK-0003- CL62 | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1305 | Electrical | PS5-61-IK-0005- CD01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IK-0005 | 0.4kV Switchboard | Office & Facilities Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1306 | Electrical | PS5-61-IK-0005- CD02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IK-0005 | 0.4kV Switchboard | Office & Facilities Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1307 | Electrical | PS5-61-IK-0005- CL01 | PS5-61-IK-0003 | 0.4kV Switchboard | Generator Electrical Building | PS5-61-IK-0005 | 0.4kV Switchboard | Office & Facilities Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1308 | Electrical | PS5-61-IK-0006- CG01 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building |  |  | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1309 | Electrical | PS5-61-IK-0006- CG02 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building |  |  | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1310 | Electrical | PS5-61-IK-0006- CG03 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building |  |  | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1311 | Electrical | PS5-61-IK-0006- CG04 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building |  |  | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1312 | Electrical | PS5-61-IK-0006- CL01 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1313 | Electrical | PS5-61-IK-0006- CL02 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1314 | Electrical | PS5-61-IK-0006- CL03 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1315 | Electrical | PS5-61-IK-0006- CL04 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1316 | Electrical | PS5-61-IK-0006- CL05 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1317 | Electrical | PS5-61-IK-0006- CL06 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1318 | Electrical | PS5-61-IK-0006- CL07 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1319 | Electrical | PS5-61-IK-0006- CL08 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1320 | Electrical | PS5-61-IK-0006- CL09 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1321 | Electrical | PS5-61-IK-0006- CL10 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1322 | Electrical | PS5-61-IK-0006- CL11 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1323 | Electrical | PS5-61-IK-0006- CL12 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1324 | Electrical | PS5-61-IK-0006- CL13 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1325 | Electrical | PS5-61-IK-0006- CL14 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1326 | Electrical | PS5-61-IK-0006- CL15 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1327 | Electrical | PS5-61-IK-0006- CL16 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1328 | Electrical | PS5-61-IK-0006- CL17 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1329 | Electrical | PS5-61-IK-0006- CL18 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1330 | Electrical | PS5-61-IK-0006- CL19 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1331 | Electrical | PS5-61-IK-0006- CL20 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1332 | Electrical | PS5-61-IK-0006- CL21 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1333 | Electrical | PS5-61-IK-0006- CL22 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1334 | Electrical | PS5-61-IK-0006- CL23 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1335 | Electrical | PS5-61-IK-0006- CL24 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1336 | Electrical | PS5-61-IK-0006- CL25 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1337 | Electrical | PS5-61-IK-0006- CL26 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1338 | Electrical | PS5-61-IK-0006- CL27 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1339 | Electrical | PS5-61-IK-0006- CL28 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-12 00:00:00 | CPP-RFI-68-331-05-0264 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1340 | Electrical | PS5-61-IK-0006- CL29 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building |  |  | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1341 | Electrical | PS5-61-IK-0006- CL30 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building |  |  | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1342 | Electrical | PS5-61-IK-0006- CL31 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building |  |  | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1343 | Electrical | PS5-61-IK-0006- CL32 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building |  |  | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1344 | Electrical | PS5-61-IK-0006- CL33 | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1345 | Electrical | PS5-61-IK-0006- CL34 | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1346 | Electrical | PS5-61-ISR- 0101-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-ISR-0101 | 33kV Shunt Reactor - 3.63 MVAr | Transformer area | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1347 | Electrical | PS5-61-ISR- 0101-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-ISR-0101 | 33kV Shunt Reactor - 3.63 MVAr | Transformer area | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1348 | Electrical | PS5-61-ISR- 0101-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-ISR-0101 | 33kV Shunt Reactor - 3.63 MVAr | Transformer area | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1349 | Electrical | PS5-61-ISR- 0101-CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-61-ISR-0101 | 33kV Shunt Reactor - 3.63 MVAr | Transformer area | 30-April-20206 | CPP-RFI-68-331-05-0239 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1350 | Electrical | PS5-61-ISR- 0102-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-ISR-0102 | 33kV Shunt Reactor - 7.2 MVAR | Transformer area | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1351 | Electrical | PS5-61-ISR- 0102-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-ISR-0102 | 33kV Shunt Reactor - 7.2 MVAR | Transformer area | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1352 | Electrical | PS5-61-ISR- 0102-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-ISR-0102 | 33kV Shunt Reactor - 7.2 MVAR | Transformer area | 2026-03-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1353 | Electrical | PS5-61-ISR- 0102-CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-61-ISR-0102 | 33kV Shunt Reactor - 7.2 MVAR | Transformer area | 30-April-20206 | CPP-RFI-68-331-05-0239 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1354 | Electrical | PS5-61-IU- 0001A-CH01 | PS5-60-GE- 8100A | Power Generator | Power generator building area | PS5-61-IU- 0001A | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1355 | Electrical | PS5-61-IU- 0001A-CH02 | PS5-60-GE- 8100A | Power Generator | Power generator building area | PS5-61-IU- 0001A | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1356 | Electrical | PS5-61-IU- 0001A-CH03 | PS5-60-GE- 8100A | Power Generator | Power generator building area | PS5-61-IU- 0001A | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1357 | Electrical | PS5-61-IU- 0001B-CH01 | PS5-60-GE- 8100B | Power Generator | Power generator building area | PS5-61-IU- 0001B | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1358 | Electrical | PS5-61-IU- 0001B-CH02 | PS5-60-GE- 8100B | Power Generator | Power generator building area | PS5-61-IU- 0001B | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1359 | Electrical | PS5-61-IU- 0001B-CH03 | PS5-60-GE- 8100B | Power Generator | Power generator building area | PS5-61-IU- 0001B | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1360 | Electrical | PS5-61-IU- 0001C-CH01 | PS5-60-GE- 8100C | Power Generator | Power generator building area | PS5-61-IU- 0001C | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1361 | Electrical | PS5-61-IU- 0001C-CH02 | PS5-60-GE- 8100C | Power Generator | Power generator building area | PS5-61-IU- 0001C | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1362 | Electrical | PS5-61-IU- 0001C-CH03 | PS5-60-GE- 8100C | Power Generator | Power generator building area | PS5-61-IU- 0001C | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1363 | Electrical | PS5-61-IU- 0001D-CH01 | PS5-60-GE- 8100D | Power Generator | Power generator building area | PS5-61-IU- 0001D | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1364 | Electrical | PS5-61-IU- 0001D-CH02 | PS5-60-GE- 8100D | Power Generator | Power generator building area | PS5-61-IU- 0001D | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1365 | Electrical | PS5-61-IU- 0001D-CH03 | PS5-60-GE- 8100D | Power Generator | Power generator building area | PS5-61-IU- 0001D | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1366 | Electrical | PS5-61-IU- 0001E-CH01 | PS5-60-GE- 8100E | Power Generator | Power generator building area | PS5-61-IU- 0001E | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1367 | Electrical | PS5-61-IU- 0001E-CH02 | PS5-60-GE- 8100E | Power Generator | Power generator building area | PS5-61-IU- 0001E | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1368 | Electrical | PS5-61-IU- 0001E-CH03 | PS5-60-GE- 8100E | Power Generator | Power generator building area | PS5-61-IU- 0001E | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1369 | Electrical | PS5-61-IU- 0001F-CH01 | PS5-60-GE- 8100F | Power Generator | Power generator building area | PS5-61-IU- 0001F | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1370 | Electrical | PS5-61-IU- 0001F-CH02 | PS5-60-GE- 8100F | Power Generator | Power generator building area | PS5-61-IU- 0001F | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1371 | Electrical | PS5-61-IU- 0001F-CH03 | PS5-60-GE- 8100F | Power Generator | Power generator building area | PS5-61-IU- 0001F | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1372 | Electrical | PS5-61-IU- 0001G-CH01 | PS5-60-GE- 8100G | Power Generator | Power generator building area | PS5-61-IU- 0001G | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1373 | Electrical | PS5-61-IU- 0001G-CH02 | PS5-60-GE- 8100G | Power Generator | Power generator building area | PS5-61-IU- 0001G | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1374 | Electrical | PS5-61-IU- 0001G-CH03 | PS5-60-GE- 8100G | Power Generator | Power generator building area | PS5-61-IU- 0001G | 11/33kV Transformer - 6.8 MVA | EITS Building (Outdoors) | 2026-02-20 00:00:00 | CPP-RFI-68-33/1-05-161 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1375 | Electrical | PS5-61-IU-0010 -CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1376 | Electrical | PS5-61-IU-0010 -CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1377 | Electrical | PS5-61-IU-0010 -CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1378 | Electrical | PS5-61-IU-0010 -CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | 30-April-20206 | CPP-RFI-68-331-05-0239 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1379 | Electrical | PS5-61-IU-0010 -CL02 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | 2026-05-03 00:00:00 | CPP-RFI-68-331-05-0243 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1380 | Electrical | PS5-61-IU-0011 -CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1381 | Electrical | PS5-61-IU-0011 -CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1382 | Electrical | PS5-61-IU-0011 -CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1383 | Electrical | PS5-61-IU-0011 -CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | 30-April-20206 | CPP-RFI-68-331-05-0239 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1384 | Electrical | PS5-61-IU-0011 -CL02 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | 30-April-20206 | CPP-RFI-68-331-05-0239 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1385 | Electrical | PS5-61-IU- 3100A-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-18 00:00:00 | CPP-RFI-68-33/1-05-181 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1386 | Electrical | PS5-61-IU- 3100A-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-18 00:00:00 | CPP-RFI-68-33/1-05-181 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1387 | Electrical | PS5-61-IU- 3100A-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-18 00:00:00 | CPP-RFI-68-33/1-05-181 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1388 | Electrical | PS5-61-IU- 3100A-CH04 | PS5-61-IV- 0006A | Pre-Magnetisation Transformer - VSD Package | VSD Package | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1389 | Electrical | PS5-61-IU- 3100A-CL01 | PS5-61-IDH- 3100A | Variable Speed Drive - Export Pump | VSD E-house | PS5-61-IU- 3100A | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0217 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1390 | Electrical | PS5-61-IU- 3100B-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-18 00:00:00 | CPP-RFI-68-33/1-05-181 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1391 | Electrical | PS5-61-IU- 3100B-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-18 00:00:00 | CPP-RFI-68-33/1-05-181 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1392 | Electrical | PS5-61-IU- 3100B-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-18 00:00:00 | CPP-RFI-68-33/1-05-181 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1393 | Electrical | PS5-61-IU- 3100B-CH04 | PS5-61-IV-0006B | Pre-Magnetisation Transformer - VSD Package | VSD Package | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1394 | Electrical | PS5-61-IU- 3100B-CL01 | PS5-61-IDH- 3100B | Variable Speed Drive - Export Pump | VSD E-house | PS5-61-IU- 3100B | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0217 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1395 | Electrical | PS5-61-IU- 3100C-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-18 00:00:00 | CPP-RFI-68-33/1-05-181 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1396 | Electrical | PS5-61-IU- 3100C-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-18 00:00:00 | CPP-RFI-68-33/1-05-181 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1397 | Electrical | PS5-61-IU- 3100C-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-18 00:00:00 | CPP-RFI-68-33/1-05-181 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1398 | Electrical | PS5-61-IU- 3100C-CH04 | PS5-61-IV-0006C | Pre-Magnetisation Transformer - VSD Package | VSD Package | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-03-28 00:00:00 | CPP-RFI-68-33/1-05-0192 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1399 | Electrical | PS5-61-IU- 3100C-CL01 | PS5-61-IDH- 3100C | Variable Speed Drive - Export Pump | VSD E-house | PS5-61-IU- 3100C | 33kV VSD Transformer | VSD Pre-Fabricated E house | 2026-04-15 00:00:00 | CPP-RFI-68-33/1-05-0217 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1400 | Electrical | PS5-61-IV- 0001A-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1401 | Electrical | PS5-61-IV- 0001A-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1402 | Electrical | PS5-61-IV- 0001A-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1403 | Electrical | PS5-61-IV- 0001A-CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-61-IV- 0001A | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1404 | Electrical | PS5-61-IV- 0001B-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1405 | Electrical | PS5-61-IV- 0001B-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1406 | Electrical | PS5-61-IV- 0001B-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1407 | Electrical | PS5-61-IV- 0001B-CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-61-IV-0001B | Distribution Transformer, Main LV MCC 0.42kV, 2.5MVA, ONAN, Dyn11, 33 / 0.42 kV | Outdoor | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1408 | Electrical | PS5-61-IV- 0002A-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1409 | Electrical | PS5-61-IV- 0002A-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1410 | Electrical | PS5-61-IV- 0002A-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1411 | Electrical | PS5-61-IV- 0002A-CL01 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-61-IV- 0002A | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1412 | Electrical | PS5-61-IV- 0002B-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1413 | Electrical | PS5-61-IV- 0002B-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1414 | Electrical | PS5-61-IV- 0002B-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1415 | Electrical | PS5-61-IV- 0002B-CL01 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-61-IV-0002B | Distribution Transformer, Power generator BLD 0.42kV, 2.5MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1416 | Electrical | PS5-61-IV- 0005A-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0005A | Distribution Transformer, Office BLD 0.42kV, 1MVA, ONAN , Dyn11, 33 / 0.42 Kv | Outdoor |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1417 | Electrical | PS5-61-IV- 0005A-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0005A | Distribution Transformer, Office BLD 0.42kV, 1MVA, ONAN , Dyn11, 33 / 0.42 Kv | Outdoor |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1418 | Electrical | PS5-61-IV- 0005A-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0005A | Distribution Transformer, Office BLD 0.42kV, 1MVA, ONAN , Dyn11, 33 / 0.42 Kv | Outdoor |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1419 | Electrical | PS5-61-IV- 0005B-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0005B | Distribution Transformer, Office BLD 0.42kV, 1MVA, ONAN , Dyn11, 33 / 0.42 Kv | Outdoor |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1420 | Electrical | PS5-61-IV- 0005B-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0005B | Distribution Transformer, Office BLD 0.42kV, 1MVA, ONAN , Dyn11, 33 / 0.42 Kv | Outdoor |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1421 | Electrical | PS5-61-IV- 0005B-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0005B | Distribution Transformer, Office BLD 0.42kV, 1MVA, ONAN , Dyn11, 33 / 0.42 Kv | Outdoor |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1422 | Electrical | PS5-61-IV- 0006A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IV- 0006A | Pre-Magnetisation Transformer - VSD Package | VSD Package | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1423 | Electrical | PS5-61-IV- 0006B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IV-0006B | Pre-Magnetisation Transformer - VSD Package | VSD Package | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1424 | Electrical | PS5-61-IV- 0006C-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-61-IV-0006C | Pre-Magnetisation Transformer - VSD Package | VSD Package | 2026-04-17 00:00:00 | CPP-RFI-68-331-05-0215 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1425 | Electrical | PS5-61-IV- 0007A-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1426 | Electrical | PS5-61-IV- 0007A-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1427 | Electrical | PS5-61-IV- 0007A-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1428 | Electrical | PS5-61-IV- 0007A-CL01 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-61-IV- 0007A | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1429 | Electrical | PS5-61-IV- 0007B-CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1430 | Electrical | PS5-61-IV- 0007B-CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1431 | Electrical | PS5-61-IV- 0007B-CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-03-22 00:00:00 | CPP-RFI-68-33/1-05-0184 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1432 | Electrical | PS5-61-IV- 0007B-CL01 | PS5-61-IG-0016 | Generator Electrical Building Normal L&SP Distribution Board PS-5 | Generator Electrical Building | PS5-61-IV-0007B | Distribution Transformer, New Power generator BLD 0.42kV, 2MVA, ONAN , Dyn11, 33 / 0.42 kV | Outdoor | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0228 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1433 | Electrical | PS5-61-NER- 0010-CH01 | PS5-61-IU-0010 | LLHT Oil Transformer, EACOP North , 0.696 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 3.35-1.75 Kv | Outdoor | PS5-61-NER- 0010 | NER of LLHT Transformer 0.696MVA, Dyn11, 33/1.75-3.35kV | Outside EITS | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1434 | Electrical | PS5-61-NER- 0010-CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-61-NER- 0010 | NER of LLHT Transformer 0.696MVA, Dyn11, 33/1.75-3.35kV | Outside EITS | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1435 | Electrical | PS5-61-NER- 0011-CH01 | PS5-61-IU-0011 | LLHT Oil Transformer, EACOP South, 1.248 MVA, ONAN, Motorised, DETC, CAPT, 9 steps, 33 / 6-3.2 kV | Outdoor | PS5-61-NER- 0011 | NER of LLHT Transformer 1.247MVA, Dyn11, 33/3.2-6kV | Outside EITS | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1436 | Electrical | PS5-61-NER- 0011-CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-61-NER- 0011 | NER of LLHT Transformer 1.247MVA, Dyn11, 33/3.2-6kV | Outside EITS | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1437 | Electrical | PS5-62-IE-0001- CD01 | PS5-62-IE-0002 | Lighting Control panel 2 - Pump Station 5 | Near EDG package | PS5-62-IE-0001 | Lighting Control panel 1 - Pump Station 5 | Near Export pump area | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1438 | Electrical | PS5-62-IE-0001- CL01 | PS5-05-IG-0006 | Outdoor Emergency Lighting DB - Field - (North Side) | Near EDG package | PS5-62-IE-0001 | Lighting Control panel 1 - Pump Station 5 | Near Export pump area | 2026-04-25 00:00:00 | CPP-RFI-68-331-05-0226 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1439 | Electrical | PS5-62-IE-0002- CD01 | PS5-08-15CB- 1001 | TELECOM SII SP3 SEC Cabinet | EITS Building | PS5-62-IE-0002 | Lighting Control panel 2 - Pump Station 5 | Near EDG package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1440 | Electrical | PS5-62-IE-0002- CL01 | PS5-05-IG-0004 | Outdoor Emergency Lighting DB - Field - (South Side) | Near Export pump area | PS5-62-IE-0002 | Lighting Control panel 2 - Pump Station 5 | Near EDG package | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1441 | Electrical | PS5-63-IV-0010 -CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-63-IV-0010 | Earthing Transformer , 3368A, 33 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1442 | Electrical | PS5-63-IV-0010 -CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-63-IV-0010 | Earthing Transformer , 3368A, 33 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1443 | Electrical | PS5-63-IV-0010 -CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-63-IV-0010 | Earthing Transformer , 3368A, 33 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1444 | Electrical | PS5-63-IV-0010 -CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-63-IV-0010 | Earthing Transformer , 3368A, 33 kV | Outdoor | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1445 | Electrical | PS5-63-IV-0011 -CH01 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-63-IV-0011 | Earthing Transformer , 3368A, 33 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1446 | Electrical | PS5-63-IV-0011 -CH02 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-63-IV-0011 | Earthing Transformer , 3368A, 33 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1447 | Electrical | PS5-63-IV-0011 -CH03 | PS5-61-IJ-0001 | CBGS-0 33kV MV Switchgear, 1250A, IAC AFLR 25kA/3s | EITS Building | PS5-63-IV-0011 | Earthing Transformer , 3368A, 33 kV | Outdoor | 2026-04-02 00:00:00 | CPP-RFI-68-33/1-05-0197 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1448 | Electrical | PS5-63-IV-0011 -CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-63-IV-0011 | Earthing Transformer , 3368A, 33 kV | Outdoor | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1449 | Electrical | PS5-63-NER- 0010-CH01 | PS5-63-IV-0010 | Earthing Transformer , 3368A, 33 kV | Outdoor | PS5-63-NER- 0010 | NER for Earthing Transformer (PS5-63-IV- 0010) | EITS Building (Outdoors) | 2026-04-11 00:00:00 | CPP-RFI-68-331-05-0210 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1450 | Electrical | PS5-63-NER- 0010-CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-63-NER- 0010 | NER for Earthing Transformer (PS5-63-IV- 0010) | EITS Building (Outdoors) | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1451 | Electrical | PS5-63-NER- 0011-CH01 | PS5-63-IV-0011 | Earthing Transformer , 3368A, 33 kV | Outdoor | PS5-63-NER- 0011 | NER for Earthing Transformer (PS5-63-IV- 0011) | EITS Building (Outdoors) | 2026-04-11 00:00:00 | CPP-RFI-68-331-05-0210 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1452 | Electrical | PS5-63-NER- 0011-CL01 | PS5-61-IG-0008 | Normal Auxiliary Distribution Panel - 3Ph 400 Inc, 1Ph 230VAC Outgoings, 160A, 50KA/1s | EITS Building | PS5-63-NER- 0011 | NER for Earthing Transformer (PS5-63-IV- 0011) | EITS Building (Outdoors) | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-07-05 00:00:00 | 2026-07-05 00:00:00
1453 | Electrical | PS5-71-BE-0004 -CL01 | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building | PS5-71-BE-0004 | CRO- prepressure module power junction box-JB3 | Generator Building | 2026-07-02 00:00:00 | CPP-RFI-68-331-05-0399 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1454 | Electrical | PS5-71-BE-0004 -CL02 | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building | PS5-71-BE-0004 | CRO- prepressure module power junction box-JB3 | Generator Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1455 | Electrical | PS5-71-BE-0004 -CL03 | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building | PS5-71-BE-0004 | CRO- prepressure module power junction box-JB3 | Generator Building | 2026-07-02 00:00:00 | CPP-RFI-68-331-05-0399 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1456 | Electrical | PS5-71-BI-0003 -CL01 | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building | PS5-71-BI-0003 | CRO- prepressure module control junction box-JB1 | Generator Building | 2026-07-02 00:00:00 | CPP-RFI-68-331-05-0399 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1457 | Electrical | PS5-71-BI-0003 -CL02 | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building | PS5-71-BI-0003 | CRO- prepressure module control junction box-JB1 | Generator Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1458 | Electrical | PS5-71-BI-0003 -CL03 | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building | PS5-71-BI-0003 | CRO- prepressure module control junction box-JB1 | Generator Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1459 | Electrical | PS5-71-BI-0003 -CL04 | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building | PS5-71-BI-0003 | CRO- prepressure module control junction box-JB1 | Generator Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1460 | Electrical | PS5-71-BI-0004 -CL01 | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building | PS5-71-BI-0004 | CRO- prepressure module control junction box-JB2 | Generator Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1461 | Electrical | PS5-71-BI-0005 -CL01 | PS5-71-IN-0003 | DFO- PRE PRESSURE CONTROL PANEL | Generator Electrical Building | PS5-71-BI-0005 | DFO- prepressure module control junction box-JB1 | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
1462 | Electrical | PS5-71-BI-0005 -CL02 | PS5-71-IN-0003 | DFO- PRE PRESSURE CONTROL PANEL | Generator Electrical Building | PS5-71-BI-0005 | DFO- prepressure module control junction box-JB1 | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
1463 | Electrical | PS5-71-BI-0005 -CL03 | PS5-71-IN-0003 | DFO- PRE PRESSURE CONTROL PANEL | Generator Electrical Building | PS5-71-BI-0005 | DFO- prepressure module control junction box-JB1 | Generator Building | 2026-06-29 00:00:00 | CPP-RFI-68-33/1-05-0387 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
1464 | Electrical | PS5-71-BI-0006 -CL01 | PS5-71-IN-0003 | DFO- PRE PRESSURE CONTROL PANEL | Generator Electrical Building | PS5-71-BI-0006 | DFO- prepressure module control junction box-JB2 | Generator Building | 24-June-2026 | CPP-RFI-68-33/1-05-0377 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
1465 | Electrical | PS5-71-DM- 3100A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-DM- 3100A | Diesel Fuel Supply Pump A | Diesel Fuel Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-16 00:00:00 | 2026-09-16 00:00:00
1466 | Electrical | PS5-71-DM- 3100B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-DM- 3100B | Diesel Fuel Supply Pump B | Diesel Fuel Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-16 00:00:00 | 2026-09-16 00:00:00
1467 | Electrical | PS5-71-DM- 3200-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-DM- 3200 | Diesel Fuel Make-Up Pump | Diesel Fuel Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-16 00:00:00 | 2026-09-16 00:00:00
1468 | Electrical | PS5-71-DM- 3300A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-DM- 3300A | Crude Fuel Oil Transfer Pump A | CFO Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1469 | Electrical | PS5-71-DM- 3300B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-DM- 3300B | Crude Fuel Oil Transfer Pump B | CFO Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1470 | Electrical | PS5-71-DM- 3400A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-DM- 3400A | Crude Fuel Oil Service Pump A | CFO Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1471 | Electrical | PS5-71-DM- 3400B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-DM- 3400B | Crude Fuel Oil Service Pump B | CFO Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1472 | Electrical | PS5-71-DM- 3500A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-DM- 3500A | Diesel Transfer Pump A | Diesel Day Fuel Day Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1473 | Electrical | PS5-71-DM- 3500B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-DM- 3500B | Diesel Transfer Pump B | Diesel Day Fuel Day Drum Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1474 | Electrical | PS5-71-FCV- 0018-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-71-FCV- 0018 | Flow Control Valve | CFO STORAGE TANK AREA | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1475 | Electrical | PS5-71-FCV- 0019-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-71-FCV- 0019 | Flow Control Valve | DIESEL FUEL DAY DRUM | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1476 | Electrical | PS5-71-FCV- 0020-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-71-FCV- 0020 | Flow Control Valve | CFO STORAGE TANK AREA | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1477 | Electrical | PS5-71-FIT- 0011A-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-71-FIT- 0011A | Coriolis Flow Ind Transmitter | CFO STORAGE TANK AREA | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1478 | Electrical | PS5-71-FIT- 0011B-CL01 | PS5-06-IG-0002 | AC UPS Distribution Board (C) Single supply loads- 230VAC, 50Hz, 80A, 25KA/1s | EITS Building | PS5-71-FIT- 0011B | Coriolis Flow Ind Transmitter | CFO STORAGE TANK AREA | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1479 | Electrical | PS5-71-HE- 2200-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-HE-2200 | Crude Fuel Oil Service Tank Heater | CFO Service tank area | 30-April-20206 | CPP-RFI-68-331-05-0239 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1480 | Electrical | PS5-71-HE- 2200-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-HE-2200 | Crude Fuel Oil Service Tank Heater | CFO Service tank area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1481 | Electrical | PS5-71-HE- 2200-CL02 | PS5-61-IG-0006 | Outdoor Normal L&SP DB - Field (South Side) | Export pump area | PS5-71-HE-2200 | Crude Fuel Oil Service Tank Heater | CFO Service tank area | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1482 | Electrical | PS5-71-HE- 2300-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-HE-2300 | Crude Fuel Oil Storage Tank Heater | CFO Stroage tank area | 2026-04-25 00:00:00 | CPP-RFI-68-33/1-05-0223 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1483 | Electrical | PS5-71-HE- 2300-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-HE-2300 | Crude Fuel Oil Storage Tank Heater | CFO Stroage tank area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1484 | Electrical | PS5-71-HE- 2300-CL02 | PS5-61-IG-0006 | Outdoor Normal L&SP DB - Field (South Side) | Export pump area | PS5-71-HE-2300 | Crude Fuel Oil Storage Tank Heater | CFO Stroage tank area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1485 | Electrical | PS5-71-HE- 2400A-CL01 | PS5-71-IE-0001 | Crude Fuel Oil Storage Tank Feed Heater Control Panel 1 | EITS Building | PS5-71-HE- 2400A | Crude Fuel Oil Storage Tank Feed Heater | CFO Stroage tank area | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1486 | Electrical | PS5-71-HE- 2400A-CL02 | PS5-71-IE-0001 | Crude Fuel Oil Storage Tank Feed Heater Control Panel 1 | EITS Building | PS5-71-HE- 2400A | Crude Fuel Oil Storage Tank Feed Heater | CFO Stroage tank area | 2026-04-24 00:00:00 | CPP-RFI-68-331-05-0225 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1487 | Electrical | PS5-71-HE- 2400A-CL03 | PS5-71-IE-0001 | Crude Fuel Oil Storage Tank Feed Heater Control Panel 1 | EITS Building | PS5-71-HE- 2400A | Crude Fuel Oil Storage Tank Feed Heater | CFO Stroage tank area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1488 | Electrical | PS5-71-HE- 2400A-CL04 | PS5-71-IE-0001 | Crude Fuel Oil Storage Tank Feed Heater Control Panel 1 | EITS Building | PS5-71-HE- 2400A | Crude Fuel Oil Storage Tank Feed Heater | CFO Stroage tank area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1489 | Electrical | PS5-71-HE- 2400B-CL01 | PS5-71-IE-0002 | Crude Fuel Oil Storage Tank Feed Heater Control Panel 2 | EITS Building | PS5-71-HE- 2400B | Crude Fuel Oil Storage Tank Feed Heater | CFO Stroage tank area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1490 | Electrical | PS5-71-HE- 2400B-CL02 | PS5-71-IE-0002 | Crude Fuel Oil Storage Tank Feed Heater Control Panel 2 | EITS Building | PS5-71-HE- 2400B | Crude Fuel Oil Storage Tank Feed Heater | CFO Stroage tank area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1491 | Electrical | PS5-71-HE- 2400B-CL03 | PS5-71-IE-0002 | Crude Fuel Oil Storage Tank Feed Heater Control Panel 2 | EITS Building | PS5-71-HE- 2400B | Crude Fuel Oil Storage Tank Feed Heater | CFO Stroage tank area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1492 | Electrical | PS5-71-HE- 2400B-CL04 | PS5-71-IE-0002 | Crude Fuel Oil Storage Tank Feed Heater Control Panel 2 | EITS Building | PS5-71-HE- 2400B | Crude Fuel Oil Storage Tank Feed Heater | CFO Stroage tank area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1493 | Electrical | PS5-71-IE-0001- CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IE-0001 | Crude Fuel Oil Storage Tank Feed Heater Control Panel 1 | EITS Building
1494 | Electrical | PS5-71-IE-0002- CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IE-0002 | Crude Fuel Oil Storage Tank Feed Heater Control Panel 2 | EITS Building
1495 | Electrical | PS5-71-IES- 3100A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IES- 3100A | Diesel Fuel Supply Pump A-LCS | Diesel Fuel Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-16 00:00:00 | 2026-09-16 00:00:00
1496 | Electrical | PS5-71-IES- 3100B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IES- 3100B | Diesel Fuel Supply Pump B-LCS | Diesel Fuel Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-16 00:00:00 | 2026-09-16 00:00:00
1497 | Electrical | PS5-71-IES- 3200-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IES-3200 | Diesel Fuel Make-Up Pump-LCS | Diesel Fuel Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-16 00:00:00 | 2026-09-16 00:00:00
1498 | Electrical | PS5-71-IES- 3300A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IES- 3300A | Crude Fuel Oil Transfer Pump A-LCS | CFO Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1499 | Electrical | PS5-71-IES- 3300B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IES- 3300B | Crude Fuel Oil Transfer Pump B-LCS | CFO Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1500 | Electrical | PS5-71-IES- 3400A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IES- 3400A | Crude Fuel Oil Service Pump A-LCS | CFO Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1501 | Electrical | PS5-71-IES- 3400B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IES- 3400B | Crude Fuel Oil Service Pump B-LCS | CFO Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1502 | Electrical | PS5-71-IES- 3500A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IES- 3500A | Diesel Transfer Pump A- LCS | Diesel fuel day drum area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1503 | Electrical | PS5-71-IES- 3500B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-71-IES- 3500B | Diesel Transfer Pump B- LCS | Diesel fuel day drum area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1504 | Electrical | PS5-71-IN-0001 -CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-71-IN-0001 | DFO- SEPARATOR CONTROL PANEL | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1505 | Electrical | PS5-71-IN-0001 -CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-71-IN-0001 | DFO- SEPARATOR CONTROL PANEL | Generator Electrical Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1506 | Electrical | PS5-71-IN-0001 -CL03 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-71-IN-0001 | DFO- SEPARATOR CONTROL PANEL | Generator Electrical Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1507 | Electrical | PS5-71-IN-0002 -CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1508 | Electrical | PS5-71-IN-0002 -CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1509 | Electrical | PS5-71-IN-0002 -CL03 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-71-IN-0002 | CRO-PRE PRESSURECONTROL PANEL | Generator Electrical Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1510 | Electrical | PS5-71-IN-0003 -CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-71-IN-0003 | DFO- PRE PRESSURE CONTROL PANEL | Generator Electrical Building |  |  | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
1511 | Electrical | PS5-71-IN-0003 -CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-71-IN-0003 | DFO- PRE PRESSURE CONTROL PANEL | Generator Electrical Building |  |  | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
1512 | Electrical | PS5-71-IN-0003 -CL03 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-71-IN-0003 | DFO- PRE PRESSURE CONTROL PANEL | Generator Electrical Building | 2026-06-04 00:00:00 | CPP-RFI-68-33/1-05-0309 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
1513 | Electrical | PS5-71-IN- 0004A-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-71-IN- 0004A | CRO- SEPARATOR CONTROL PANEL-1 | Generator Electrical Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1514 | Electrical | PS5-71-IN- 0004A-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-71-IN- 0004A | CRO- SEPARATOR CONTROL PANEL-1 | Generator Electrical Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1515 | Electrical | PS5-71-IN- 0004A-CL03 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-71-IN- 0004A | CRO- SEPARATOR CONTROL PANEL-1 | Generator Electrical Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1516 | Electrical | PS5-71-IN- 0004B-CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-71-IN- 0004B | CRO- SEPARATOR CONTROL PANEL-2 | Generator Electrical Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1517 | Electrical | PS5-71-IN- 0004B-CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-71-IN- 0004B | CRO- SEPARATOR CONTROL PANEL-2 | Generator Electrical Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1518 | Electrical | PS5-71-IN- 0004B-CL03 | PS5-60-IH-0002 | GENERATOR COMMON MCC - Generator Elect. Building | Generator Electrical Building | PS5-71-IN- 0004B | CRO- SEPARATOR CONTROL PANEL-2 | Generator Electrical Building | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1519 | Electrical | PS5-71-LCV- 4101-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-71-LCV- 4101 | LCV - CFO STORAGE TANK AREA | Field_CFO STORAGE TANK AREA | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1520 | Electrical | PS5-71-MOV- 0001-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-71-MOV- 0001 | Motor Operated Valve | Power generator building area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1521 | Electrical | PS5-71-MOV- 0002-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-71-MOV- 0002 | Motor Operated Valve | Power generator building area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
1522 | Electrical | PS5-71-MOV- 0003-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-71-MOV- 0003 | Motor Operated Valve | Power generator building area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1523 | Electrical | PS5-71-MOV- 0004-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-71-MOV- 0004 | Motor Operated Valve | Power generator building area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
1524 | Electrical | PS5-71-MOV- 0007-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-71-MOV- 0007 | Motor Operated Valve | Power generator building area | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1525 | Electrical | PS5-71-MOV- 0008-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-71-MOV- 0008 | Motor Operated Valve | Power generator building area | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1526 | Electrical | PS5-71-MOV- 0009-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-71-MOV- 0009 | Motor Operated Valve | Power generator building area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1527 | Electrical | PS5-71-MOV- 0010-CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-71-MOV- 0010 | Motor Operated Valve | Power generator building area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1528 | Electrical | PS5-71-SDV- 0001-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-71-SDV- 0001 | Shutdown Valve | DIESEL FUEL DAY DRUM | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1529 | Electrical | PS5-71-SDV- 0022-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-71-SDV- 0022 | Shutdown Valve | CFO STORAGE TANK AREA |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1530 | Electrical | PS5-71-SDV- 0029-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-71-SDV- 0029 | Shutdown Valve | DIESEL FUEL STORAGE AREA | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-16 00:00:00 | 2026-09-16 00:00:00
1531 | Electrical | PS5-71-SDV- 0039-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-71-SDV- 0039 | Shutdown Valve | CFO STORAGE TANK AREA | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1532 | Electrical | PS5-71-UZ- 6200-CL01 | PS5-61-IG-0014 | Outdoor Power DB - Field(North) | Near EITS | PS5-71-UZ-6200 | Diesel Fuel Dispenser Station | Diesel Fuel Dispenser Station | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-16 00:00:00 | 2026-09-16 00:00:00
1533 | Electrical | PS5-71-XV-0089 -CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-71-XV-0089 | On / Off Valve | CFO STORAGE TANKS AREA | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1534 | Electrical | PS5-71-XV-0090 -CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-71-XV-0090 | On / Off Valve | CFO STORAGE TANKS AREA | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1535 | Electrical | PS5-71-XV-0091 -CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-71-XV-0091 | On / Off Valve | Power generator building area |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1536 | Electrical | PS5-71-XV-0092 -CL01 | PS5-61-IG-0042 | MOV DB - Field | Near Export pump area | PS5-71-XV-0092 | On / Off Valve | DIESEL FUEL DAY DRUM ARE | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1537 | Electrical | PS5-74-IG-5101 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-74-IG-5101 | Nitrogen Generation Skid Power Distribution Panel | Nitrogen Generation Skid | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
1538 | Electrical | PS5-74-LB-5101 -CL01 | PS5-06-IG- 0004A | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-74-LB-5101 | Nitrogen Generation Skid - Unit Control Panel | Nitrogen Generation Skid | 2026-05-10 00:00:00 | CPP-RFI-68-331-05-0260 | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
1539 | Electrical | PS5-74-LB-5101 -CL02 | PS5-06-IG- 0004B | AC UPS DB - Generator Electrical Bldng | Generator Electrical Building | PS5-74-LB-5101 | Nitrogen Generation Skid - Unit Control Panel | Nitrogen Generation Skid | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
1540 | Electrical | PS5-75-DM- 3100A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-75-DM- 3100A | Corrosion inhbitor Pump A | Near DRA injection package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1541 | Electrical | PS5-75-DM- 3100B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-75-DM- 3100B | Corrosion inhibitor Pump B | Near DRA injection package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1542 | Electrical | PS5-75-DM- 3200A-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-75-DM- 3200A | Biocide injection Pump A | Near DRA injection package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1543 | Electrical | PS5-75-DM- 3200B-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-75-DM- 3200B | Biocide injection Pump B | Near DRA injection package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1544 | Electrical | PS5-75-IES- 3100A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-75-IES- 3100A | Corrosion inhbitor Pump A-LCS | Near DRA injection package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1545 | Electrical | PS5-75-IES- 3100B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-75-IES- 3100B | Corrosion inhibitor Pump B-LCS | Near DRA injection package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1546 | Electrical | PS5-75-IES- 3200A-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-75-IES- 3200A | Biocide injection Pump A -LCS | Near DRA injection package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1547 | Electrical | PS5-75-IES- 3200B-CD01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-75-IES- 3200B | Biocide injection Pump B -LCS | Near DRA injection package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1548 | Electrical | PS5-75-ISO- 0001-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-75-ISO- 0001 | Power socket-DRA Injection package MCC | Field_DRA injection package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1549 | Electrical | PS5-75-ISO- 0002-CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-75-ISO- 0002 | Power socket-DRA Injection Pkg portable recirculation pump | Field_DRA injection package | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1550 | Electrical | PS5-75-MOV- 0001-CL01 | PS5-61-IG-0043 | MOV DB - Field | Near Export pump area | PS5-75-MOV- 0001 | Motorized Operated Valve - DRA Injection Package | DRA Injection Package | 2026-06-03 00:00:00 | CPP-RFI-68-331-05-0312 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1551 | Electrical | PS5-78-JC- 9100A-CL01 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-78-JC- 9100A | 10 OHT Crane - Generator Building | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1552 | Electrical | PS5-78-JC- 9100B-CL01 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-78-JC- 9100B | 10 OHT Crane - Generator Building | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1553 | Electrical | PS5-78-JC- 9100C-CL01 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-78-JC- 9100C | 10 OHT Crane - Generator Building | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1554 | Electrical | PS5-78-JC- 9100D-CL01 | PS5-61-IK-0006 | 0.4kV Switchboard | Gen Electrical Building | PS5-78-JC- 9100D | 10 OHT Crane - Generator Building | Generator Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1555 | Electrical | PS5-79-BH- 0001-CH01 | PS5-61-IJ-0010 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | PS5-79-BH-0001 | LLHT High Voltage Power Junction Box_North | Near export pump area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1556 | Electrical | PS5-79-BH- 0001-CH02 | PS5-61-IJ-0010 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | PS5-79-BH-0001 | LLHT High Voltage Power Junction Box_North | Near export pump area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1557 | Electrical | PS5-79-BH- 0001-CH03 | PS5-61-IJ-0010 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | PS5-79-BH-0001 | LLHT High Voltage Power Junction Box_North | Near export pump area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1558 | Electrical | PS5-79-BH- 0002-CH01 | PS5-61-IJ-0011 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | PS5-79-BH-0002 | LLHT High Voltage Power Junction Box_South | Near export pump area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1559 | Electrical | PS5-79-BH- 0002-CH02 | PS5-61-IJ-0011 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | PS5-79-BH-0002 | LLHT High Voltage Power Junction Box_South | Near export pump area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1560 | Electrical | PS5-79-BH- 0002-CH03 | PS5-61-IJ-0011 | SM6 LLHT 7.2 kV MV Switchgear, 630A, 16kA/3s | EITS Building | PS5-79-BH-0002 | LLHT High Voltage Power Junction Box_South | Near export pump area | 2026-05-05 00:00:00 | CPP-RFI-68-331-05-0244 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1561 | Electrical | PS5-79-IV-0001 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0001 | Electrical Heat Tracing Transformer 1 - 63KVA 400/400V | Near CFO Service Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1562 | Electrical | PS5-79-IV-0002 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0002 | Electrical Heat Tracing Transformer 2 - 100KVA 400/400V | Near CFO Service Pump area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1563 | Electrical | PS5-79-IV-0003 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0003 | Electrical Heat Tracing Transformer 3 - 63KVA 400/400V | Near Diesel Fuel Day Tank Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1564 | Electrical | PS5-79-IV-0004 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0004 | Electrical Heat Tracing Transformer 4 - 63KVA 400/400V | Near Diesel Fuel Day Tank Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1565 | Electrical | PS5-79-IV-0005 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0005 | Electrical Heat Tracing Transformer 5 - 100KVA 400/400V | Near Diesel Fuel Day Tank Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1566 | Electrical | PS5-79-IV-0006 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0006 | Electrical Heat Tracing Transformer 6 - 63KVA 400/400V | Near Export Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1567 | Electrical | PS5-79-IV-0007 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0007 | Electrical Heat Tracing Transformer 7 - 100KVA 400/400V | Near Export Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1568 | Electrical | PS5-79-IV-0008 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0008 | Electrical Heat Tracing Transformer 8 - 100KVA 400/400V | Near Export Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1569 | Electrical | PS5-79-IV-0009 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0009 | Electrical Heat Tracing Transformer 9 - 100KVA 400/400V | Near Export Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1570 | Electrical | PS5-79-IV-0010 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0010 | Electrical Heat Tracing Transformer 10 - 100KVA 400/400V | Near Export Pump Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1571 | Electrical | PS5-79-IV-0011 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0011 | Electrical Heat Tracing Transformer 11 - 100KVA 400/400V | Power generator building area | 2026-05-24 00:00:00 | CPP-RFI-68-331-05-0295 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1572 | Electrical | PS5-79-IV-0012 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-79-IV-0012 | Electrical Heat Tracing Transformer 12 - 100KVA 400/400V | Power generator building area | 2026-05-01 00:00:00 | CPP-RFI-68-331-05-0240 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1573 | Electrical | PS5-82-IN-0001 -CL01 | PS5-61-IK-0001 | 0.4kV Switchboard | EITS Building | PS5-82-IN-0001 | MCC for Sewage Treatment Package | Sewage Treatment Pkge -North w | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-30 00:00:00 | 2026-09-30 00:00:00
1574 | Electrical | PS5-87-IRF- 0001-CL01 | PS5-61-IG-0007 | Outdoor Normal Lighting DB - Field - (North Side) | Near EDG package | PS5-87-IRF-0001 | Transformer Rectifier Unit 1-for tank (PS5-53- TR-4100) | Fire water storage Tank area | 2026-05-13 00:00:00 | CPP-RFI-68-331-05-0266 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1575 | Electrical | PS5-87-IRF- 0002-CL01 | PS5-61-IG-0006 | Outdoor Normal L&SP DB - Field (South Side) | Export pump area | PS5-87-IRF-0002 | Transformer rectifier unit 2-for tank (PS5-71-TR- 4100) | CFO Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1576 | Electrical | PS5-87-IRF- 0003-CL01 | PS5-61-IG-0006 | Outdoor Normal L&SP DB - Field (South Side) | Export pump area | PS5-87-IRF-0003 | Transformer rectifier unit 3-for tank (PS5-71-TR- 4200) | CFO Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1577 | Electrical | PS5-87-IRF- 0004-CL01 | PS5-61-IG-0007 | Outdoor Normal Lighting DB - Field - (North Side) | Near EDG package | PS5-87-IRF-0004 | Transformer rectifier unit 4-for tank ( PS5-71-TR- 4400) | Diesel fuel tank Area | 2026-04-17 00:00:00 | CPP-RFI-68-33/1-05-0211 | 2026-09-16 00:00:00 | 2026-09-16 00:00:00
1578 | Instrument | PS5-74-LB-5101-CC01 | PS5-74-LB-5101 |  | Package Skid | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1579 | Instrument | PS5-74-LB-5101-CC02 | PS5-74-LB-5101 |  | Package Skid | PS5-04-PMC-0006 |  | 33kV EITS Building
1580 | Instrument | PS5-74-LB-5101-CJ01 | PS5-74-LB-5101 |  | Package Skid | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1581 | Instrument | PS5-01-BI-0001-CC01 | PS5-01-BI-0001 |  | Package Skid | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1582 | Instrument | PS5-01-BI-0002-CC01 | PS5-01-BI-0002 |  | Package Skid | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1583 | Instrument | PS5-01-BI-0003-CC01 | PS5-01-BI-0003 |  | Package Skid | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1584 | Instrument | PS5-01-BI-0004-CC01 | PS5-01-BI-0004 |  | Package Skid | PS5-03-SFMC-0012 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1585 | Instrument | PS5-01-BI-0005-CC01 | PS5-01-BI-0005 |  | Package Skid | PS5-03-SFMC-0012 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1586 | Instrument | PS5-01-BI-0006-CC01 | PS5-01-BI-0006 |  | Package Skid | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1587 | Instrument | PS5-01-BI-1117-CC01 | PS5-01-FIT-0003A | Instr:PS5-01-BI-1117, InstrLoc:Field, Branch:PS5-01-FIT-0003A-CJ01, Sz:1P X 1.0 OS FL RTD, L:65m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035 | 2026-06-25 00:00:00 | 2026-06-25 00:00:00
1588 | Instrument | PS5-01-BI-1118-CC01 | PS5-01-FCV-0003A | Instr:PS5-01-BI-1118, InstrLoc:Field, Branch:PS5-01-FY-0003A-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041 | 2026-06-25 00:00:00 | 2026-06-25 00:00:00
1589 | Instrument | PS5-01-BI-1501-CC01 | PS5-01-PIT-0010 | Instr:PS5-01-BI-1501, InstrLoc:Field, Branch:PS5-01-PIT-0010-CJ01, Sz:1P X 1.0 OS FR, L:115m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
1590 | Instrument | PS5-01-BI-1515-CC01 | PS5-01-PDIT-0011A | Instr:PS5-01-BI-1515, InstrLoc:Field, Branch:PS5-01-PDIT-0011A-CJ01, Sz:1P X 1.0 OS FR, L:50m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035 | 2026-06-25 00:00:00 | 2026-06-25 00:00:00
1591 | Instrument | PS5-01-BI-1520-CC01 | PS5-01-PIT-8101A | Instr:PS5-01-BI-1520, InstrLoc:Field, Branch:PS5-01-PIT-8101A-CJ01, Sz:1P X 1.0 OS FR, L:55m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1592 | Instrument | PS5-01-BI-1571-CC01 | PS5-01-BI-1571 |  | Package Skid | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1593 | Instrument | PS5-01-BI-2110-CC01 | PS5-01-FCV-0003A | Instr:PS5-01-BI-2110, InstrLoc:Field, Branch:PS5-01-FXS-0003A-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035 | 2026-06-25 00:00:00 | 2026-06-25 00:00:00
1594 | Instrument | PS5-01-BI-2520-CC01 | PS5-01-SY-8101A | Instr:PS5-01-BI-2520, InstrLoc:Field, Branch:PS5-01-SY-8101A-CJ01, Sz:1P X 2.5 OS FR, L:55m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0012 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1595 | Instrument | PS5-01-BI-2571A-CC01 | PS5-01-BI-2571A |  | Package Skid | PS5-03-SFMC-0012 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1596 | Instrument | PS5-01-BI-2571B-CC01 | PS5-01-BI-2571B |  | Package Skid | PS5-03-SFMC-0012 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1597 | Instrument | PS5-01-IE-0002A-CC01 | PS5-01-IE-0002A |  | Package Skid | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1598 | Instrument | PS5-01-IE-0002A-CC02 | PS5-01-IE-0002A |  | Package Skid | PS5-03-SFMC-0013 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1599 | Instrument | PS5-01-IE-0002B-CC01 | PS5-01-IE-0002B |  | Package Skid | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1600 | Instrument | PS5-01-IE-0002B-CC02 | PS5-01-IE-0002B |  | Package Skid | PS5-03-SFMC-0013 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-09-11 00:00:00 | 2026-09-11 00:00:00
1601 | Instrument | PS5-01-IE-0009A-CC01 | PS5-01-IE-0009A |  | Package Skid | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
1602 | Instrument | PS5-01-IE-0009A-CC02 | PS5-01-IE-0009A |  | Package Skid | PS5-03-SFMC-0012 |  | 33kV EITS Building |  |  | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
1603 | Instrument | PS5-01-IE-0009B-CC01 | PS5-01-IE-0009B |  | Package Skid | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
1604 | Instrument | PS5-01-IE-0009B-CC02 | PS5-01-IE-0009B |  | Package Skid | PS5-03-SFMC-0012 |  | 33kV EITS Building |  |  | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
1605 | Instrument | PS5-01-LB-0004-CC01 | PS5-01-LB-0004 |  | UCP | PS5-03-SFMC-0011 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1606 | Instrument | PS5-01-LB-0004-CC02 | PS5-01-LB-0004 |  | UCP | PS5-03-SFMC-0012 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1607 | Instrument | PS5-01-LB-0004-CC03 | PS5-01-LB-0004 |  | UCP | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1608 | Instrument | PS5-01-LIT-4201-CJ01 | PS5-01-LIT-4201 |  | Package Skid | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1609 | Instrument | PS5-01-PIT-0014-CJ01 | PS5-01-PIT-0014 |  | Field | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
1610 | Instrument | PS5-01-PIT-0015-CJ01 | PS5-01-PIT-0015 |  | Field | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
1611 | Instrument | PS5-01-PIT-0016-CJ01 | PS5-01-PIT-0016 |  | Field | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
1612 | Instrument | PS5-01-PIT-0017-CJ01 | PS5-01-PIT-0017 |  | Field | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-09-14 00:00:00 | 2026-09-14 00:00:00
1613 | Instrument | PS5-03-BI-1502-CC01 | PS5-03-RDIR-0405 | Instr:PS5-03-BI-1502, InstrLoc:Field, Branch:PS5-03-RDIR-0405-CJ01, Sz:1T X 1.5 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1614 | Instrument | PS5-03-BI-1503-CC01 | PS5-03-RDIR-0403 | Instr:PS5-03-BI-1503, InstrLoc:Field, Branch:PS5-03-RDIR-0403-CJ01, Sz:1T X 1.5 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1615 | Instrument | PS5-03-BI-1506-CC01 | PS5-03-RDIR-0122 | Instr:PS5-03-BI-1506, InstrLoc:Field, Branch:PS5-03-RDIR-0122-CJ01, Sz:1T X 1.5 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
1616 | Instrument | PS5-03-BI-1507-CC01 | PS5-03-RDIR-0104 | Instr:PS5-03-BI-1507, InstrLoc:Field, Branch:PS5-03-RDIR-0104-CJ01, Sz:1T X 1.5 OS FR, L:80m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
1617 | Instrument | PS5-03-BI-1508-CC01 | PS5-03-RDIR-0108 | Instr:PS5-03-BI-1508, InstrLoc:Field, Branch:PS5-03-RDIR-0108-CJ01, Sz:1T X 1.5 OS FR, L:60m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
1618 | Instrument | PS5-03-BI-1509-CC01 | PS5-03-RDIR-0114 | Instr:PS5-03-BI-1509, InstrLoc:Field, Branch:PS5-03-RDIR-0114-CJ01, Sz:1T X 1.5 OS FR, L:80m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036/ CPP-RFI-68-64-11-0067 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
1619 | Instrument | PS5-03-BI-1510-CC01 | PS5-03-RDIR-0819 | Instr:PS5-03-BI-1510, InstrLoc:Field, Branch:PS5-03-RDIR-0819-CJ01, Sz:1T X 1.5 OS FR, L:60m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1620 | Instrument | PS5-03-BI-1511-CC01 | PS5-03-RDUIR-0701 | Instr:PS5-03-BI-1511, InstrLoc:Building, Branch:PS5-03-RDUIR-0701-CJ01, Sz:1T X 1.5 OS FR, L:55m, GlandS:M20, GlandD:M20 | Bldg | PS5-03-SFMC-0007 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1621 | Instrument | PS5-03-BI-1512-CC01 | PS5-03-RDUIR-0907 | Instr:PS5-03-BI-1512, InstrLoc:Building, Branch:PS5-03-RDUIR-0907-CJ01, Sz:1T X 1.5 OS FR, L:40m, GlandS:M20, GlandD:M20 | Bldg | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1622 | Instrument | PS5-03-BI-1513-CC01 | PS5-03-RDUIR-1007 | Instr:PS5-03-BI-1513, InstrLoc:Building, Branch:PS5-03-RDUIR-1007-CJ01, Sz:1T X 1.5 OS FR, L:40m, GlandS:M20, GlandD:M20 | Bldg | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1623 | Instrument | PS5-03-BI-1514-CC01 | PS5-03-RDUIR-1107 | Instr:PS5-03-BI-1514, InstrLoc:Building, Branch:PS5-03-RDUIR-1107-CJ01, Sz:1T X 1.5 OS FR, L:40m, GlandS:M20, GlandD:M20 | Bldg | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1624 | Instrument | PS5-03-BI-1516-CC01 | PS5-03-RDUIR-1208 | Instr:PS5-03-BI-1516, InstrLoc:Building, Branch:PS5-03-RDUIR-1208-CJ01, Sz:1T X 1.5 OS FR, L:60m, GlandS:M20, GlandD:M20 | Bldg | PS5-03-SFMC-0008 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1625 | Instrument | PS5-03-BI-2501-CC01 | PS5-03-RDH-0614 | Instr:PS5-03-BI-2501, InstrLoc:Field, Branch:PS5-03-RDH-0614-CJ01, Sz:1P X 1.0 OS FR, L:50m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1626 | Instrument | PS5-03-BI-2502-CC01 | PS5-03-RDH-0601 | Instr:PS5-03-BI-2502, InstrLoc:Field, Branch:PS5-03-RDH-0601-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1627 | Instrument | PS5-03-BI-2503-CC01 | PS5-03-RDH-0607 | Instr:PS5-03-BI-2503, InstrLoc:Field, Branch:PS5-03-RDH-0607-CJ01, Sz:1P X 1.0 OS FR, L:55m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-06-25 00:00:00 | 2026-06-25 00:00:00
1628 | Instrument | PS5-03-BI-2504-CC01 | PS5-03-RMAC-0101 | Instr:PS5-03-BI-2504, InstrLoc:Field, Branch:PS5-03-RMAC-0101-CJ01, Sz:1P X 1.0 OS FR, L:80m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
1629 | Instrument | PS5-03-BI-2505-CC01 | PS5-03-RDH-0828 | Instr:PS5-03-BI-2505, InstrLoc:Field, Branch:PS5-03-RDH-0828-CJ01, Sz:1P X 1.0 OS FR, L:150m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1630 | Instrument | PS5-03-BI-2506-CC01 | PS5-03-RDH-0901 | Instr:PS5-03-BI-2506, InstrLoc:Building, Branch:PS5-03-RDH-0901-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Bldg | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-06-25 00:00:00 | 2026-06-25 00:00:00
1631 | Instrument | PS5-03-BI-2507-CC01 | PS5-03-RDH-1001 | Instr:PS5-03-BI-2507, InstrLoc:Building, Branch:PS5-03-RDH-1001-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Bldg | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1632 | Instrument | PS5-03-BI-2508-CC01 | PS5-03-RDH-1101 | Instr:PS5-03-BI-2508, InstrLoc:Building, Branch:PS5-03-RDH-1101-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Bldg | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1633 | Instrument | PS5-03-BI-2509-CC01 | PS5-03-RMAC-0401 | Instr:PS5-03-BI-2509, InstrLoc:Field, Branch:PS5-03-RMAC-0401-CJ01, Sz:1P X 1.0 OS FR, L:142m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035 | 2026-06-25 00:00:00 | 2026-06-25 00:00:00
1634 | Instrument | PS5-03-BI-2510-CC01 | PS5-03-RDH-0302 | Instr:PS5-03-BI-2510, InstrLoc:Field, Branch:PS5-03-RDH-0302-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0010 |  | 33kV EITS Building |  |  | 2026-09-25 00:00:00 | 2026-09-25 00:00:00
1635 | Instrument | PS5-03-BI-2511-CC01 | PS5-03-GDLHP-0137 | Instr:PS5-03-BI-2511, InstrLoc:Field, Branch:PS5-03-GDLHP-0137-CJ01, Sz:1P X 1.0 OS FR, L:55m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035/ CPP-RFI-68-64-11-0067 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
1636 | Instrument | PS5-03-BI-2512-CC01 | PS5-03-GDLHP-0401 | Instr:PS5-03-BI-2512, InstrLoc:Field, Branch:PS5-03-GDLHP-0401-CJ01, Sz:1P X 1.0 OS FR, L:45m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1637 | Instrument | PS5-03-BI-2514-CC01 | PS5-03-RDH-1201 | Instr:PS5-03-BI-2514, InstrLoc:Building, Branch:PS5-03-RDH-1201-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Bldg | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-06-25 00:00:00 | 2026-06-25 00:00:00
1638 | Instrument | PS5-03-BI-2515-CC01 | PS5-03-RDH-1302 | Instr:PS5-03-BI-2515, InstrLoc:Building, Branch:PS5-03-RDH-1302-CJ01, Sz:1P X 1.0 OS FR, L:55m, GlandS:M20, GlandD:M20 | Bldg | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035 | 2026-06-25 00:00:00 | 2026-06-25 00:00:00
1639 | Instrument | PS5-03-HS-7002-CJ01 | PS5-03-HS-7002 |  | Field | PS5-03-SFMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038 | 2026-09-25 00:00:00 | 2026-09-25 00:00:00
1640 | Instrument | PS5-03-NMR-0801-CJ01 | PS5-03-NMR-0801 |  | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1641 | Instrument | PS5-03-NMR-0802-CJ01 | PS5-03-NMR-0802 |  | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1642 | Instrument | PS5-03-NMR-0803-CJ01 | PS5-03-NMR-0803 |  | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1643 | Instrument | PS5-03-NMR-0804-CJ01 | PS5-03-NMR-0804 |  | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1644 | Instrument | PS5-03-RMAC-0120-CJ01 | PS5-03-RMAC-0120 |  | Field | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038 | 2026-08-25 00:00:00 | 2026-08-25 00:00:00
1645 | Instrument | PS5-03-RMAC-0824-CJ01 | PS5-03-RMAC-0824 |  | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1646 | Instrument | PS5-03-SEA-0002-CC01 | PS5-03-SEA-0002 |  | Guard House Bldg FACP | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043 | 2026-09-25 00:00:00 | 2026-09-25 00:00:00
1647 | Instrument | PS5-03-SEA-0002-CJ01 | PS5-03-SEA-0002 |  | Guard House Bldg FACP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037 | 2026-09-25 00:00:00 | 2026-09-25 00:00:00
1648 | Instrument | PS5-03-SEA-0003-CC01 | PS5-03-SEA-0003 |  | Generator Control Bldg FACP | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
1649 | Instrument | PS5-03-SEA-0003-CJ01 | PS5-03-SEA-0003 |  | Generator Control Bldg FACP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
1650 | Instrument | PS5-03-SEA-0005-CC01 | PS5-03-SEA-0005 |  | Off Bldg FACP | PS5-03-SFMC-0010 |  | 33kV EITS Building |  |  | 2026-09-30 00:00:00 | 2026-09-30 00:00:00
1651 | Instrument | PS5-03-SEA-0005-CJ01 | PS5-03-SEA-0005 |  | Off Bldg FACP | PS5-04-PMC-0004 |  | 33kV EITS Building
1652 | Instrument | PS5-03-SEA-0006-CC01 | PS5-03-SEA-0006 |  | Warehouse Bldg FACP | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1653 | Instrument | PS5-03-SEA-0006-CJ01 | PS5-03-SEA-0006 |  | Warehouse Bldg FACP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1654 | Instrument | PS5-06-GU-0003A-CC01 | PS5-06-GU-0003A |  | Generator Control Bldg | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1655 | Instrument | PS5-06-GU-0003B-CC01 | PS5-06-GU-0003B |  | Generator Control Bldg | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1656 | Instrument | PS5-09-BI-2501-CC01 | PS5-09-BI-2501 |  | Warehouse Bldg | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1657 | Instrument | PS5-09-BI-2502-CC01 | PS5-09-BI-2502 |  | Off Bldg | PS5-03-SFMC-0011 |  | 33kV EITS Building
1658 | Instrument | PS5-09-BI-2504-CC01 | PS5-09-BI-2504 |  | Off Bldg | PS5-03-SFMC-0010 |  | 33kV EITS Building
1659 | Instrument | PS5-09-BI-2503-CC01 | PS5-09-BI-2503 |  | Generator Control Bldg | PS5-03-SFMC-0011 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049
1660 | Instrument | PS5-09-LB-0006-CC01 | PS5-09-LB-0006 |  | Off Bldg HCP | PS5-03-SFMC-0013 |  | 33kV EITS Building
1661 | Instrument | PS5-09-LB-0006-CC05 | PS5-09-LB-0006 |  | Off Bldg HCP | PS5-03-SFMC-0012 |  | 33kV EITS Building
1662 | Instrument | PS5-09-LB-0006-CC02 | PS5-09-LB-0006 |  | Off Bldg HCP | PS5-03-SFMC-0011 |  | 33kV EITS Building
1663 | Instrument | PS5-09-LB-0006-CC03 | PS5-09-LB-0006 |  | Off Bldg HCP | PS5-04-PMC-0003 |  | 33kV EITS Building
1664 | Instrument | PS5-09-LB-0006-CC04 | PS5-09-LB-0006 |  | Off Bldg HCP | PS5-03-SFMC-0011 |  | 33kV EITS Building
1665 | Instrument | PS5-09-LB-0007-CC01 | PS5-09-LB-0007 |  | Warehouse Bldg HCP | PS5-03-SFMC-0013 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1666 | Instrument | PS5-09-LB-0007-CC02 | PS5-09-LB-0007 |  | Warehouse Bldg HCP | PS5-03-SFMC-0011 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1667 | Instrument | PS5-09-LB-0007-CC03 | PS5-09-LB-0007 |  | Warehouse Bldg HCP | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1668 | Instrument | PS5-09-LB-0007-CC04 | PS5-09-LB-0007 |  | Warehouse Bldg HCP | PS5-03-SFMC-0011 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1669 | Instrument | PS5-09-LB-0008-CC01 | PS5-09-LB-0008 |  | Generator Control Bldg HCP | PS5-03-SFMC-0013 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1670 | Instrument | PS5-09-LB-0008-CC02 | PS5-09-LB-0008 |  | Generator Control Bldg HCP | PS5-03-SFMC-0011 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1671 | Instrument | PS5-09-LB-0008-CC03 | PS5-09-LB-0008 |  | Generator Control Bldg HCP | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049
1672 | Instrument | PS5-09-LB-0008-CC04 | PS5-09-LB-0008 |  | Generator Control Bldg HCP | PS5-03-SFMC-0011 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1673 | Instrument | PS5-09-LB-0008-CC05 | PS5-09-LB-0008 |  | Generator Control Bldg HCP | PS5-03-SFMC-0012 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1674 | Instrument | PS5-09-LB-0008-CC06 | PS5-09-LB-0008 |  | Generator Control Bldg HCP | PS5-03-SFMC-0012 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1675 | Instrument | PS5-09-LB-0008-CC07 | PS5-09-LB-0008 |  | Generator Control Bldg HCP | PS5-03-SFMC-0012 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1676 | Instrument | PS5-09-LB-0008-CC08 | PS5-09-LB-0008 |  | Generator Control Bldg HCP | PS5-03-SFMC-0011 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1677 | Instrument | PS5-25-BI-1101-CC01 | PS5-25-FIT-0001 | Instr:PS5-25-BI-1101, InstrLoc:Field, Branch:PS5-25-FIT-0001-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1678 | Instrument | PS5-25-BI-1102-CC01 | PS5-25-ZIT-0001 | Instr:PS5-25-BI-1102, InstrLoc:Field, Branch:PS5-25-ZIT-0001-CC01, Sz:2P X 1.0 OS FL RTD, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041
1679 | Instrument | PS5-25-BI-1103-CC01 | PS5-25-FIT-0003A | Instr:PS5-25-BI-1103, InstrLoc:Field, Branch:PS5-25-FIT-0003A-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1680 | Instrument | PS5-25-BI-1104-CC01 | PS5-25-FIT-0003C | Instr:PS5-25-BI-1104, InstrLoc:Field, Branch:PS5-25-FIT-0003C-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1681 | Instrument | PS5-25-BI-1115-CC01 | PS5-25-PIT-0013 | Instr:PS5-25-BI-1115, InstrLoc:Field, Branch:PS5-25-PIT-0013-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1682 | Instrument | PS5-25-BI-1201-CC01 | PS5-25-ESDV-0021 | Instr:PS5-25-BI-1201, InstrLoc:Field, Branch:PS5-25-ESDV-0021-CC01, Sz:2P X 1.0 OS FR, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-03-SFMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1683 | Instrument | PS5-25-BI-1301-CC01 | PS5-25-PIT-0008A | Instr:PS5-25-BI-1301, InstrLoc:Field, Branch:PS5-25-PIT-0008A-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1684 | Instrument | PS5-25-BI-1302-CC01 | PS5-25-TIT-0002A | Instr:PS5-25-BI-1302, InstrLoc:Field, Branch:PS5-25-TIT-0002A-CJ01, Sz:1P X 1.0 OS FR, L:65m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1685 | Instrument | PS5-25-BI-1310-CC01 | PS5-25-TIT-0002C | Instr:PS5-25-BI-1310, InstrLoc:Field, Branch:PS5-25-TIT-0002C-CJ01, Sz:1P X 1.0 OS FR, L:50m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0002 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1686 | Instrument | PS5-25-BI-2101-CC01 | PS5-25-MOV-0001 | Instr:PS5-25-BI-2101, InstrLoc:Field, Branch:PS5-25-MXS-0001-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1687 | Instrument | PS5-25-BI-2102-CC01 | PS5-25-MOV-0008 | Instr:PS5-25-BI-2102, InstrLoc:Field, Branch:PS5-25-MXS-0008-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1688 | Instrument | PS5-25-BI-2103-CC01 | PS5-25-MOV-0026 | Instr:PS5-25-BI-2103, InstrLoc:Field, Branch:PS5-25-MOV-0026-CC01, Sz:6P X 0.75 OS FL RTD, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041
1689 | Instrument | PS5-25-BI-2104-CC01 | PS5-25-XV-0053 | Instr:PS5-25-BI-2104, InstrLoc:Field, Branch:PS5-25-XV-0053-CC01, Sz:2P X 1.0 OS FL RTD, L:65m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1690 | Instrument | PS5-25-BI-2105-CC01 | PS5-25-XV-0053 | Instr:PS5-25-BI-2105, InstrLoc:Field, Branch:PS5-25-XXS-0053-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1691 | Instrument | PS5-25-BI-2106-CC01 | PS5-25-FCV-0003A | Instr:PS5-25-BI-2106, InstrLoc:Field, Branch:PS5-25-FXS-0003A-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1692 | Instrument | PS5-25-BI-2108-CC01 | PS5-25-SDV-0035C | Instr:PS5-25-BI-2108, InstrLoc:Field, Branch:PS5-25-SY-0035CB-CJ01, Sz:1P X 2.5 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1693 | Instrument | PS5-25-BI-2109-CC01 | PS5-25-SDV-0035A | Instr:PS5-25-BI-2109, InstrLoc:Field, Branch:PS5-25-SY-0035AB-CJ01, Sz:1P X 2.5 OS FL RTD, L:70m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041
1694 | Instrument | PS5-25-BI-2201-CC01 | PS5-25-ESDV-0021 | Instr:PS5-25-BI-2201, InstrLoc:Field, Branch:PS5-25-ESDV-0021-CC02, Sz:2P X 1.0 OS FR, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-03-SFMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1695 | Instrument | PS5-25-BI-2203-CC01 | PS5-25-ESDV-0021 | Instr:PS5-25-BI-2203, InstrLoc:Field, Branch:PS5-25-ESDV-0021-CC03, Sz:2P X 1.0 OS FR, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-03-SFMC-0001 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041
1696 | Instrument | PS5-25-BI-2205-CC01 | PS5-25-ESDV-0021 | Instr:PS5-25-BI-2205, InstrLoc:Field, Branch:PS5-25-ESY-0021A-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1697 | Instrument | PS5-25-BI-2301-CC01 | PS5-25-SDV-0035A | Instr:PS5-25-BI-2301, InstrLoc:Field, Branch:PS5-25-SXS-0035A-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1698 | Instrument | PS5-25-BI-2302-CC01 | PS5-25-SDV-0022 | Instr:PS5-25-BI-2302, InstrLoc:Field, Branch:PS5-25-SXS-0022-CJ01, Sz:1P X 1.0 OS FR, L:35m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1699 | Instrument | PS5-25-BI-2305-CC01 | PS5-25-SDV-0035A | Instr:PS5-25-BI-2305, InstrLoc:Field, Branch:PS5-25-SDV-0035A-CC01, Sz:2P X 1.0 OS FR, L:70m, GlandS:M25, GlandD:M25 | Field | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1700 | Instrument | PS5-25-BI-2308-CC01 | PS5-25-SDV-0035A | Instr:PS5-25-BI-2308, InstrLoc:Field, Branch:PS5-25-SY-0035AA-CJ01, Sz:1P X 2.5 OS FR, L:50m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041
1701 | Instrument | PS5-25-BI-2309-CC01 | PS5-25-ESDV-0021 | Instr:PS5-25-BI-2309, InstrLoc:Field, Branch:PS5-25-ESY-0021B-CJ01, Sz:1P X 2.5 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0035
1702 | Instrument | PS5-25-BI-2312-CC01 | PS5-25-SDV-0035C | Instr:PS5-25-BI-2312, InstrLoc:Field, Branch:PS5-25-SXS-0035C-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041
1703 | Instrument | PS5-25-BI-2315-CC01 | PS5-25-SDV-0035C | Instr:PS5-25-BI-2315, InstrLoc:Field, Branch:PS5-25-SDV-0035C-CC01, Sz:2P X 1.0 OS FR, L:50m, GlandS:M25, GlandD:M25 | Field | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041
1704 | Instrument | PS5-25-BI-2316-CC01 | PS5-25-SDV-0035C | Instr:PS5-25-BI-2316, InstrLoc:Field, Branch:PS5-25-SY-0035CA-CJ01, Sz:1P X 2.5 OS FR, L:50m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1705 | Instrument | PS5-25-SHSR-0052-CJ01 | PS5-25-SDV-0052 |  | Field | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1706 | Instrument | PS5-28-BI-1105-CC01 | PS5-28-PIT-0015 | Instr:PS5-28-BI-1105, InstrLoc:Field, Branch:PS5-28-PIT-0015-CJ01, Sz:1P X 1.0 OS FL RTD, L:50m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041
1707 | Instrument | PS5-28-BI-1106-CC01 | PS5-28-LIT-1201 | Instr:PS5-28-BI-1106, InstrLoc:Field, Branch:PS5-28-LIT-1201-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1708 | Instrument | PS5-28-BI-1114-CC01 | PS5-28-TIT-1401 | Instr:PS5-28-BI-1114, InstrLoc:Field, Branch:PS5-28-TIT-1401-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049
1709 | Instrument | PS5-28-BI-1303-CC01 | PS5-28-LIT-1102 | Instr:PS5-28-BI-1303, InstrLoc:Field, Branch:PS5-28-LIT-1102-CJ01, Sz:1P X 1.0 OS FR, L:50m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1710 | Instrument | PS5-28-BI-1307-CC01 | PS5-28-TIT-1402 | Instr:PS5-28-BI-1307, InstrLoc:Field, Branch:PS5-28-TIT-1402-CJ01, Sz:1P X 1.0 OS FR, L:65m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1711 | Instrument | PS5-28-BI-2304-CC01 | PS5-28-SDV-0045 | Instr:PS5-28-BI-2304, InstrLoc:Field, Branch:PS5-28-SDV-0045-CC01, Sz:2P X 1.0 OS FR, L:25m, GlandS:M25, GlandD:M25 | Field | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-15 00:00:00 | CPP-RFI-68-64-04-0038
1712 | Instrument | PS5-28-HXA-1101-CJ01 | PS5-28-HXA-1101 |  | Field | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1713 | Instrument | PS5-28-LB-8200-CC01 | PS5-28-LB-8200 |  | LP | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1714 | Instrument | PS5-28-LB-8200-CJ01 | PS5-28-LB-8200 |  | LP | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1715 | Instrument | PS5-50-BI-1107-CC01 | PS5-28-LIT-0002 | Instr:PS5-50-BI-1107, InstrLoc:Field, Branch:PS5-28-LIT-0002-CJ01, Sz:1P X 1.0 OS FL RTD, L:90m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1716 | Instrument | PS5-50-IE-0001-CC01 | PS5-50-IE-0001 |  | LP | PS5-04-PMC-0008 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1717 | Instrument | PS5-50-IE-0001-CC02 | PS5-50-IE-0001 |  | LP | PS5-04-PMC-0007 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1718 | Instrument | PS5-50-IE-0002-CC01 | PS5-50-IE-0002 |  | LP | PS5-04-PMC-0008 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1719 | Instrument | PS5-50-IE-0002-CC02 | PS5-50-IE-0002 |  | LP | PS5-04-PMC-0007 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1720 | Instrument | PS5-50-IE-0001-CJ01 | PS5-50-LIT-0001 |  | LP | PS5-04-PMC-0001 |  | 33kV EITS Building
1721 | Instrument | PS5-50-IE-0002-CJ01 | PS5-50-LIT-0002 |  | LP | PS5-04-PMC-0001 |  | 33kV EITS Building
1722 | Instrument | PS5-53-BI-1108-CC01 | PS5-53-LIT-4101 | Instr:PS5-53-BI-1108, InstrLoc:Field, Branch:PS5-53-LIT-4101-CJ01, Sz:1P X 1.0 OS FL RTD, L:90m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1723 | Instrument | PS5-53-BI-1304-CC01 | PS5-53-LIT-4102 | Instr:PS5-53-BI-1304, InstrLoc:Field, Branch:PS5-53-LIT-4102-CJ01, Sz:1P X 1.0 OS FR, L:35m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0002 |  | 33kV EITS Building
1724 | Instrument | PS5-53-LA-0001-CC01 | PS5-53-LA-0001 |  | UCP | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1725 | Instrument | PS5-53-LA-0001-CC02 | PS5-53-LA-0001 |  | UCP | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1726 | Instrument | PS5-60-IE-0003A-CC21 | PS5-60-IE-0003A |  | GCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1727 | Instrument | PS5-60-IE-0003A-CC22 | PS5-60-IE-0003A |  | GCP | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1728 | Instrument | PS5-60-IE-0003A-CC23 | PS5-60-IE-0003A |  | GCP | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1729 | Instrument | PS5-60-IE-0003A-CC24 | PS5-60-IE-0003A |  | GCP | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1730 | Instrument | PS5-60-IE-0003B-CC21 | PS5-60-IE-0003B |  | GCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1731 | Instrument | PS5-60-IE-0003B-CC22 | PS5-60-IE-0003B |  | GCP | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1732 | Instrument | PS5-60-IE-0003B-CC23 | PS5-60-IE-0003B |  | GCP | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1733 | Instrument | PS5-60-IE-0003B-CC24 | PS5-60-IE-0003B |  | GCP | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1734 | Instrument | PS5-60-IE-0003C-CC21 | PS5-60-IE-0003C |  | GCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1735 | Instrument | PS5-60-IE-0003C-CC22 | PS5-60-IE-0003C |  | GCP | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1736 | Instrument | PS5-60-IE-0003C-CC23 | PS5-60-IE-0003C |  | GCP | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1737 | Instrument | PS5-60-IE-0003C-CC24 | PS5-60-IE-0003C |  | GCP | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1738 | Instrument | PS5-60-IE-0003D-CC21 | PS5-60-IE-0003D |  | GCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1739 | Instrument | PS5-60-IE-0003D-CC22 | PS5-60-IE-0003D |  | GCP | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1740 | Instrument | PS5-60-IE-0003D-CC23 | PS5-60-IE-0003D |  | GCP | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1741 | Instrument | PS5-60-IE-0003D-CC24 | PS5-60-IE-0003D |  | GCP | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1742 | Instrument | PS5-60-IE-0003E-CC21 | PS5-60-IE-0003E |  | GCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1743 | Instrument | PS5-60-IE-0003E-CC22 | PS5-60-IE-0003E |  | GCP | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049
1744 | Instrument | PS5-60-IE-0003E-CC23 | PS5-60-IE-0003E |  | GCP | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1745 | Instrument | PS5-60-IE-0003E-CC24 | PS5-60-IE-0003E |  | GCP | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1746 | Instrument | PS5-60-IE-0003F-CC21 | PS5-60-IE-0003F |  | GCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1747 | Instrument | PS5-60-IE-0003F-CC22 | PS5-60-IE-0003F |  | GCP | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1748 | Instrument | PS5-60-IE-0003F-CC23 | PS5-60-IE-0003F |  | GCP | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1749 | Instrument | PS5-60-IE-0003F-CC24 | PS5-60-IE-0003F |  | GCP | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1750 | Instrument | PS5-60-IE-0003G-CC21 | PS5-60-IE-0003G |  | GCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1751 | Instrument | PS5-60-IE-0003G-CC22 | PS5-60-IE-0003G |  | GCP | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1752 | Instrument | PS5-60-IE-0003G-CC23 | PS5-60-IE-0003G |  | GCP | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1753 | Instrument | PS5-60-IE-0003G-CC24 | PS5-60-IE-0003G |  | GCP | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1754 | Instrument | PS5-60-IE-0004-CC08 | PS5-60-IE-0004 |  | MCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1755 | Instrument | PS5-60-IE-0004-CC11 | PS5-60-IE-0004 |  | MCP | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1756 | Instrument | PS5-60-IE-0004-CC12 | PS5-60-IE-0004 |  | MCP | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1757 | Instrument | PS5-60-SEA-0001-CC18 | PS5-60-SEA-0001 |  | UCP | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1758 | Instrument | PS5-71-BI-1109-CC01 | PS5-71-LIT-4101 | Instr:PS5-71-BI-1109, InstrLoc:Field, Branch:PS5-71-LIT-4101-CJ01, Sz:1P X 1.0 OS FL RTD, L:45m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041
1759 | Instrument | PS5-71-BI-1110-CC01 | PS5-71-PDIT-0056B | Instr:PS5-71-BI-1110, InstrLoc:Field, Branch:PS5-71-PDIT-0056B-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1760 | Instrument | PS5-71-BI-1111-CC01 | PS5-71-FIT-0005 | Instr:PS5-71-BI-1111, InstrLoc:Field, Branch:PS5-71-FIT-0005-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1761 | Instrument | PS5-71-BI-1112-CC01 | PS5-71-FIT-0012 | Instr:PS5-71-BI-1112, InstrLoc:Field, Branch:PS5-71-FIT-0012-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1762 | Instrument | PS5-71-BI-1113-CC01 | PS5-71-FCV-0019 | Instr:PS5-71-BI-1113, InstrLoc:Field, Branch:PS5-71-FY-0019-CJ01, Sz:1P X 1.0 OS FL RTD, L:50m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1763 | Instrument | PS5-71-BI-1116-CC01 | PS5-71-FCV-0018 | Instr:PS5-71-BI-1116, InstrLoc:Field, Branch:PS5-71-FY-0018-CJ01, Sz:1P X 1.0 OS FL RTD, L:25m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1764 | Instrument | PS5-71-BI-1117-CC01 | PS5-71-XV-0089 | Instr:PS5-71-BI-1117, InstrLoc:Field, Branch:PS5-71-PIT-0089-CJ01, Sz:1P X 1.0 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1765 | Instrument | PS5-71-BI-2101-CC01 | PS5-71-XV-0089 | Instr:PS5-71-BI-2101, InstrLoc:Field, Branch:PS5-71-XY-0089-CJ01, Sz:1P X 2.5 OS FL RTD, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0004 |  | 33kV EITS Building
1766 | Instrument | PS5-71-BI-1305-CC01 | PS5-71-LIT-4102 | Instr:PS5-71-BI-1305, InstrLoc:Field, Branch:PS5-71-LIT-4102-CJ01, Sz:1P X 1.0 OS FR, L:45m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0002 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0041
1767 | Instrument | PS5-71-BI-1306-CC01 | PS5-71-LIT-4202 | Instr:PS5-71-BI-1306, InstrLoc:Field, Branch:PS5-71-LIT-4202-CJ01, Sz:1P X 1.0 OS FR, L:45m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1768 | Instrument | PS5-71-BI-1308-CC01 | PS5-71-LIT-4402 | Instr:PS5-71-BI-1308, InstrLoc:Field, Branch:PS5-71-LIT-4402-CJ01, Sz:1P X 1.0 OS FR, L:60m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0001 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1769 | Instrument | PS5-71-BI-2107-CC01 | PS5-71-LCV-4101 | Instr:PS5-71-BI-2107, InstrLoc:Field, Branch:PS5-71-LXS-4101-CJ01, Sz:1P X 1.0 OS FL RTD, L:45m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1770 | Instrument | PS5-71-BI-2113-CC01 | PS5-71-XV-0091 | Instr:PS5-71-BI-2113, InstrLoc:Field, Branch:PS5-71-XV-0091-CC01, Sz:2P X 1.0 OS FL RTD, L:50m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1771 | Instrument | PS5-71-BI-2114-CC01 | PS5-71-XV-0091 | Instr:PS5-71-BI-2114, InstrLoc:Field, Branch:PS5-71-XXS-0091-CJ01, Sz:1P X 1.0 OS FL RTD, L:50m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1772 | Instrument | PS5-71-BI-2115-CC01 | PS5-71-XV-0091 | Instr:PS5-71-BI-2115, InstrLoc:Field, Branch:PS5-71-XY-0091-CJ01, Sz:1P X 1.0 OS FL RTD, L:50m, GlandS:M20, GlandD:M20 | Field | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1773 | Instrument | PS5-71-BI-2116-CC01 | PS5-71-XV-0089 | Instr:PS5-71-BI-2116, InstrLoc:Field, Branch:PS5-71-XV-0089-CC01, Sz:2P X 1.0 OS FL RTD, L:55m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1774 | Instrument | PS5-71-BI-2118-CC01 | PS5-71-MOV-0007 | Instr:PS5-71-BI-2118, InstrLoc:Field, Branch:PS5-71-MOV-0007-CC01, Sz:6P X 0.75 OS FL RTD, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1775 | Instrument | PS5-71-BI-2119-CC01 | PS5-71-MOV-0009 | Instr:PS5-71-BI-2119, InstrLoc:Field, Branch:PS5-71-MOV-0009-CC01, Sz:6P X 0.75 OS FL RTD, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1776 | Instrument | PS5-71-BI-2120-CC01 | PS5-71-MOV-0001 | Instr:PS5-71-BI-2120, InstrLoc:Field, Branch:PS5-71-MOV-0001-CC01, Sz:6P X 0.75 OS FL RTD, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1777 | Instrument | PS5-71-BI-2121-CC01 | PS5-71-MOV-0003 | Instr:PS5-71-BI-2121, InstrLoc:Field, Branch:PS5-71-MOV-0003-CC01, Sz:6P X 0.75 OS FL RTD, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043
1778 | Instrument | PS5-71-BI-2122-CC01 | PS5-71-MOV-0007 | Instr:PS5-71-BI-2122, InstrLoc:Field, Branch:PS5-71-MOV-0007-CC02, Sz:6P X 0.75 OS FL RTD, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1779 | Instrument | PS5-71-BI-2123-CC01 | PS5-71-MOV-0009 | Instr:PS5-71-BI-2123, InstrLoc:Field, Branch:PS5-71-MOV-0009-CC02, Sz:6P X 0.75 OS FL RTD, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1780 | Instrument | PS5-71-BI-2124-CC01 | PS5-71-MOV-0001 | Instr:PS5-71-BI-2124, InstrLoc:Field, Branch:PS5-71-MOV-0001-CC02, Sz:6P X 0.75 OS FL RTD, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1781 | Instrument | PS5-71-BI-2125-CC01 | PS5-71-MOV-0003 | Instr:PS5-71-BI-2125, InstrLoc:Field, Branch:PS5-71-MOV-0003-CC02, Sz:6P X 0.75 OS FL RTD, L:40m, GlandS:M25, GlandD:M25 | Field | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1782 | Instrument | PS5-71-BI-2306-CC01 | PS5-71-SDV-0022 | Instr:PS5-71-BI-2306, InstrLoc:Field, Branch:PS5-71-SDV-0022-CC01, Sz:2P X 1.0 OS FR, L:50m, GlandS:M25, GlandD:M25 | Field | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1783 | Instrument | PS5-71-BI-2307-CC01 | PS5-71-SDV-0029 | Instr:PS5-71-BI-2307, InstrLoc:Field, Branch:PS5-71-SDV-0029-CC01, Sz:2P X 1.0 OS FR, L:25m, GlandS:M25, GlandD:M25 | Field | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1784 | Instrument | PS5-71-BI-2310-CC01 | PS5-71-SDV-0039 | Instr:PS5-71-BI-2310, InstrLoc:Field, Branch:PS5-71-SY-0039-CJ01, Sz:1P X 2.5 OS FR, L:45m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0035
1785 | Instrument | PS5-71-BI-2313-CC01 | PS5-71-SDV-0029 | Instr:PS5-71-BI-2313, InstrLoc:Field, Branch:PS5-71-SXS-0029-CJ01, Sz:1P X 1.0 OS FR, L:25m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0004 |  | 33kV EITS Building
1786 | Instrument | PS5-71-BI-2314-CC01 | PS5-71-SDV-0022 | Instr:PS5-71-BI-2314, InstrLoc:Field, Branch:PS5-71-SXS-0022-CJ01, Sz:1P X 1.0 OS FR, L:40m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-05-09 00:00:00 | CPP-RFI-68-64-04-0035
1787 | Instrument | PS5-71-BI-2317-CC01 | PS5-71-SDV-0029 | Instr:PS5-71-BI-2317, InstrLoc:Field, Branch:PS5-71-SY-0029-CJ01, Sz:1P X 2.5 OS FR, L:25m, GlandS:M20, GlandD:M20 | Field | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1788 | Instrument | PS5-71-IN-0001-CC08 | PS5-71-IN-0001 |  | UCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1789 | Instrument | PS5-71-IN-0001-CC09 | PS5-71-IN-0001 |  | UCP | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1790 | Instrument | PS5-71-IN-0001-CC10 | PS5-71-IN-0001 |  | UCP | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1791 | Instrument | PS5-71-IN-0002-CC05 | PS5-71-IN-0002 |  | UCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-64-04-0038
1792 | Instrument | PS5-71-IN-0002-CC06 | PS5-71-IN-0002 |  | UCP | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-64-04-0038
1793 | Instrument | PS5-71-IN-0002-CC07 | PS5-71-IN-0002 |  | UCP | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-17 00:00:00 | CPP-RFI-68-64-04-0038
1794 | Instrument | PS5-71-IN-0003-CC05 | PS5-71-IN-0003 |  | UCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1795 | Instrument | PS5-71-IN-0003-CC06 | PS5-71-IN-0003 |  | UCP | PS5-03-SFMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1796 | Instrument | PS5-71-IN-0003-CC07 | PS5-71-IN-0003 |  | UCP | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1797 | Instrument | PS5-71-IN-0004A-CC08 | PS5-71-IN-0004A |  | UCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1798 | Instrument | PS5-71-IN-0004A-CC09 | PS5-71-IN-0004A |  | UCP | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1799 | Instrument | PS5-71-IN-0004A-CC12 | PS5-71-IN-0004A |  | UCP | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1800 | Instrument | PS5-71-IN-0004B-CC08 | PS5-71-IN-0004B |  | UCP | PS5-04-PMC-0004 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1801 | Instrument | PS5-71-IN-0004B-CC09 | PS5-71-IN-0004B |  | UCP | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1802 | Instrument | PS5-71-IN-0004B-CC12 | PS5-71-IN-0004B |  | UCP | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1803 | Instrument | PS5-75-BI-1177-CC01 | PS5-75-BI-1177 |  | Package Skid | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1804 | Instrument | PS5-75-BI-1178-CC01 | PS5-75-BI-1178 |  | Package Skid | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1805 | Instrument | PS5-75-BI-1371-CC01 | PS5-75-BI-1371 |  | Package Skid | PS5-03-SFMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1806 | Instrument | PS5-75-BI-1372-CC01 | PS5-75-BI-1372 |  | Package Skid | PS5-03-SFMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1807 | Instrument | PS5-75-BI-0001-CC01 | PS5-75-BI-0001 |  | Skid | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049
1808 | Instrument | PS5-75-BI-0002-CC01 | PS5-75-BI-0002 |  | Skid | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049
1809 | Instrument | PS5-75-BI-0002-CC02 | PS5-75-BI-0002 |  | Skid | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049
1810 | Instrument | PS5-75-BI-0002-CC03 | PS5-75-BI-0002 |  | Skid | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049
1811 | Instrument | PS5-75-MOV-0001-CC01 | PS5-75-MOV-0001 |  | Field | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1812 | Instrument | PS5-75-MOV-0001-CC02 | PS5-75-MOV-0001 |  | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037
1813 | Instrument | PS5-79-IG-0001-CJ01 | PS5-79-XA-0001 |  | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1814 | Instrument | PS5-79-IG-0002-CJ01 | PS5-79-XA-0002 |  | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1815 | Instrument | PS5-79-IG-0003-CJ01 | PS5-79-XA-0003 |  | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1816 | Instrument | PS5-79-IG-0004-CJ01 | PS5-79-XA-0004 |  | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1817 | Instrument | PS5-79-IG-0005-CJ01 | PS5-79-XA-0005 |  | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1818 | Instrument | PS5-79-IG-0006-CJ01 | PS5-79-XA-0006 |  | Field | PS5-04-PMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1819 | Instrument | PS5-79-IG-0007-CJ01 | PS5-79-XA-0007 |  | Field | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1820 | Instrument | PS5-79-IG-0008-CJ01 | PS5-79-XA-0008 |  | Field | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1821 | Instrument | PS5-79-IG-0009-CJ01 | PS5-79-XA-0009 |  | Field | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1822 | Instrument | PS5-79-IG-0010-CJ01 | PS5-79-XA-0010 |  | Field | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1823 | Instrument | PS5-79-IG-0011-CJ01 | PS5-79-XA-0011 |  | Field | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1824 | Instrument | PS5-79-IG-0012-CJ01 | PS5-79-XA-0012 |  | Field | PS5-04-PMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1825 | Instrument | PS5-71-TIT-2403A-CJ01 | PS5-71-TIT-2403A |  | Field | PS5-71-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1826 | Instrument | PS5-71-TIT-2403B-CJ01 | PS5-71-TIT-2403B |  | Field | PS5-71-IE-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1827 | Instrument | PS5-05-BI-0002-CC01 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1828 | Instrument | PS5-05-BI-0002-CC02 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1829 | Instrument | PS5-05-IE-8101-CC01 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1830 | Instrument | PS5-05-BI-0002-CJ01 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1831 | Instrument | PS5-05-BI-0002-CJ02 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1832 | Instrument | PS5-05-BI-0002-CC05 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1833 | Instrument | PS5-05-GC-8100-CC01 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1834 | Instrument | PS5-05-LIT-4101-CJ01 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1835 | Instrument | PS5-05-UH-8100-CC01 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1836 | Instrument | PS5-05-BI-0002-CC03 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1837 | Instrument | PS5-05-UH-8100-CC02 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1838 | Instrument | PS5-05-BI-0002-CJ03 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1839 | Instrument | PS5-03-SEA-0001-CC01 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-06-30 00:00:00 | 2026-06-30 00:00:00
1840 | Instrument | PS5-05-BI-0002-CC06 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1841 | Instrument | PS5-05-BI-0002-CC04 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1842 | Instrument | PS5-05-IG-0009-CC01 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1843 | Instrument | PS5-05-IG-0009-CC02 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1844 | Instrument | PS5-05-IG-0009-CJ01 | PS5-05-BI-0002 |  | Field | PS5-05-IE-8100 |  | Generator Control Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1845 | Instrument | PS5-05-BI-0002-CC11 | PS5-05-BI-0002 |  | Field | PS5-03-SFMC-0009 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1846 | Instrument | PS5-05-BI-0002-CC12 | PS5-05-BI-0002 |  | Field | PS5-03-SFMC-0011 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1847 | Instrument | PS5-05-IE-8100-CC01 | PS5-05-IE-8100 |  | Generator Control Bldg | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049
1848 | Instrument | PS5-05-IE-8100-CC02 | PS5-05-IE-8100 |  | Generator Control Bldg | PS5-03-SFMC-0003 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1849 | Instrument | PS5-03-MTX-0001-CC01 | PS5-03-MTX-0001 |  | Off Bldg | PS5-03-SFMC-0001 |  | 33kV EITS Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1850 | Instrument | PS5-03-MTX-0001-CC02 | PS5-03-MTX-0001 |  | Off Bldg | PS5-03-SFMC-0001 |  | 33kV EITS Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1851 | Instrument | PS5-03-MTX-0001-CC03 | PS5-03-MTX-0001 |  | Off Bldg | PS5-03-SFMC-0004 |  | 33kV EITS Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1852 | Instrument | PS5-03-MTX-0001-CC04 | PS5-03-MTX-0001 |  | Off Bldg | PS5-03-SFMC-0005 |  | 33kV EITS Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1853 | Instrument | PS5-03-MTX-0001-CC05 | PS5-03-MTX-0001 |  | Off Bldg | PS5-03-SFMC-0010 |  | 33kV EITS Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1854 | Instrument | PS5-03-MTX-0001-CC06 | PS5-03-MTX-0001 |  | Off Bldg | PS5-03-SFMC-0011 |  | 33kV EITS Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1855 | Instrument | PS5-03-MTX-0001-CC07 | PS5-03-MTX-0001 |  | Off Bldg | PS5-03-SFMC-0011 |  | 33kV EITS Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1856 | Instrument | PS5-03-MTX-0001-CC08 | PS5-03-MTX-0001 |  | Off Bldg | PS5-03-SFMC-0012 |  | 33kV EITS Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1857 | Instrument | PS5-25-BI-1174A-CC01 | PS5-25-BI-1174A |  | Package Skid | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1858 | Instrument | PS5-25-BI-1174B-CC01 | PS5-25-BI-1174B |  | Package Skid | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1859 | Instrument | PS5-25-BI-1174C-CC01 | PS5-25-BI-1174C |  | Package Skid | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1860 | Instrument | PS5-25-BI-1274A-CC01 | PS5-25-BI-1274A |  | Package Skid | PS5-03-SFMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1861 | Instrument | PS5-25-BI-1274B-CC01 | PS5-25-BI-1274B |  | Package Skid | PS5-03-SFMC-0002 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1862 | Instrument | PS5-25-BI-1274C-CC01 | PS5-25-BI-1274C |  | Package Skid | PS5-03-SFMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1863 | Instrument | PS5-61-IDH-3100A-CC01 | PS5-61-IDH-3100A |  | E-House | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1864 | Instrument | PS5-61-IDH-3100A-CC02 | PS5-61-IDH-3100A |  | E-House | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1865 | Instrument | PS5-61-IDH-3100A-CC03 | PS5-61-IDH-3100A |  | E-House | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1866 | Instrument | PS5-61-IDH-3100B-CC01 | PS5-61-IDH-3100B |  | E-House | PS5-04-PMC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1867 | Instrument | PS5-61-IDH-3100B-CC02 | PS5-61-IDH-3100B |  | E-House | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1868 | Instrument | PS5-61-IDH-3100B-CC03 | PS5-61-IDH-3100B |  | E-House | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1869 | Instrument | PS5-61-IDH-3100C-CC01 | PS5-61-IDH-3100C |  | E-House | PS5-04-PMC-0002 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1870 | Instrument | PS5-61-IDH-3100C-CC02 | PS5-61-IDH-3100C |  | E-House | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1871 | Instrument | PS5-61-IDH-3100C-CC03 | PS5-61-IDH-3100C |  | E-House | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1872 | Instrument | PS5-25-MXS-3101AA-CJ01 | PS5-61-IDH-3100A |  | E-House | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1873 | Instrument | PS5-25-MXS-3101BA-CJ01 | PS5-61-IDH-3100B |  | E-House | PS5-03-SFMC-0005 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1874 | Instrument | PS5-25-MXS-3101CA-CJ01 | PS5-61-IDH-3100C |  | E-House | PS5-03-SFMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1875 | Instrument | PS5-83-EHO-0001A-CC01 | PS5-83-EHO-0001A |  | E-House | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1876 | Instrument | PS5-83-EHO-0001B-CC01 | PS5-83-EHO-0001B |  | E-House | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1877 | Instrument | PS5-83-EHO-0001C-CC01 | PS5-83-EHO-0001C |  | E-House | PS5-03-SFMC-0010 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1878 | Instrument | PS5-83-EHO-0001A-CJ01 | PS5-83-EHO-0001A |  | E-House | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1879 | Instrument | PS5-83-EHO-0001B-CJ01 | PS5-83-EHO-0001B |  | E-House | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1880 | Instrument | PS5-83-EHO-0001C-CJ01 | PS5-83-EHO-0001C |  | E-House | PS5-04-PMC-0006 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1881 | Instrument | PS5-25-BI-1801A-CC01 | PS5-25-BI-1801A |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054
1882 | Instrument | PS5-25-BI-1802A-CC01 | PS5-25-BI-1802A |  | Package Skid | PS5-61-IDH-3100A |  | E-House | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1883 | Instrument | PS5-25-BI-1802A-CC02 | PS5-25-BI-1802A |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1884 | Instrument | PS5-25-BI-1803A-CC01 | PS5-25-BI-1803A |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1885 | Instrument | PS5-25-BI-1803A-CC02 | PS5-25-BI-1803A |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1886 | Instrument | PS5-25-BI-1801B-CC01 | PS5-25-BI-1801B |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1887 | Instrument | PS5-25-BI-1802B-CC01 | PS5-25-BI-1802B |  | Package Skid | PS5-61-IDH-3100B |  | E-House | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1888 | Instrument | PS5-25-BI-1802B-CC02 | PS5-25-BI-1802B |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1889 | Instrument | PS5-25-BI-1803B-CC01 | PS5-25-BI-1803B |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1890 | Instrument | PS5-25-BI-1803B-CC02 | PS5-25-BI-1803B |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1891 | Instrument | PS5-25-BI-1801C-CC01 | PS5-25-BI-1801C |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1892 | Instrument | PS5-25-BI-1802C-CC01 | PS5-25-BI-1802C |  | Package Skid | PS5-61-IDH-3100C |  | E-House | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038 | 2026-08-28 00:00:00 | 2026-08-28 00:00:00
1893 | Instrument | PS5-25-BI-1802C-CC02 | PS5-25-BI-1802C |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1894 | Instrument | PS5-25-BI-1803C-CC01 | PS5-25-BI-1803C |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1895 | Instrument | PS5-25-BI-1803C-CC02 | PS5-25-BI-1803C |  | Package Skid | PS5-25-IE-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1896 | Instrument | PS5-71-BI-0001-CC01 | PS5-71-BI-0001 |  | Package Skid | PS5-26-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1897 | Instrument | PS5-71-BI-0021-CC01 | PS5-71-BI-0021 |  | Package Skid | PS5-26-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036
1898 | Instrument | PS5-71-BI-0021-CC02 | PS5-71-BI-0021 |  | Package Skid | PS5-26-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1899 | Instrument | PS5-25-MXS-3101AB-CJ01 | PS5-61-IDH-3100A |  | E-House | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1900 | Instrument | PS5-25-MXS-3101BB-CJ01 | PS5-61-IDH-3100B |  | E-House | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1901 | Instrument | PS5-25-MXS-3101CB-CJ01 | PS5-61-IDH-3100C |  | E-House | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1902 | Instrument | PS5-25-PIT-0052-CJ01 | PS5-25-SDV-0052 |  | Field | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1903 | Instrument | PS5-25-PIT-0071A-CJ01 | PS5-25-PIT-0071A |  | Field | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1904 | Instrument | PS5-25-PIT-0071B-CJ01 | PS5-25-PIT-0071B |  | Field | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1905 | Instrument | PS5-25-PIT-0071C-CJ01 | PS5-25-PIT-0071C |  | Field | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1906 | Instrument | PS5-25-SDV-0052-CC01 | PS5-25-SDV-0052 |  | Field | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1907 | Instrument | PS5-25-SXS-0052-CJ01 | PS5-25-SDV-0052 |  | Field | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1908 | Instrument | PS5-25-SY-0052A-CJ01 | PS5-25-SDV-0052 |  | Field | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1909 | Instrument | PS5-25-SDV-0052-CJ01 | PS5-25-SDV-0052IDC24 |  | Field | PS5-01-LA-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0038
1910 | Instrument | PS5-01-BI-0007-CC01 | PS5-01-BI-0007 |  | Package Skid | PS5-01-LB-0004 |  | Generator Control Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1911 | Instrument | PS5-01-BI-0008-CC01 | PS5-01-BI-0008 |  | Package Skid | PS5-01-LB-0004 |  | Generator Control Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1912 | Instrument | PS5-01-BI-0009-CC01 | PS5-01-BI-0009 |  | Package Skid | PS5-01-LB-0004 |  | Generator Control Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
1913 | Instrument | PS5-09-LB-0008-CX01 | PS5-09-LB-0008 |  | Generator Control Bldg HCP | PS5-04-PNC-0001 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
1914 | Instrument | PS5-09-LB-0006-CX01 | PS5-09-LB-0006 |  | Off Bldg HCP | PS5-04-PNC-0001 |  | 33kV EITS Building |  |  | 2026-10-31 00:00:00 | 2026-10-31 00:00:00
1915 | Instrument | PS5-09-LB-0007-CX01 | PS5-09-LB-0007 |  | Warehouse Bldg HCP | PS5-04-PNC-0001 |  | 33kV EITS Building | 2026-05-06 00:00:00 | CPP-RFI-68-64-04-0043 | 2026-10-27 00:00:00 | 2026-10-27 00:00:00
1916 | Instrument | PS5-60-IE-0004-CX03 | PS5-60-IE-0004 |  | Generator Control Bldg | PS5-04-PNC-0001 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1917 | Instrument | PS5-60-IE-0004-CX04 | PS5-60-IE-0004 |  | Generator Control Bldg | PS5-04-PNC-0001 |  | 33kV EITS Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1918 | Instrument | PS5-60-LA-0003-CX01 | PS5-60-LA-0003 |  | Generator Control Bldg | PS5-04-PNC-0001 |  | 33kV EITS Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1919 | Instrument | PS5-74-LB-5101-CX01 | PS5-74-LB-5101 |  | Package Skid | PS5-04-PNC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
1920 | Instrument | PS5-82-LA-0001-CX01 | PS5-82-LA-0001 |  | Package Skid | PS5-04-PNC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0037 | 2026-09-30 00:00:00 | 2026-09-30 00:00:00
1921 | Instrument | PS5-53-LA-0001-CX01 | PS5-53-LA-0001 |  | Package Skid | PS5-04-PNC-0001 |  | 33kV EITS Building | 2026-04-16 00:00:00 | CPP-RFI-68-64-04-0036 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1922 | Instrument | PS5-60-IN-0001A-CA01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0001A |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1923 | Instrument | PS5-60-IN-0001B-CA01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0001B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1924 | Instrument | PS5-60-IN-0001C-CA01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0001C |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1925 | Instrument | PS5-60-IN-0001D-CA01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0001D |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1926 | Instrument | PS5-60-IN-0001E-CA01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0001E |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1927 | Instrument | PS5-60-IN-0001F-CA01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0001F |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1928 | Instrument | PS5-60-IN-0001G-CA01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0001G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1929 | Instrument | PS5-60-IE-0003B-CA03 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1930 | Instrument | PS5-60-IE-0003B-CA04 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1931 | Instrument | PS5-60-IE-0003B-CA05 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1932 | Instrument | PS5-60-IE-0003C-CA03 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1933 | Instrument | PS5-60-IE-0003C-CA04 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1934 | Instrument | PS5-60-IE-0003C-CA05 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1935 | Instrument | PS5-60-IE-0003D-CA03 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1936 | Instrument | PS5-60-IE-0003D-CA04 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1937 | Instrument | PS5-60-IE-0003D-CA05 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1938 | Instrument | PS5-60-IE-0003E-CA03 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1939 | Instrument | PS5-60-IE-0003E-CA04 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1940 | Instrument | PS5-60-IE-0003E-CA05 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1941 | Instrument | PS5-60-IE-0003F-CA03 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
1942 | Instrument | PS5-60-IE-0003F-CA04 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
1943 | Instrument | PS5-60-IE-0003F-CA05 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
1944 | Instrument | PS5-60-IE-0003G-CA03 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1945 | Instrument | PS5-60-IE-0003G-CA04 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1946 | Instrument | PS5-60-IE-0003G-CA05 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1947 | Instrument | PS5-60-IE-0004-CA01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1948 | Instrument | PS5-60-IE-0004-CA07 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1949 | Instrument | PS5-60-IE-0004-CA08 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1950 | Instrument | PS5-60-IE-0004-CA14 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1951 | Instrument | PS5-60-IE-0004-CA15 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1952 | Instrument | PS5-60-IE-0004-CA21 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1953 | Instrument | PS5-60-IN-0002A-CA01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1954 | Instrument | PS5-60-IN-0002B-CA01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0002B |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
1955 | Instrument | PS5-60-IN-0002C-CA01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0002C |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1956 | Instrument | PS5-60-IN-0002D-CA01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0002D |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1957 | Instrument | PS5-60-IN-0002E-CA01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0002E |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1958 | Instrument | PS5-60-IN-0002F-CA01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0002F |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1959 | Instrument | PS5-60-IN-0002G-CA01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0002G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1960 | Instrument | PS5-60-LA-0002B-CA01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1961 | Instrument | PS5-60-LA-0002B-CA02 | PS5-60-LA-0002A |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1962 | Instrument | PS5-60-LA-0002B-CA03 | PS5-60-LA-0002A |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1963 | Instrument | PS5-60-LA-0002B-CA04 | PS5-60-LA-0002A |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1964 | Instrument | PS5-60-LA-0002B-CA05 | PS5-60-LA-0002C |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1965 | Instrument | PS5-60-LA-0002B-CA06 | PS5-60-LA-0002C |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1966 | Instrument | PS5-60-LA-0002C-CA01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1967 | Instrument | PS5-60-LA-0002C-CA02 | PS5-60-LA-0002A |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1968 | Instrument | PS5-60-LA-0002C-CA03 | PS5-60-LA-0002A |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1969 | Instrument | PS5-60-LA-0002C-CA04 | PS5-60-LA-0002A |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1970 | Instrument | PS5-60-LA-0002C-CA05 | PS5-60-LA-0002B |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1971 | Instrument | PS5-60-LA-0002C-CA06 | PS5-60-LA-0002B |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
1972 | Instrument | PS5-60-SEA-0001-CA01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
1973 | Instrument | PS5-71-IN-0001-CA01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0001 |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1974 | Instrument | PS5-71-IN-0002-CA01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0002 |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1975 | Instrument | PS5-71-IN-0003-CA01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0003 |  | Powergen Building |  |  | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
1976 | Instrument | PS5-71-IN-0004A-CA01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1977 | Instrument | PS5-71-IN-0004B-CA01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
1978 | Instrument | PS5-60-IN-0001A-CC02 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0001A |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1979 | Instrument | PS5-60-IN-0001B-CC02 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0001B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1980 | Instrument | PS5-60-IN-0001C-CC02 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0001C |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1981 | Instrument | PS5-60-IN-0001D-CC02 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0001D |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1982 | Instrument | PS5-60-IN-0001E-CC02 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0001E |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1983 | Instrument | PS5-60-IN-0001F-CC02 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0001F |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1984 | Instrument | PS5-60-IN-0001G-CC02 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0001G |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1985 | Instrument | PS5-60-IN-0001A-CC04 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0001A |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1986 | Instrument | PS5-60-IN-0001B-CC04 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0001B |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1987 | Instrument | PS5-60-IN-0001C-CC04 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0001C |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1988 | Instrument | PS5-60-IN-0001D-CC04 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0001D |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1989 | Instrument | PS5-60-IN-0001E-CC04 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0001E |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1990 | Instrument | PS5-60-IN-0001F-CC04 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0001F |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
1991 | Instrument | PS5-60-IN-0001G-CC04 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0001G |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
1992 | Instrument | PS5-60-BI-0002-CC04 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-BI-0002 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1993 | Instrument | PS5-60-BI-0002-CC03 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-BI-0002 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1994 | Instrument | PS5-60-BI-0001A-CC03 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0001A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
1995 | Instrument | PS5-60-BI-0001B-CC03 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0001B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1996 | Instrument | PS5-60-BI-0001C-CC03 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0001C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1997 | Instrument | PS5-60-BI-0001D-CC03 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0001D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1998 | Instrument | PS5-60-BI-0001E-CC03 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0001E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
1999 | Instrument | PS5-60-BI-0001F-CC03 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0001F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2000 | Instrument | PS5-60-BI-0001G-CC03 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0001G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2001 | Instrument | PS5-60-BI-0001A-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0001A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2002 | Instrument | PS5-60-BI-0001B-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0001B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2003 | Instrument | PS5-60-BI-0001C-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0001C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2004 | Instrument | PS5-60-BI-0001D-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0001D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2005 | Instrument | PS5-60-BI-0001E-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0001E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2006 | Instrument | PS5-60-BI-0001F-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0001F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2007 | Instrument | PS5-60-BI-0001G-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0001G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2008 | Instrument | PS5-60-IE-0002B-CC05 | PS5-60-IE-0002A |  | Powergen Bldg | PS5-60-IE-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2009 | Instrument | PS5-60-IE-0002C-CC05 | PS5-60-IE-0002B |  | Powergen Bldg | PS5-60-IE-0002C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2010 | Instrument | PS5-60-IE-0002D-CC05 | PS5-60-IE-0002C |  | Powergen Bldg | PS5-60-IE-0002D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2011 | Instrument | PS5-60-IE-0002E-CC05 | PS5-60-IE-0002D |  | Powergen Bldg | PS5-60-IE-0002E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2012 | Instrument | PS5-60-IE-0002F-CC05 | PS5-60-IE-0002E |  | Powergen Bldg | PS5-60-IE-0002F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2013 | Instrument | PS5-60-IE-0002G-CC05 | PS5-60-IE-0002F |  | Powergen Bldg | PS5-60-IE-0002G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2014 | Instrument | PS5-61-BI-0001-CC03 | PS5-61-TE-0003A |  | Powergen Bldg | PS5-61-BI-0001 |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2015 | Instrument | PS5-61-BI-0002-CC03 | PS5-61-TE-0003B |  | Powergen Bldg | PS5-61-BI-0002 |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2016 | Instrument | PS5-61-BI-0003-CC03 | PS5-61-TE-0003C |  | Powergen Bldg | PS5-61-BI-0003 |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2017 | Instrument | PS5-61-BI-0004-CC03 | PS5-61-TE-0003D |  | Powergen Bldg | PS5-61-BI-0004 |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2018 | Instrument | PS5-61-BI-0005-CC03 | PS5-61-TE-0003E |  | Powergen Bldg | PS5-61-BI-0005 |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2019 | Instrument | PS5-61-BI-0006-CC03 | PS5-61-TE-0003F |  | Powergen Bldg | PS5-61-BI-0006 |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2020 | Instrument | PS5-61-BI-0007-CC03 | PS5-61-TE-0003G |  | Powergen Bldg | PS5-61-BI-0007 |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2021 | Instrument | PS5-60-BE-0004A-CC01 | PS5-60-IN-0001A |  | Powergen Bldg | PS5-60-BE-0004A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2022 | Instrument | PS5-60-BE-0004B-CC01 | PS5-60-IN-0001B |  | Powergen Bldg | PS5-60-BE-0004B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2023 | Instrument | PS5-60-BE-0004C-CC01 | PS5-60-IN-0001C |  | Powergen Bldg | PS5-60-BE-0004C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2024 | Instrument | PS5-60-BE-0004D-CC01 | PS5-60-IN-0001D |  | Powergen Bldg | PS5-60-BE-0004D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2025 | Instrument | PS5-60-BE-0004E-CC01 | PS5-60-IN-0001E |  | Powergen Bldg | PS5-60-BE-0004E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2026 | Instrument | PS5-60-BE-0004F-CC01 | PS5-60-IN-0001F |  | Powergen Bldg | PS5-60-BE-0004F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2027 | Instrument | PS5-60-BE-0004G-CC01 | PS5-60-IN-0001G |  | Powergen Bldg | PS5-60-BE-0004G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2028 | Instrument | PS5-60-BI-0016A-CC03 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0016A |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2029 | Instrument | PS5-60-BI-0016B-CC03 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0016B |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2030 | Instrument | PS5-60-BI-0016C-CC03 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0016C |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2031 | Instrument | PS5-60-BI-0016D-CC03 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0016D |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2032 | Instrument | PS5-60-BI-0016E-CC03 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0016E |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2033 | Instrument | PS5-60-BI-0016F-CC03 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0016F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2034 | Instrument | PS5-60-BI-0016G-CC03 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0016G |  | Powergen Building | 2026-06-23 00:00:00 | CPP-RFI-68-64-04-0071 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2035 | Instrument | PS5-60-BE-0001-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-BE-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2036 | Instrument | PS5-60-BE-0002-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-BE-0002 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2037 | Instrument | PS5-60-SY-0007-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-SY-0007 |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2038 | Instrument | PS5-60-SY-0008-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-SY-0008 |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2039 | Instrument | PS5-60-SY-0009-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-SY-0009 |  | Powergen Building |  |  | 2026-08-14 00:00:00 | 2026-08-14 00:00:00
2040 | Instrument | PS5-60-SY-0010-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-SY-0010 |  | Powergen Building |  |  | 2026-08-14 00:00:00 | 2026-08-14 00:00:00
2041 | Instrument | PS5-60-SY-0011-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-SY-0011 |  | Powergen Building |  |  | 2026-08-14 00:00:00 | 2026-08-14 00:00:00
2042 | Instrument | PS5-60-SY-0012-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-SY-0012 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-14 00:00:00 | 2026-08-14 00:00:00
2043 | Instrument | PS5-60-SY-0013-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-SY-0013 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2044 | Instrument | PS5-71-IN-0001-CC04 | PS5-71-IN-0001 |  | Powergen Bldg | PS5-71-BI-0011A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2045 | Instrument | PS5-71-IN-0001-CC05 | PS5-71-IN-0001 |  | Powergen Bldg | PS5-71-BI-0011B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2046 | Instrument | PS5-71-IN-0004A-CC04 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2047 | Instrument | PS5-71-IN-0004A-CC05 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2048 | Instrument | PS5-71-IN-0004B-CC04 | PS5-71-IN-0004B |  | Powergen Bldg | PS5-71-BI-0011B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2049 | Instrument | PS5-71-IN-0004B-CC05 | PS5-71-IN-0004B |  | Powergen Bldg | PS5-71-BI-0011B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2050 | Instrument | PS5-60-IE-0003A-CC25 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-TX-41100A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2051 | Instrument | PS5-60-IE-0003A-CC26 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-TX-41100B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2052 | Instrument | PS5-60-IE-0003B-CC25 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-TX-41200A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2053 | Instrument | PS5-60-IE-0003B-CC26 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-TX-41200B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2054 | Instrument | PS5-60-IE-0003C-CC25 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-TX-41300A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2055 | Instrument | PS5-60-IE-0003C-CC26 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-TX-41300B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2056 | Instrument | PS5-60-IE-0003D-CC25 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-TX-41400A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2057 | Instrument | PS5-60-IE-0003D-CC26 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-TX-41400B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2058 | Instrument | PS5-60-IE-0003E-CC25 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-TX-41500A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2059 | Instrument | PS5-60-IE-0003E-CC26 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-TX-41500B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2060 | Instrument | PS5-60-IE-0003F-CC25 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-TX-41600A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2061 | Instrument | PS5-60-IE-0003F-CC26 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-TX-41600B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0078 | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2062 | Instrument | PS5-60-IE-0003G-CC25 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-TX-41700A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2063 | Instrument | PS5-60-IE-0003G-CC26 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-TX-41700B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2064 | Instrument | PS5-60-IN-0001A-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0001A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2065 | Instrument | PS5-60-IN-0001B-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0001B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2066 | Instrument | PS5-60-IN-0001C-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0001C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2067 | Instrument | PS5-60-IN-0001D-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0001D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2068 | Instrument | PS5-60-IN-0001E-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0001E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2069 | Instrument | PS5-60-IN-0001F-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0001F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2070 | Instrument | PS5-60-IN-0001G-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0001G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2071 | Instrument | PS5-60-IN-0001A-CC03 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0001A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2072 | Instrument | PS5-60-IN-0001B-CC03 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0001B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2073 | Instrument | PS5-60-IN-0001C-CC03 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0001C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2074 | Instrument | PS5-60-IN-0001D-CC03 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0001D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2075 | Instrument | PS5-60-IN-0001E-CC03 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0001E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2076 | Instrument | PS5-60-IN-0001F-CC03 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0001F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2077 | Instrument | PS5-60-IN-0001G-CC03 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0001G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2078 | Instrument | PS5-60-BI-0006A-CC05 | PS5-60-IN-0002A |  | Powergen Bldg | PS5-60-BI-0006A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2079 | Instrument | PS5-60-BI-0006B-CC05 | PS5-60-IN-0002B |  | Powergen Bldg | PS5-60-BI-0006B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2080 | Instrument | PS5-60-BI-0006C-CC05 | PS5-60-IN-0002C |  | Powergen Bldg | PS5-60-BI-0006C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2081 | Instrument | PS5-60-BI-0006D-CC05 | PS5-60-IN-0002D |  | Powergen Bldg | PS5-60-BI-0006D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2082 | Instrument | PS5-60-BI-0006E-CC05 | PS5-60-IN-0002E |  | Powergen Bldg | PS5-60-BI-0006E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2083 | Instrument | PS5-60-BI-0006F-CC05 | PS5-60-IN-0002F |  | Powergen Bldg | PS5-60-BI-0006F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2084 | Instrument | PS5-60-BI-0006G-CC05 | PS5-60-IN-0002G |  | Powergen Bldg | PS5-60-BI-0006G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2085 | Instrument | PS5-60-IE-0003A-CC15 | PS5-60-IE-0002A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2086 | Instrument | PS5-60-IE-0003B-CC15 | PS5-60-IE-0002B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2087 | Instrument | PS5-60-LA-0003-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-LA-0003 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2088 | Instrument | PS5-71-BI-0009-CC02 | PS5-71-IN-0001 |  | Powergen Bldg | PS5-71-BI-0009 |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2089 | Instrument | PS5-71-BI-0009-CC03 | PS5-71-IN-0001 |  | Powergen Bldg | PS5-71-BI-0009 |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2090 | Instrument | PS5-71-BI-0011B-CC03 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2091 | Instrument | PS5-60-BI-0003-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-BI-0003 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2092 | Instrument | PS5-60-IN-0002A-CC06 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0002A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2093 | Instrument | PS5-60-IN-0002B-CC06 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0002B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2094 | Instrument | PS5-60-IN-0002C-CC06 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0002C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2095 | Instrument | PS5-60-IN-0002D-CC06 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0002D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2096 | Instrument | PS5-60-IN-0002E-CC06 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0002E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2097 | Instrument | PS5-60-IN-0002F-CC06 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0002F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2098 | Instrument | PS5-60-IN-0002G-CC06 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0002G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2099 | Instrument | PS5-71-BI-0003-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-BI-0003 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2100 | Instrument | PS5-71-BI-0005-CC02 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-BI-0005 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
2101 | Instrument | PS5-71-IN-0001-CC03 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2102 | Instrument | PS5-71-IN-0004A-CC03 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2103 | Instrument | PS5-71-IN-0004B-CC03 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2104 | Instrument | PS5-60-BI-0003-CC02 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-BI-0003 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2105 | Instrument | PS5-60-BI-0006A-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0006A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2106 | Instrument | PS5-60-BI-0006B-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0006B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2107 | Instrument | PS5-60-BI-0006C-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0006C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2108 | Instrument | PS5-60-BI-0006D-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0006D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2109 | Instrument | PS5-60-BI-0006E-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0006E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2110 | Instrument | PS5-60-BI-0006F-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0006F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2111 | Instrument | PS5-60-BI-0006G-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0006G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2112 | Instrument | PS5-60-BI-0016A-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0016A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2113 | Instrument | PS5-60-BI-0016B-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0016B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2114 | Instrument | PS5-60-BI-0016C-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0016C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2115 | Instrument | PS5-60-BI-0016D-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0016D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2116 | Instrument | PS5-60-BI-0016E-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0016E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2117 | Instrument | PS5-60-BI-0016F-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0016F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2118 | Instrument | PS5-60-BI-0016G-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0016G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2119 | Instrument | PS5-60-BI-0002-CC02 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-BI-0002 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2120 | Instrument | PS5-60-BI-0005A-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0005A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2121 | Instrument | PS5-60-BI-0005A-CC02 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0005A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2122 | Instrument | PS5-60-BI-0005B-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0005B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2123 | Instrument | PS5-60-BI-0005B-CC02 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0005B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2124 | Instrument | PS5-60-BI-0005C-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0005C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2125 | Instrument | PS5-60-BI-0005C-CC02 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0005C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2126 | Instrument | PS5-60-BI-0005D-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0005D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2127 | Instrument | PS5-60-BI-0005D-CC02 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0005D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2128 | Instrument | PS5-60-BI-0005E-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0005E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2129 | Instrument | PS5-60-BI-0005E-CC02 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0005E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2130 | Instrument | PS5-60-BI-0005F-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0005F |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2131 | Instrument | PS5-60-BI-0005F-CC02 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0005F |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2132 | Instrument | PS5-60-BI-0005G-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0005G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2133 | Instrument | PS5-60-BI-0005G-CC02 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0005G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2134 | Instrument | PS5-60-BI-0006A-CC03 | PS5-60-IN-0002A |  | Powergen Bldg | PS5-60-BI-0006A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2135 | Instrument | PS5-60-BI-0006A-CC06 | PS5-60-IN-0002A |  | Powergen Bldg | PS5-60-BI-0006A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2136 | Instrument | PS5-60-BI-0006B-CC03 | PS5-60-IN-0002B |  | Powergen Bldg | PS5-60-BI-0006B |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2137 | Instrument | PS5-60-BI-0006B-CC06 | PS5-60-IN-0002B |  | Powergen Bldg | PS5-60-BI-0006B |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2138 | Instrument | PS5-60-BI-0006C-CC03 | PS5-60-IN-0002C |  | Powergen Bldg | PS5-60-BI-0006C |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2139 | Instrument | PS5-60-BI-0006C-CC06 | PS5-60-IN-0002C |  | Powergen Bldg | PS5-60-BI-0006C |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2140 | Instrument | PS5-60-BI-0006D-CC03 | PS5-60-IN-0002D |  | Powergen Bldg | PS5-60-BI-0006D |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2141 | Instrument | PS5-60-BI-0006D-CC06 | PS5-60-IN-0002D |  | Powergen Bldg | PS5-60-BI-0006D |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2142 | Instrument | PS5-60-BI-0006E-CC03 | PS5-60-IN-0002E |  | Powergen Bldg | PS5-60-BI-0006E |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2143 | Instrument | PS5-60-BI-0006E-CC06 | PS5-60-IN-0002E |  | Powergen Bldg | PS5-60-BI-0006E |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2144 | Instrument | PS5-60-BI-0006F-CC03 | PS5-60-IN-0002F |  | Powergen Bldg | PS5-60-BI-0006F |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2145 | Instrument | PS5-60-BI-0006F-CC06 | PS5-60-IN-0002F |  | Powergen Bldg | PS5-60-BI-0006F |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2146 | Instrument | PS5-60-BI-0006G-CC03 | PS5-60-IN-0002G |  | Powergen Bldg | PS5-60-BI-0006G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2147 | Instrument | PS5-60-BI-0006G-CC06 | PS5-60-IN-0002G |  | Powergen Bldg | PS5-60-BI-0006G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2148 | Instrument | PS5-60-IE-0003A-CC07 | PS5-60-IE-0002A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2149 | Instrument | PS5-60-IE-0003B-CC06 | PS5-60-IE-0002B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2150 | Instrument | PS5-60-IE-0003B-CC07 | PS5-60-IE-0002B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2151 | Instrument | PS5-60-IE-0003C-CC06 | PS5-60-IE-0002C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2152 | Instrument | PS5-60-IE-0003C-CC07 | PS5-60-IE-0002C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2153 | Instrument | PS5-60-IE-0003D-CC06 | PS5-60-IE-0002D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2154 | Instrument | PS5-60-IE-0003D-CC07 | PS5-60-IE-0002D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2155 | Instrument | PS5-60-IE-0003E-CC06 | PS5-60-IE-0002E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2156 | Instrument | PS5-60-IE-0003E-CC07 | PS5-60-IE-0002E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2157 | Instrument | PS5-60-IE-0003F-CC06 | PS5-60-IE-0002F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2158 | Instrument | PS5-60-IE-0003F-CC07 | PS5-60-IE-0002F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2159 | Instrument | PS5-60-IE-0003G-CC06 | PS5-60-IE-0002G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2160 | Instrument | PS5-60-IE-0003G-CC07 | PS5-60-IE-0002G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2161 | Instrument | PS5-60-IN-0002A-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2162 | Instrument | PS5-60-IN-0002A-CC04 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2163 | Instrument | PS5-60-IN-0002B-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0002B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2164 | Instrument | PS5-60-IN-0002B-CC04 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0002B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2165 | Instrument | PS5-60-IN-0002C-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0002C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2166 | Instrument | PS5-60-IN-0002C-CC04 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0002C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2167 | Instrument | PS5-60-IN-0002D-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0002D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2168 | Instrument | PS5-60-IN-0002D-CC04 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0002D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2169 | Instrument | PS5-60-IN-0002E-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0002E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2170 | Instrument | PS5-60-IN-0002E-CC04 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0002E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2171 | Instrument | PS5-60-IN-0002F-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0002F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2172 | Instrument | PS5-60-IN-0002F-CC04 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0002F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2173 | Instrument | PS5-60-IN-0002G-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0002G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2174 | Instrument | PS5-60-IN-0002G-CC04 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0002G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2175 | Instrument | PS5-60-SEA-0001-CC10 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2176 | Instrument | PS5-60-VS-9101A-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-VS-9101A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2177 | Instrument | PS5-60-VS-9101B-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-VS-9101B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2178 | Instrument | PS5-60-VS-9101C-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-VS-9101C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2179 | Instrument | PS5-60-VS-9101D-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-VS-9101D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2180 | Instrument | PS5-60-VS-9101E-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-VS-9101E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2181 | Instrument | PS5-60-VS-9101F-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-VS-9101F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2182 | Instrument | PS5-60-VS-9101G-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-VS-9101G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2183 | Instrument | PS5-71-BI-0003-CC04 | PS5-71-IN-0002 |  | Powergen Bldg | PS5-71-BI-0003 |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2184 | Instrument | PS5-71-BI-0006-CC01 | PS5-71-IN-0003 |  | Powergen Bldg | PS5-71-BI-0006 |  | Powergen Building |  |  | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
2185 | Instrument | PS5-71-BI-0009-CC04 | PS5-71-IN-0001 |  | Powergen Bldg | PS5-71-BI-0009 |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2186 | Instrument | PS5-71-BI-0010-CC01 | PS5-71-IN-0001 |  | Powergen Bldg | PS5-71-BI-0010 |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2187 | Instrument | PS5-71-BI-0011A-CC03 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2188 | Instrument | PS5-71-IN-0001-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2189 | Instrument | PS5-71-IN-0001-CC02 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2190 | Instrument | PS5-71-IN-0002-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0002 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2191 | Instrument | PS5-71-IN-0003-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0003 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
2192 | Instrument | PS5-71-IN-0003-CC02 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0003 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
2193 | Instrument | PS5-60-BI-0006A-CC02 | PS5-60-IN-0002A |  | Powergen Bldg | PS5-60-BI-0006A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2194 | Instrument | PS5-60-BI-0006B-CC02 | PS5-60-IN-0002B |  | Powergen Bldg | PS5-60-BI-0006B |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2195 | Instrument | PS5-60-BI-0006C-CC02 | PS5-60-IN-0002C |  | Powergen Bldg | PS5-60-BI-0006C |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2196 | Instrument | PS5-60-BI-0006D-CC02 | PS5-60-IN-0002D |  | Powergen Bldg | PS5-60-BI-0006D |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2197 | Instrument | PS5-60-BI-0006E-CC02 | PS5-60-IN-0002E |  | Powergen Bldg | PS5-60-BI-0006E |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2198 | Instrument | PS5-60-BI-0006F-CC02 | PS5-60-IN-0002F |  | Powergen Bldg | PS5-60-BI-0006F |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2199 | Instrument | PS5-60-BI-0006G-CC02 | PS5-60-IN-0002G |  | Powergen Bldg | PS5-60-BI-0006G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2200 | Instrument | PS5-60-IE-0003A-CC03 | PS5-60-IE-0001A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2201 | Instrument | PS5-60-IE-0003B-CC03 | PS5-60-IE-0001B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2202 | Instrument | PS5-60-IE-0003C-CC03 | PS5-60-IE-0001C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2203 | Instrument | PS5-60-IE-0003D-CC03 | PS5-60-IE-0001D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2204 | Instrument | PS5-60-IE-0003E-CC03 | PS5-60-IE-0001E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2205 | Instrument | PS5-60-IE-0003F-CC03 | PS5-60-IE-0001F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2206 | Instrument | PS5-60-IN-0002A-CC03 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2207 | Instrument | PS5-60-IN-0002A-CC05 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2208 | Instrument | PS5-60-IN-0002B-CC03 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0002B |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2209 | Instrument | PS5-60-IN-0002B-CC05 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0002B |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2210 | Instrument | PS5-60-IN-0002C-CC03 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0002C |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2211 | Instrument | PS5-60-IN-0002C-CC05 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0002C |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2212 | Instrument | PS5-60-IN-0002D-CC03 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0002D |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2213 | Instrument | PS5-60-IN-0002D-CC05 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0002D |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2214 | Instrument | PS5-60-IN-0002E-CC03 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0002E |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2215 | Instrument | PS5-60-IN-0002E-CC05 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0002E |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2216 | Instrument | PS5-60-IN-0002F-CC03 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0002F |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2217 | Instrument | PS5-60-IN-0002F-CC05 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0002F |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2218 | Instrument | PS5-60-IN-0002G-CC03 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0002G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2219 | Instrument | PS5-60-IN-0002G-CC05 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0002G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2220 | Instrument | PS5-60-LA-0002A-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-LA-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2221 | Instrument | PS5-60-LA-0002A-CC02 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-LA-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2222 | Instrument | PS5-60-LA-0002A-CC03 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-LA-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2223 | Instrument | PS5-60-LA-0002A-CC04 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-LA-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2224 | Instrument | PS5-60-LA-0002A-CC05 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-LA-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2225 | Instrument | PS5-60-LA-0002A-CC06 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-LA-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2226 | Instrument | PS5-60-LA-0002A-CC07 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-LA-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2227 | Instrument | PS5-60-LA-0002A-CC08 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-LA-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2228 | Instrument | PS5-60-LA-0002A-CC09 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-LA-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2229 | Instrument | PS5-60-LA-0002B-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2230 | Instrument | PS5-60-LA-0002B-CC02 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2231 | Instrument | PS5-60-LA-0002B-CC03 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2232 | Instrument | PS5-60-LA-0002B-CC04 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2233 | Instrument | PS5-60-LA-0002B-CC05 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2234 | Instrument | PS5-60-LA-0002B-CC06 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-LA-0002B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2235 | Instrument | PS5-60-LA-0002C-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2236 | Instrument | PS5-60-LA-0002C-CC02 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2237 | Instrument | PS5-60-LA-0002C-CC03 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2238 | Instrument | PS5-60-LA-0002C-CC04 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2239 | Instrument | PS5-60-LA-0002C-CC05 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2240 | Instrument | PS5-60-LA-0002C-CC06 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-LA-0002C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2241 | Instrument | PS5-60-SEA-0001-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2242 | Instrument | PS5-60-SEA-0001-CC02 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2243 | Instrument | PS5-60-SEA-0001-CC03 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2244 | Instrument | PS5-60-SEA-0001-CC04 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2245 | Instrument | PS5-60-SEA-0001-CC05 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2246 | Instrument | PS5-60-SEA-0001-CC06 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2247 | Instrument | PS5-60-SEA-0001-CC07 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2248 | Instrument | PS5-60-SEA-0001-CC11 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2249 | Instrument | PS5-60-SEA-0001-CC12 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2250 | Instrument | PS5-60-SEA-0001-CC13 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2251 | Instrument | PS5-60-SEA-0001-CC14 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2252 | Instrument | PS5-60-SEA-0001-CC15 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2253 | Instrument | PS5-60-SEA-0001-CC16 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2254 | Instrument | PS5-60-SEA-0001-CC17 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2255 | Instrument | PS5-61-BI-0001-CC02 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-61-BI-0001 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2256 | Instrument | PS5-61-BI-0002-CC02 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-61-BI-0002 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2257 | Instrument | PS5-61-BI-0003-CC02 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-61-BI-0003 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2258 | Instrument | PS5-61-BI-0004-CC02 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-61-BI-0004 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2259 | Instrument | PS5-61-BI-0005-CC02 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-61-BI-0005 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2260 | Instrument | PS5-61-BI-0006-CC02 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-61-BI-0006 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2261 | Instrument | PS5-61-BI-0007-CC02 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-61-BI-0007 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2262 | Instrument | PS5-71-IN-0001-CC06 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2263 | Instrument | PS5-71-IN-0001-CC07 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2264 | Instrument | PS5-71-IN-0002-CC03 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0002 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0080 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2265 | Instrument | PS5-71-IN-0002-CC04 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0002 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2266 | Instrument | PS5-71-IN-0003-CC03 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0003 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
2267 | Instrument | PS5-71-IN-0003-CC04 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0003 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
2268 | Instrument | PS5-71-IN-0004A-CC06 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2269 | Instrument | PS5-71-IN-0004A-CC07 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2270 | Instrument | PS5-71-IN-0004B-CC06 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2271 | Instrument | PS5-71-IN-0004B-CC07 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2272 | Instrument | PS5-60-BI-0019A-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0019A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2273 | Instrument | PS5-60-BI-0019B-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0019B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2274 | Instrument | PS5-60-BI-0019C-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0019C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2275 | Instrument | PS5-60-BI-0019D-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0019D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2276 | Instrument | PS5-60-BI-0019E-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0019E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2277 | Instrument | PS5-60-BI-0019F-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0019F |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2278 | Instrument | PS5-60-BI-0019G-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0019G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2279 | Instrument | PS5-60-IE-0003C-CC15 | PS5-60-IE-0002C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2280 | Instrument | PS5-60-IE-0003D-CC15 | PS5-60-IE-0002D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2281 | Instrument | PS5-60-IE-0003E-CC15 | PS5-60-IE-0002E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2282 | Instrument | PS5-60-IE-0003F-CC15 | PS5-60-IE-0002F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2283 | Instrument | PS5-60-IE-0003G-CC15 | PS5-60-IE-0002G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2284 | Instrument | PS5-60-BI-0019A-CC02 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0019A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2285 | Instrument | PS5-60-BI-0019B-CC02 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0019B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2286 | Instrument | PS5-60-BI-0019C-CC02 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0019C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2287 | Instrument | PS5-60-BI-0019D-CC02 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0019D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2288 | Instrument | PS5-60-BI-0019E-CC02 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0019E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2289 | Instrument | PS5-60-BI-0019F-CC02 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0019F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2290 | Instrument | PS5-60-BI-0019G-CC02 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0019G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2291 | Instrument | PS5-60-IE-0003A-CC06 | PS5-60-IE-0002A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2292 | Instrument | PS5-60-IE-0003A-CC16 | PS5-60-IE-0002A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2293 | Instrument | PS5-60-IE-0003A-CC17 | PS5-60-IE-0002A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2294 | Instrument | PS5-60-IE-0003B-CC16 | PS5-60-IE-0002B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2295 | Instrument | PS5-60-IE-0003B-CC17 | PS5-60-IE-0002B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2296 | Instrument | PS5-60-IE-0003C-CC16 | PS5-60-IE-0002C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2297 | Instrument | PS5-60-IE-0003C-CC17 | PS5-60-IE-0002C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2298 | Instrument | PS5-60-IE-0003D-CC16 | PS5-60-IE-0002D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2299 | Instrument | PS5-60-IE-0003D-CC17 | PS5-60-IE-0002D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2300 | Instrument | PS5-60-IE-0003E-CC16 | PS5-60-IE-0002E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2301 | Instrument | PS5-60-IE-0003E-CC17 | PS5-60-IE-0002E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2302 | Instrument | PS5-60-IE-0003F-CC16 | PS5-60-IE-0002F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2303 | Instrument | PS5-60-IE-0003F-CC17 | PS5-60-IE-0002F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2304 | Instrument | PS5-60-IE-0003G-CC03 | PS5-60-IE-0001G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2305 | Instrument | PS5-60-IE-0003G-CC16 | PS5-60-IE-0002G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2306 | Instrument | PS5-60-IE-0003G-CC17 | PS5-60-IE-0002G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2307 | Instrument | PS5-60-BI-0017A-CC02 | PS5-60-IN-0002A |  | Powergen Bldg | PS5-60-BI-0017A |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2308 | Instrument | PS5-60-BI-0017B-CC02 | PS5-60-IN-0002B |  | Powergen Bldg | PS5-60-BI-0017B |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2309 | Instrument | PS5-60-BI-0017C-CC02 | PS5-60-IN-0002C |  | Powergen Bldg | PS5-60-BI-0017C |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2310 | Instrument | PS5-60-BI-0017D-CC02 | PS5-60-IN-0002D |  | Powergen Bldg | PS5-60-BI-0017D |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2311 | Instrument | PS5-60-BI-0017E-CC02 | PS5-60-IN-0002E |  | Powergen Bldg | PS5-60-BI-0017E |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2312 | Instrument | PS5-60-BI-0017F-CC02 | PS5-60-IN-0002F |  | Powergen Bldg | PS5-60-BI-0017F |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2313 | Instrument | PS5-60-BI-0017G-CC02 | PS5-60-IN-0002G |  | Powergen Bldg | PS5-60-BI-0017G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2314 | Instrument | PS5-71-BI-0008A-CC01 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0008A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2315 | Instrument | PS5-71-BI-0008A-CC02 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0008A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2316 | Instrument | PS5-71-BI-0008B-CC01 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0008B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2317 | Instrument | PS5-71-BI-0008B-CC02 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0008B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2318 | Instrument | PS5-60-BI-0002-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-BI-0002 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2319 | Instrument | PS5-60-IE-0003A-CC08 | PS5-60-IE-0002A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2320 | Instrument | PS5-60-IE-0003A-CC09 | PS5-60-IE-0002A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2321 | Instrument | PS5-60-IE-0003A-CC10 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2322 | Instrument | PS5-60-IE-0003A-CC11 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2323 | Instrument | PS5-60-IE-0003B-CC08 | PS5-60-IE-0002B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2324 | Instrument | PS5-60-IE-0003B-CC09 | PS5-60-IE-0002B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2325 | Instrument | PS5-60-IE-0003B-CC10 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2326 | Instrument | PS5-60-IE-0003B-CC11 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2327 | Instrument | PS5-60-IE-0003C-CC08 | PS5-60-IE-0002C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2328 | Instrument | PS5-60-IE-0003C-CC09 | PS5-60-IE-0002C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2329 | Instrument | PS5-60-IE-0003C-CC10 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2330 | Instrument | PS5-60-IE-0003C-CC11 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2331 | Instrument | PS5-60-IE-0003D-CC08 | PS5-60-IE-0002D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2332 | Instrument | PS5-60-IE-0003D-CC09 | PS5-60-IE-0002D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2333 | Instrument | PS5-60-IE-0003D-CC10 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2334 | Instrument | PS5-60-IE-0003D-CC11 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2335 | Instrument | PS5-60-IE-0003E-CC08 | PS5-60-IE-0002E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2336 | Instrument | PS5-60-IE-0003E-CC09 | PS5-60-IE-0002E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2337 | Instrument | PS5-60-IE-0003E-CC10 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2338 | Instrument | PS5-60-IE-0003E-CC11 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2339 | Instrument | PS5-60-IE-0003F-CC08 | PS5-60-IE-0002F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2340 | Instrument | PS5-60-IE-0003F-CC09 | PS5-60-IE-0002F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2341 | Instrument | PS5-60-IE-0003F-CC10 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2342 | Instrument | PS5-60-IE-0003F-CC11 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2343 | Instrument | PS5-60-IE-0003G-CC08 | PS5-60-IE-0002G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2344 | Instrument | PS5-60-IE-0003G-CC09 | PS5-60-IE-0002G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2345 | Instrument | PS5-60-IE-0003G-CC10 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2346 | Instrument | PS5-60-IE-0003G-CC11 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2347 | Instrument | PS5-60-IN-0002A-CC02 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IN-0002A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2348 | Instrument | PS5-60-IN-0002B-CC02 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IN-0002B |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2349 | Instrument | PS5-60-IN-0002C-CC02 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IN-0002C |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2350 | Instrument | PS5-60-IN-0002D-CC02 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IN-0002D |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2351 | Instrument | PS5-60-IN-0002E-CC02 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IN-0002E |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2352 | Instrument | PS5-60-IN-0002F-CC02 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IN-0002F |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2353 | Instrument | PS5-60-IN-0002G-CC02 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IN-0002G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2354 | Instrument | PS5-71-BI-0001A-CC01 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0001A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2355 | Instrument | PS5-71-BI-0001B-CC01 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0001B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2356 | Instrument | PS5-71-BI-0002-CC01 | PS5-71-IN-0001 |  | Powergen Bldg | PS5-71-BI-0002 |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2357 | Instrument | PS5-71-BI-0004-CC01 | PS5-71-IN-0002 |  | Powergen Bldg | PS5-71-BI-0004 |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2358 | Instrument | PS5-71-BI-0005-CC01 | PS5-71-IN-0003 |  | Powergen Bldg | PS5-71-BI-0005 |  | Powergen Building |  |  | 2026-07-21 00:00:00 | 2026-07-21 00:00:00
2359 | Instrument | PS5-71-IN-0002-CC02 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0002 |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2360 | Instrument | PS5-71-IN-0004A-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2361 | Instrument | PS5-71-IN-0004A-CC02 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2362 | Instrument | PS5-71-IN-0004B-CC01 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2363 | Instrument | PS5-71-IN-0004B-CC02 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2364 | Instrument | PS5-60-IE-0003A-CC01 | PS5-60-IE-0001A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2365 | Instrument | PS5-60-IE-0003A-CC02 | PS5-60-IE-0001A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2366 | Instrument | PS5-60-IE-0003B-CC01 | PS5-60-IE-0001B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2367 | Instrument | PS5-60-IE-0003B-CC02 | PS5-60-IE-0001B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2368 | Instrument | PS5-60-IE-0003C-CC01 | PS5-60-IE-0001C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2369 | Instrument | PS5-60-IE-0003C-CC02 | PS5-60-IE-0001C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2370 | Instrument | PS5-60-IE-0003D-CC01 | PS5-60-IE-0001D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2371 | Instrument | PS5-60-IE-0003D-CC02 | PS5-60-IE-0001D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2372 | Instrument | PS5-60-IE-0003E-CC01 | PS5-60-IE-0001E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2373 | Instrument | PS5-60-IE-0003E-CC02 | PS5-60-IE-0001E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2374 | Instrument | PS5-60-IE-0003F-CC01 | PS5-60-IE-0001F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2375 | Instrument | PS5-60-IE-0003F-CC02 | PS5-60-IE-0001F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2376 | Instrument | PS5-60-IE-0003G-CC01 | PS5-60-IE-0001G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2377 | Instrument | PS5-60-IE-0003G-CC02 | PS5-60-IE-0001G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2378 | Instrument | PS5-60-IE-0003A-CC04 | PS5-60-IE-0001A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2379 | Instrument | PS5-60-IE-0003B-CC04 | PS5-60-IE-0001B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2380 | Instrument | PS5-60-IE-0003C-CC04 | PS5-60-IE-0001C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2381 | Instrument | PS5-60-IE-0003D-CC04 | PS5-60-IE-0001D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2382 | Instrument | PS5-60-IE-0003E-CC04 | PS5-60-IE-0001E |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2383 | Instrument | PS5-60-IE-0003F-CC04 | PS5-60-IE-0001F |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2384 | Instrument | PS5-60-IE-0003G-CC04 | PS5-60-IE-0001G |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2385 | Instrument | PS5-60-IE-0003B-CC05 | PS5-60-IE-0001B |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2386 | Instrument | PS5-60-IE-0003C-CC05 | PS5-60-IE-0001C |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2387 | Instrument | PS5-60-IE-0003D-CC05 | PS5-60-IE-0001D |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2388 | Instrument | PS5-60-IE-0003E-CC05 | PS5-60-IE-0001E |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2389 | Instrument | PS5-60-IE-0003F-CC05 | PS5-60-IE-0001F |  | Powergen Bldg | PS5-60-IE-0003G |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2390 | Instrument | PS5-60-IE-0003G-CC05 | PS5-60-IE-0001G |  | Powergen Bldg | PS5-60-IE-0003H |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2391 | Instrument | PS5-60-IE-0003A-CC05 | PS5-60-IE-0001A |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2392 | Instrument | PS5-71-BI-0011A-CC04 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2393 | Instrument | PS5-71-BI-0011B-CC04 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2394 | Instrument | PS5-71-BI-0003-CC02 | PS5-71-IN-0002 |  | Powergen Bldg | PS5-71-BI-0003 |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2395 | Instrument | PS5-71-BI-0003-CC03 | PS5-71-IN-0002 |  | Powergen Bldg | PS5-71-BI-0003 |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2396 | Instrument | PS5-60-BI-0006A-CC04 | PS5-60-IN-0002A |  | Powergen Bldg | PS5-60-BI-0006A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2397 | Instrument | PS5-60-BI-0006B-CC04 | PS5-60-IN-0002B |  | Powergen Bldg | PS5-60-BI-0006B |  | Powergen Building |  |  | 2026-08-04 00:00:00 | 2026-08-04 00:00:00
2398 | Instrument | PS5-60-BI-0006C-CC04 | PS5-60-IN-0002C |  | Powergen Bldg | PS5-60-BI-0006C |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2399 | Instrument | PS5-60-BI-0006D-CC04 | PS5-60-IN-0002D |  | Powergen Bldg | PS5-60-BI-0006D |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2400 | Instrument | PS5-60-BI-0006E-CC04 | PS5-60-IN-0002E |  | Powergen Bldg | PS5-60-BI-0006E |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2401 | Instrument | PS5-60-BI-0006F-CC04 | PS5-60-IN-0002F |  | Powergen Bldg | PS5-60-BI-0006F |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2402 | Instrument | PS5-60-BI-0006G-CC04 | PS5-60-IN-0002G |  | Powergen Bldg | PS5-60-BI-0006G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2403 | Instrument | PS5-60-BI-0016A-CCO4 | PS5-60-IE-0001A |  | Powergen Bldg | PS5-60-BI-0016A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2404 | Instrument | PS5-60-BI-0016B-CCO4 | PS5-60-IE-0001B |  | Powergen Bldg | PS5-60-BI-0016B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2405 | Instrument | PS5-60-BI-0016C-CCO4 | PS5-60-IE-0001C |  | Powergen Bldg | PS5-60-BI-0016C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2406 | Instrument | PS5-60-BI-0016D-CCO4 | PS5-60-IE-0001D |  | Powergen Bldg | PS5-60-BI-0016D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2407 | Instrument | PS5-60-BI-0016E-CCO4 | PS5-60-IE-0001E |  | Powergen Bldg | PS5-60-BI-0016E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2408 | Instrument | PS5-60-BI-0016F-CCO4 | PS5-60-IE-0001F |  | Powergen Bldg | PS5-60-BI-0016F |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2409 | Instrument | PS5-60-BI-0016G-CCO4 | PS5-60-IE-0001G |  | Powergen Bldg | PS5-60-BI-0016G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2410 | Instrument | PS5-60-BI-0008A-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0008A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2411 | Instrument | PS5-60-BI-0008B-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0008B |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2412 | Instrument | PS5-60-BI-0009A-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0009A |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2413 | Instrument | PS5-60-BI-0009B-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0009B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2414 | Instrument | PS5-60-BI-0010A-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0010A |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2415 | Instrument | PS5-60-BI-0010B-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0010B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2416 | Instrument | PS5-60-BI-0011A-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0011A |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2417 | Instrument | PS5-60-BI-0011B-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0011B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2418 | Instrument | PS5-60-BI-0012A-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0012A |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2419 | Instrument | PS5-60-BI-0012B-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0012B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2420 | Instrument | PS5-60-BI-0013A-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0013A |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2421 | Instrument | PS5-60-BI-0013B-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0013B |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2422 | Instrument | PS5-60-BI-0014A-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0014A |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2423 | Instrument | PS5-60-BI-0014B-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0014B |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2424 | Instrument | PS5-60-BI-0016A-CC02 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-BI-0016A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2425 | Instrument | PS5-60-BI-0016B-CC02 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-BI-0016B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2426 | Instrument | PS5-60-BI-0016C-CC02 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-BI-0016C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2427 | Instrument | PS5-60-BI-0016D-CC02 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-BI-0016D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2428 | Instrument | PS5-60-BI-0016E-CC02 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-BI-0016E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2429 | Instrument | PS5-60-BI-0016F-CC02 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-BI-0016F |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2430 | Instrument | PS5-60-BI-0016G-CC02 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-BI-0016G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2431 | Instrument | PS5-60-BI-0004A-CCO1 | PS5-60-IE-0001A |  | Powergen Bldg | PS5-60-BI-0004A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2432 | Instrument | PS5-60-BI-0004B-CCO1 | PS5-60-IE-0001B |  | Powergen Bldg | PS5-60-BI-0004B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2433 | Instrument | PS5-60-BI-0004C-CCO1 | PS5-60-IE-0001C |  | Powergen Bldg | PS5-60-BI-0004C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2434 | Instrument | PS5-60-BI-0004D-CCO1 | PS5-60-IE-0001D |  | Powergen Bldg | PS5-60-BI-0004D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2435 | Instrument | PS5-60-BI-0004E-CCO1 | PS5-60-IE-0001E |  | Powergen Bldg | PS5-60-BI-0004E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2436 | Instrument | PS5-60-BI-0004F-CCO1 | PS5-60-IE-0001F |  | Powergen Bldg | PS5-60-BI-0004F |  | Powergen Building |  |  | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2437 | Instrument | PS5-60-BI-0004G-CCO1 | PS5-60-IE-0001G |  | Powergen Bldg | PS5-60-BI-0004G |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2438 | Instrument | PS5-71-BI-0009-CC01 | PS5-71-IN-0001 |  | Powergen Bldg | PS5-71-BI-0009 |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2439 | Instrument | PS5-71-BI-0011A-CC01 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2440 | Instrument | PS5-71-BI-0011A-CC02 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2441 | Instrument | PS5-71-BI-0011A-CC05 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2442 | Instrument | PS5-71-BI-0011B-CC01 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2443 | Instrument | PS5-71-BI-0011B-CC02 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2444 | Instrument | PS5-71-BI-0011B-CC05 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-BI-0011B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2445 | Instrument | PS5-03-GDIR-0901-CC01 | PS5-03-GDIR-0901 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2446 | Instrument | PS5-03-GDIR-0902-CC01 | PS5-03-GDIR-0902 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2447 | Instrument | PS5-03-GDIR-0903-CC01 | PS5-03-GDIR-0903 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2448 | Instrument | PS5-03-GDIR-0904-CC01 | PS5-03-GDIR-0904 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2449 | Instrument | PS5-03-GDIR-0906-CC01 | PS5-03-GDIR-0906 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0081 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2450 | Instrument | PS5-03-GDIR-0907-CC01 | PS5-03-GDIR-0907 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2451 | Instrument | PS5-03-GDIR-0908-CC01 | PS5-03-GDIR-0908 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2452 | Instrument | PS5-03-GDIR-0909-CC01 | PS5-03-GDIR-0909 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2453 | Instrument | PS5-03-GDIR-1001-CC01 | PS5-03-GDIR-1001 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2454 | Instrument | PS5-03-GDIR-1002-CC01 | PS5-03-GDIR-1002 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2455 | Instrument | PS5-03-GDIR-1003-CC01 | PS5-03-GDIR-1003 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2456 | Instrument | PS5-03-GDIR-1004-CC01 | PS5-03-GDIR-1004 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2457 | Instrument | PS5-03-GDIR-1006-CC01 | PS5-03-GDIR-1006 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2458 | Instrument | PS5-03-GDIR-1007-CC01 | PS5-03-GDIR-1007 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2459 | Instrument | PS5-03-GDIR-1008-CC01 | PS5-03-GDIR-1008 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2460 | Instrument | PS5-03-GDIR-1009-CC01 | PS5-03-GDIR-1009 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2461 | Instrument | PS5-03-GDIR-1101-CC01 | PS5-03-GDIR-1101 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2462 | Instrument | PS5-03-GDIR-1102-CC01 | PS5-03-GDIR-1102 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2463 | Instrument | PS5-03-GDIR-1103-CC01 | PS5-03-GDIR-1103 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2464 | Instrument | PS5-03-GDIR-1104-CC01 | PS5-03-GDIR-1104 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2465 | Instrument | PS5-03-GDIR-1106-CC01 | PS5-03-GDIR-1106 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2466 | Instrument | PS5-03-GDIR-1107-CC01 | PS5-03-GDIR-1107 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2467 | Instrument | PS5-03-GDIR-1108-CC01 | PS5-03-GDIR-1108 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2468 | Instrument | PS5-03-GDIR-1109-CC01 | PS5-03-GDIR-1109 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2469 | Instrument | PS5-03-GDIR-1201-CC01 | PS5-03-GDIR-1201 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2470 | Instrument | PS5-03-GDIR-1202-CC01 | PS5-03-GDIR-1202 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2471 | Instrument | PS5-03-GDIR-1203-CC01 | PS5-03-GDIR-1203 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2472 | Instrument | PS5-03-GDIR-1204-CC01 | PS5-03-GDIR-1204 |  | Powergen Bldg | PS5-60-SEA-0001 |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2473 | Instrument | PS5-60-IE-0003B-CA02 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IE-0003B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2474 | Instrument | PS5-60-IE-0003C-CA02 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IE-0003C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2475 | Instrument | PS5-60-IE-0003D-CA02 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IE-0003D |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2476 | Instrument | PS5-60-IE-0003E-CA02 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IE-0003E |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2477 | Instrument | PS5-60-IE-0003F-CA02 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IE-0003F |  | Powergen Building |  |  | 2026-08-01 00:00:00 | 2026-08-01 00:00:00
2478 | Instrument | PS5-60-IE-0004-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2479 | Instrument | PS5-60-IE-0004-CC02 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2480 | Instrument | PS5-60-IE-0004-CC03 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2481 | Instrument | PS5-60-IE-0004-CC04 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2482 | Instrument | PS5-60-IE-0004-CC05 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2483 | Instrument | PS5-60-IE-0004-CC06 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2484 | Instrument | PS5-71-IN-0001-CA11 | PS5-71-IN-0001 |  | Powergen Bldg | PS5-60-IE-0003A |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2485 | Instrument | PS5-71-IN-0004A-CC11 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2486 | Instrument | PS5-71-IN-0004A-CC13 | PS5-71-IN-0004A |  | Powergen Bldg | PS5-71-IN-0004B |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2487 | Instrument | PS5-71-IN-0004B-CC11 | PS5-71-IN-0004B |  | Powergen Bldg | PS5-71-IN-0001 |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2488 | Instrument | PS5-60-IE-0004-CC07 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IE-0004 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2489 | Instrument | PS5-71-IN-0004A-CC10 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-71-IN-0004A |  | Powergen Building |  |  | 2026-09-15 00:00:00 | 2026-09-15 00:00:00
2490 | Instrument | PS5-60-BI-0008A-CC02 | PS5-60-IH-0001A |  | Powergen Bldg | PS5-60-BI-0008A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2491 | Instrument | PS5-60-BI-0008B-CC02 | PS5-60-IH-0001A |  | Powergen Bldg | PS5-60-BI-0008B |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2492 | Instrument | PS5-60-BI-0009A-CC02 | PS5-60-IH-0001B |  | Powergen Bldg | PS5-60-BI-0009A |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2493 | Instrument | PS5-60-BI-0009B-CC02 | PS5-60-IH-0001B |  | Powergen Bldg | PS5-60-BI-0009B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2494 | Instrument | PS5-60-BI-0010A-CC02 | PS5-60-IH-0001C |  | Powergen Bldg | PS5-60-BI-0010A |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2495 | Instrument | PS5-60-BI-0010B-CC02 | PS5-60-IH-0001C |  | Powergen Bldg | PS5-60-BI-0010B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2496 | Instrument | PS5-60-BI-0011A-CC02 | PS5-60-IH-0001D |  | Powergen Bldg | PS5-60-BI-0011A |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2497 | Instrument | PS5-60-BI-0011B-CC02 | PS5-60-IH-0001D |  | Powergen Bldg | PS5-60-BI-0011B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2498 | Instrument | PS5-60-BI-0012A-CC02 | PS5-60-IH-0001E |  | Powergen Bldg | PS5-60-BI-0012A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2499 | Instrument | PS5-60-BI-0012B-CC02 | PS5-60-IH-0001E |  | Powergen Bldg | PS5-60-BI-0012B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2500 | Instrument | PS5-60-BI-0013A-CC02 | PS5-60-IH-0001F |  | Powergen Bldg | PS5-60-BI-0013A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2501 | Instrument | PS5-60-BI-0013B-CC02 | PS5-60-IH-0001F |  | Powergen Bldg | PS5-60-BI-0013B |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2502 | Instrument | PS5-60-BI-0014A-CC02 | PS5-60-IH-0001G |  | Powergen Bldg | PS5-60-BI-0014A |  | Powergen Building | 2026-07-04 00:00:00 | CPP-68-64-04-0079 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2503 | Instrument | PS5-60-BI-0014B-CC02 | PS5-60-IH-0001G |  | Powergen Bldg | PS5-60-BI-0014B |  | Powergen Building |  |  | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2504 | Instrument | PS5-61-BI-0001-CC01 | PS5-60-IE-0003A |  | Powergen Bldg | PS5-61-BI-0001 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2505 | Instrument | PS5-61-BI-0002-CC01 | PS5-60-IE-0003B |  | Powergen Bldg | PS5-61-BI-0002 |  | Powergen Building | 2026-04-24 00:00:00 | CPP-RFI-68-64-04-0054 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2506 | Instrument | PS5-61-BI-0003-CC01 | PS5-60-IE-0003C |  | Powergen Bldg | PS5-61-BI-0003 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2507 | Instrument | PS5-61-BI-0004-CC01 | PS5-60-IE-0003D |  | Powergen Bldg | PS5-61-BI-0004 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2508 | Instrument | PS5-61-BI-0005-CC01 | PS5-60-IE-0003E |  | Powergen Bldg | PS5-61-BI-0005 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2509 | Instrument | PS5-61-BI-0006-CC01 | PS5-60-IE-0003F |  | Powergen Bldg | PS5-61-BI-0006 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-08-21 00:00:00 | 2026-08-21 00:00:00
2510 | Instrument | PS5-61-BI-0007-CC01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-61-BI-0007 |  | Powergen Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0050 | 2026-08-30 00:00:00 | 2026-08-30 00:00:00
2511 | Instrument | PS5-60-IH-0001A-CA01 | PS5-60-IE-0003G |  | Powergen Bldg | PS5-60-IH-0001A |  | Powergen Building |  |  | 2026-07-17 00:00:00 | 2026-07-17 00:00:00
2512 | Instrument | PS5-60-IH-0001B-CA01 | PS5-60-IE-0001B |  | Powergen Bldg | PS5-60-IH-0001B |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2513 | Instrument | PS5-60-IH-0001C-CA01 | PS5-60-IE-0001C |  | Powergen Bldg | PS5-60-IH-0001C |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2514 | Instrument | PS5-60-IH-0001D-CA01 | PS5-60-IE-0001D |  | Powergen Bldg | PS5-60-IH-0001D |  | Powergen Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
2515 | Instrument | PS5-60-IH-0001E-CA01 | PS5-60-IE-0001E |  | Powergen Bldg | PS5-60-IH-0001E |  | Powergen Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
2516 | Instrument | PS5-60-IH-0001F-CA01 | PS5-60-IE-0001F |  | Powergen Bldg | PS5-60-IH-0001F |  | Powergen Building |  |  | 2026-07-15 00:00:00 | 2026-07-15 00:00:00
2517 | Instrument | PS5-60-IH-0001G-CA01 | PS5-60-IE-0001G |  | Powergen Bldg | PS5-60-IH-0001G |  | Powergen Building |  |  | 2026-08-15 00:00:00 | 2026-08-15 00:00:00
2518 | Instrument | PS5-60-LA-0003-CC02 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-LA-0003 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2519 | Instrument | PS5-60-LA-0003-CC03 | PS5-60-IE-0004 |  | Powergen Bldg | PS5-60-LA-0003 |  | Powergen Building |  |  | 2026-07-30 00:00:00 | 2026-07-30 00:00:00
2520 | Instrument | PS5-75-LA-6200-CX01 | PS5-75-LA-6200 |  | Skid | PS5-04-PNC-0001 |  | 33kV EITS Building | 2026-05-20 00:00:00 | CPP-RFI-68-64-04-0049 | 2026-10-15 00:00:00 | 2026-10-15 00:00:00
2521 | Telecom | PS5-08-01MP-0001-CC01 | PS5-08-13CB-1001 | SII SP3 SAF CABINET | EITS BLDG | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2522 | Telecom | PS5-08-01MP-0001-CC02 | PS5-08-13CB-1001 | SII SP3 SAF CABINET | EITS BLDG | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2523 | Telecom | PS5-08-01MP-0001-CC03 | PS5-08-13CB-1001 | SII SP3 SAF CABINET | EITS BLDG | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2524 | Telecom | PS5-08-01MP-0001-CC04 | PS5-08-13CB-1001 | SII SP3 SAF CABINET | EITS BLDG | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2525 | Telecom | PS5-08-01LS-0101-CR01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | EITS BLDG | PS5-08-01LS-0101 | PAGA LOUDSPEAKER | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2526 | Telecom | PS5-08-01LS-0102-CR01 | PS5-08-01LS-0101 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0102 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2527 | Telecom | PS5-08-01BT-0003-CR01 | PS5-08-01LS-0102 | PAGA LOUDSPEAKER | FIELD | PS5-08-01BT-0003 | PAGA JUNCTION BOX | SECONDARY MUSTER AREA
2528 | Telecom | PS5-08-01BT-0003-CR02 | PS5-08-01OC-0002 | OVERRIDE CONTROL UNIT | SECONDARY MUSTER AREA | PS5-08-01BT-0003 | PAGA JUNCTION BOX | SECONDARY MUSTER AREA
2529 | Telecom | PS5-08-01LS-0103-CR01 | PS5-08-01OC-0002 | OVERRIDE CONTROL UNIT | SECONDARY MUSTER AREA | PS5-08-01LS-0103 | PAGA LOUDSPEAKER | FIELD
2530 | Telecom | PS5-08-01LS-0104-CR01 | PS5-08-01BT-0003 | PAGA JUNCTION BOX | SECONDARY MUSTER AREA | PS5-08-01LS-0104 | PAGA LOUDSPEAKER | FIELD
2531 | Telecom | PS5-08-01LS-0105-CR01 | PS5-08-01LS-0104 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0105 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2532 | Telecom | PS5-08-01LS-0106-CR01 | PS5-08-01LS-0105 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0106 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2533 | Telecom | PS5-08-01LS-0107-CR01 | PS5-08-01LS-0106 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0107 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2534 | Telecom | PS5-08-01LS-0108-CR01 | PS5-08-01LS-0107 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0108 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2535 | Telecom | PS5-08-01LS-0109-CR01 | PS5-08-01LS-0108 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0109 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2536 | Telecom | PS5-08-01LS-0110-CR01 | PS5-08-01LS-0109 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0110 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2537 | Telecom | PS5-08-01LS-0110-CR02 | PS5-08-01LS-0110 | PAGA LOUDSPEAKER | FIELD | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2538 | Telecom | PS5-08-01LS-0201-CR01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01LS-0201 | PAGA LOUDSPEAKER | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2539 | Telecom | PS5-08-01BT-0004-CR01 | PS5-08-01LS-0201 | PAGA LOUDSPEAKER | FIELD | PS5-08-01BT-0004 | PAGA JUNCTION BOX | SECONDARY MUSTER AREA
2540 | Telecom | PS5-08-01BT-0004-CR02 | PS5-08-01OC-0002 | OVERRIDE CONTROL UNIT | SECONDARY MUSTER AREA | PS5-08-01BT-0004 | PAGA JUNCTION BOX | SECONDARY MUSTER AREA
2541 | Telecom | PS5-08-01LS-0202-CR01 | PS5-08-01OC-0002 | OVERRIDE CONTROL UNIT | SECONDARY MUSTER AREA | PS5-08-01LS-0202 | PAGA LOUDSPEAKER | FIELD
2542 | Telecom | PS5-08-01LS-0203-CR01 | PS5-08-01BT-0004 | PAGA JUNCTION BOX | SECONDARY MUSTER AREA | PS5-08-01LS-0203 | PAGA LOUDSPEAKER | FIELD
2543 | Telecom | PS5-08-01LS-0204-CR01 | PS5-08-01LS-0203 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0204 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2544 | Telecom | PS5-08-01LS-0205-CR01 | PS5-08-01LS-0204 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0205 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2545 | Telecom | PS5-08-01LS-0206-CR01 | PS5-08-01LS-0205 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0206 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2546 | Telecom | PS5-08-01LS-0207-CR01 | PS5-08-01LS-0206 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0207 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2547 | Telecom | PS5-08-01LS-0208-CR01 | PS5-08-01LS-0207 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0208 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2548 | Telecom | PS5-08-01LS-0209-CR01 | PS5-08-01LS-0208 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0209 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2549 | Telecom | PS5-08-01LS-0210-CR01 | PS5-08-01LS-0209 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0210 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2550 | Telecom | PS5-08-01LS-0211-CR01 | PS5-08-01LS-0210 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0211 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2551 | Telecom | PS5-08-01LS-0211-CR02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01LS-0211 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2552 | Telecom | PS5-08-01LS-0301-CR01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01LS-0301 | PAGA LOUDSPEAKER (EX) | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2553 | Telecom | PS5-08-01LS-0302-CR01 | PS5-08-01LS-0301 | PAGA LOUDSPEAKER (EX) | FIELD | PS5-08-01LS-0302 | PAGA LOUDSPEAKER (EX) | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2554 | Telecom | PS5-08-01LS-0303-CR01 | PS5-08-01LS-0302 | PAGA LOUDSPEAKER (EX) | FIELD | PS5-08-01LS-0303 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2555 | Telecom | PS5-08-01LS-0304-CR01 | PS5-08-01LS-0303 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0304 | PAGA LOUDSPEAKER | FIELD
2556 | Telecom | PS5-08-01LS-0305-CR01 | PS5-08-01LS-0304 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0305 | PAGA LOUDSPEAKER | FIELD
2557 | Telecom | PS5-08-01LS-0306-CR01 | PS5-08-01LS-0305 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0306 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2558 | Telecom | PS5-08-01LS-0307-CR01 | PS5-08-01LS-0306 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0307 | PAGA LOUDSPEAKER | FIELD | 2026-07-01 00:00:00 | CPP-RFI-68-65-05-0034
2559 | Telecom | PS5-08-01BT-1501-CR01 | PS5-08-01LS-0307 | PAGA LOUDSPEAKER | FIELD | PS5-08-01BT-1501 | PAGA JUNCTION BOX | GUARD HOUSE
2560 | Telecom | PS5-08-01LS-0308-CR01 | PS5-08-01BT-1501 | PAGA JUNCTION BOX | GUARD HOUSE | PS5-08-01LS-0308 | PAGA LOUDSPEAKER | GUARD HOUSE
2561 | Telecom | PS5-08-01LS-0309-CR01 | PS5-08-01LS-0308 | PAGA LOUDSPEAKER | GUARD HOUSE | PS5-08-01LS-0309 | PAGA LOUDSPEAKER | GUARD HOUSE
2562 | Telecom | PS5-08-01LS-0309-CR02 | PS5-08-01BT-1501 | PAGA JUNCTION BOX | GUARD HOUSE | PS5-08-01LS-0309 | PAGA LOUDSPEAKER | GUARD HOUSE
2563 | Telecom | PS5-08-01LS-0310-CR01 | PS5-08-01BT-1501 | PAGA JUNCTION BOX | GUARD HOUSE | PS5-08-01LS-0310 | PAGA LOUDSPEAKER | FIELD
2564 | Telecom | PS5-08-01LS-0310-CR02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01LS-0310 | PAGA LOUDSPEAKER | FIELD
2565 | Telecom | PS5-08-01LS-0401-CR01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01LS-0401 | PAGA LOUDSPEAKER (EX) | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2566 | Telecom | PS5-08-01LS-0402-CR01 | PS5-08-01LS-0401 | PAGA LOUDSPEAKER (EX) | FIELD | PS5-08-01LS-0402 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2567 | Telecom | PS5-08-01LS-0403-CR01 | PS5-08-01LS-0402 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0403 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2568 | Telecom | PS5-08-01LS-0404-CR01 | PS5-08-01LS-0403 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0404 | PAGA LOUDSPEAKER | FIELD | 2026-07-01 00:00:00 | CPP-RFI-68-65-05-0034
2569 | Telecom | PS5-08-01LS-0405-CR01 | PS5-08-01LS-0404 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0405 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2570 | Telecom | PS5-08-01BT-1502-CR01 | PS5-08-01LS-0405 | PAGA LOUDSPEAKER | FIELD | PS5-08-01BT-1502 | PAGA JUNCTION BOX | GUARD HOUSE
2571 | Telecom | PS5-08-01LS-0406-CR01 | PS5-08-01BT-1502 | PAGA JUNCTION BOX | GUARD HOUSE | PS5-08-01LS-0406 | PAGA LOUDSPEAKER | GUARD HOUSE
2572 | Telecom | PS5-08-01LS-0407-CR01 | PS5-08-01LS-0406 | PAGA LOUDSPEAKER | GUARD HOUSE | PS5-08-01LS-0407 | PAGA LOUDSPEAKER | GUARD HOUSE
2573 | Telecom | PS5-08-01LS-0408-CR01 | PS5-08-01LS-0407 | PAGA LOUDSPEAKER | GUARD HOUSE | PS5-08-01LS-0408 | PAGA LOUDSPEAKER | GUARD HOUSE
2574 | Telecom | PS5-08-01LS-0408-CR02 | PS5-08-01BT-1502 | PAGA JUNCTION BOX | GUARD HOUSE | PS5-08-01LS-0408 | PAGA LOUDSPEAKER | GUARD HOUSE
2575 | Telecom | PS5-08-01LS-0409-CR01 | PS5-08-01BT-1502 | PAGA JUNCTION BOX | GUARD HOUSE | PS5-08-01LS-0409 | PAGA LOUDSPEAKER | FIELD
2576 | Telecom | PS5-08-01LS-0410-CR01 | PS5-08-01LS-0409 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0410 | PAGA LOUDSPEAKER | FIELD
2577 | Telecom | PS5-08-01LS-0411-CR01 | PS5-08-01LS-0410 | PAGA LOUDSPEAKER | FIELD | PS5-08-01LS-0411 | PAGA LOUDSPEAKER | FIELD
2578 | Telecom | PS5-08-01LS-0411-CR02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01LS-0411 | PAGA LOUDSPEAKER | FIELD | 2026-04-12 00:00:00 | CPP-RFI-68-65-05-0024
2579 | Telecom | PS5-08-01BT-1903-CR01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1903 | PAGA JUNCTION BOX | POWER GEN BLDG | 06-July-2026 | CPP-RFI-68-65-05-0036
2580 | Telecom | PS5-08-01LS-0501-CR01 | PS5-08-01BT-1903 | PAGA JUNCTION BOX | POWER GEN BLDG | PS5-08-01LS-0501 | PAGA LOUDSPEAKER | POWER GEN BLDG
2581 | Telecom | PS5-08-01LS-0502-CR01 | PS5-08-01LS-0501 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0502 | PAGA LOUDSPEAKER | POWER GEN BLDG
2582 | Telecom | PS5-08-01LS-0503-CR01 | PS5-08-01LS-0502 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0503 | PAGA LOUDSPEAKER | POWER GEN BLDG
2583 | Telecom | PS5-08-01LS-0504-CR01 | PS5-08-01LS-0503 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0504 | PAGA LOUDSPEAKER | POWER GEN BLDG
2584 | Telecom | PS5-08-01LS-0505-CR01 | PS5-08-01LS-0504 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0505 | PAGA LOUDSPEAKER | POWER GEN BLDG
2585 | Telecom | PS5-08-01LS-0506-CR01 | PS5-08-01LS-0505 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0506 | PAGA LOUDSPEAKER | POWER GEN BLDG
2586 | Telecom | PS5-08-01LS-0507-CR01 | PS5-08-01LS-0506 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0507 | PAGA LOUDSPEAKER | POWER GEN BLDG
2587 | Telecom | PS5-08-01LS-0508-CR01 | PS5-08-01LS-0507 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0508 | PAGA LOUDSPEAKER | POWER GEN BLDG
2588 | Telecom | PS5-08-01LS-0509-CR01 | PS5-08-01LS-0508 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0509 | PAGA LOUDSPEAKER | POWER GEN BLDG
2589 | Telecom | PS5-08-01LS-0510-CR01 | PS5-08-01LS-0509 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0510 | PAGA LOUDSPEAKER | POWER GEN BLDG
2590 | Telecom | PS5-08-01LS-0511-CR01 | PS5-08-01LS-0510 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0511 | PAGA LOUDSPEAKER | POWER GEN BLDG
2591 | Telecom | PS5-08-01LS-0512-CR01 | PS5-08-01LS-0511 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0512 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG
2592 | Telecom | PS5-08-01LS-0517-CR01 | PS5-08-01LS-0512 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG | PS5-08-01LS-0517 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG
2593 | Telecom | PS5-08-01LS-0518-CR01 | PS5-08-01LS-0517 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG | PS5-08-01LS-0518 | PAGA LOUDSPEAKER | POWER GEN BLDG
2594 | Telecom | PS5-08-01LS-0519-CR01 | PS5-08-01LS-0518 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0519 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG
2595 | Telecom | PS5-08-01LS-0520-CR01 | PS5-08-01LS-0519 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG | PS5-08-01LS-0520 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG
2596 | Telecom | PS5-08-01LS-0521-CR01 | PS5-08-01LS-0520 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG | PS5-08-01LS-0521 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG
2597 | Telecom | PS5-08-01LS-0522-CR01 | PS5-08-01LS-0521 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG | PS5-08-01LS-0522 | PAGA LOUDSPEAKER | POWER GEN BLDG
2598 | Telecom | PS5-08-01LS-0522-CR02 | PS5-08-01BT-1903 | PAGA JUNCTION BOX | POWER GEN BLDG | PS5-08-01LS-0522 | PAGA LOUDSPEAKER | POWER GEN BLDG
2599 | Telecom | PS5-08-01BT-1901-CR01 | PS5-08-01BT-1903 | PAGA JUNCTION BOX | POWER GEN BLDG | PS5-08-01BT-1901 | PAGA JUNCTION BOX | GEN. ELECT. BLDG
2600 | Telecom | PS5-08-01LS-0523-CR01 | PS5-08-01BT-1901 | PAGA JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-01LS-0523 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2601 | Telecom | PS5-08-01LS-0524-CR01 | PS5-08-01LS-0523 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0524 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2602 | Telecom | PS5-08-01LS-0525-CR01 | PS5-08-01LS-0524 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0525 | PAGA LOUDSPEAKER (EX) | GEN. ELECT. BLDG
2603 | Telecom | PS5-08-01LS-0526-CR01 | PS5-08-01LS-0525 | PAGA LOUDSPEAKER (EX) | GEN. ELECT. BLDG | PS5-08-01LS-0526 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2604 | Telecom | PS5-08-01LS-0527-CR01 | PS5-08-01LS-0526 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0527 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2605 | Telecom | PS5-08-01LS-0528-CR01 | PS5-08-01LS-0527 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0528 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2606 | Telecom | PS5-08-01LS-0529-CR01 | PS5-08-01LS-0528 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0529 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2607 | Telecom | PS5-08-01LS-0530-CR01 | PS5-08-01LS-0529 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0530 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2608 | Telecom | PS5-08-01LS-0530-CR02 | PS5-08-01BT-1901 | PAGA JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-01LS-0530 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2609 | Telecom | PS5-08-01BT-1901-CR02 | PS5-08-01BT-1901 | PAGA JUNCTION BOX | POWER GEN BLDG | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | 2026-07-01 00:00:00 | CPP-RFI-68-65-05-0034
2610 | Telecom | PS5-08-01BT-1904-CR01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1904 | PAGA JUNCTION BOX | POWER GEN BLDG | 06-July-2026 | CPP-RFI-68-65-05-0036
2611 | Telecom | PS5-08-01LS-0601-CR01 | PS5-08-01BT-1904 | PAGA JUNCTION BOX | POWER GEN BLDG | PS5-08-01LS-0601 | PAGA LOUDSPEAKER | POWER GEN BLDG
2612 | Telecom | PS5-08-01LS-0602-CR01 | PS5-08-01LS-0601 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0602 | PAGA LOUDSPEAKER | POWER GEN BLDG
2613 | Telecom | PS5-08-01LS-0603-CR01 | PS5-08-01LS-0602 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0603 | PAGA LOUDSPEAKER | POWER GEN BLDG
2614 | Telecom | PS5-08-01LS-0604-CR01 | PS5-08-01LS-0603 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0604 | PAGA LOUDSPEAKER | POWER GEN BLDG
2615 | Telecom | PS5-08-01LS-0605-CR01 | PS5-08-01LS-0604 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0605 | PAGA LOUDSPEAKER | POWER GEN BLDG
2616 | Telecom | PS5-08-01LS-0606-CR01 | PS5-08-01LS-0605 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0606 | PAGA LOUDSPEAKER | POWER GEN BLDG
2617 | Telecom | PS5-08-01LS-0607-CR01 | PS5-08-01LS-0606 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0607 | PAGA LOUDSPEAKER | POWER GEN BLDG
2618 | Telecom | PS5-08-01LS-0608-CR01 | PS5-08-01LS-0607 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0608 | PAGA LOUDSPEAKER | POWER GEN BLDG
2619 | Telecom | PS5-08-01LS-0609-CR01 | PS5-08-01LS-0608 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0609 | PAGA LOUDSPEAKER | POWER GEN BLDG
2620 | Telecom | PS5-08-01LS-0610-CR01 | PS5-08-01LS-0609 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0610 | PAGA LOUDSPEAKER | POWER GEN BLDG
2621 | Telecom | PS5-08-01LS-0611-CR01 | PS5-08-01LS-0610 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0611 | PAGA LOUDSPEAKER | POWER GEN BLDG
2622 | Telecom | PS5-08-01LS-0612-CR01 | PS5-08-01LS-0611 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0612 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG
2623 | Telecom | PS5-08-01LS-0617-CR01 | PS5-08-01LS-0612 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG | PS5-08-01LS-0617 | PAGA LOUDSPEAKER | POWER GEN BLDG
2624 | Telecom | PS5-08-01LS-0618-CR01 | PS5-08-01LS-0617 | PAGA LOUDSPEAKER | POWER GEN BLDG | PS5-08-01LS-0618 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG
2625 | Telecom | PS5-08-01LS-0619-CR01 | PS5-08-01LS-0618 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG | PS5-08-01LS-0619 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG
2626 | Telecom | PS5-08-01LS-0620-CR01 | PS5-08-01LS-0619 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG | PS5-08-01LS-0620 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG
2627 | Telecom | PS5-08-01LS-0621-CR01 | PS5-08-01LS-0620 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG | PS5-08-01LS-0621 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG
2628 | Telecom | PS5-08-01LS-0621-CR02 | PS5-08-01LS-0621 | PAGA LOUDSPEAKER (EX) | POWER GEN BLDG | PS5-08-01BT-1904 | PAGA JUNCTION BOX | POWER GEN BLDG
2629 | Telecom | PS5-08-01BT-1902-CR01 | PS5-08-01BT-1904 | PAGA JUNCTION BOX | POWER GEN BLDG | PS5-08-01BT-1902 | PAGA JUNCTION BOX | GEN. ELECT. BLDG
2630 | Telecom | PS5-08-01BT-1902-CR02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1902 | PAGA JUNCTION BOX | GEN. ELECT. BLDG | 06-July-2026 | CPP-RFI-68-65-05-0036
2631 | Telecom | PS5-08-01LS-0622-CR01 | PS5-08-01BT-1902 | PAGA JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-01LS-0622 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2632 | Telecom | PS5-08-01LS-0623-CR01 | PS5-08-01LS-0622 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0623 | PAGA LOUDSPEAKER (EX) | GEN. ELECT. BLDG
2633 | Telecom | PS5-08-01LS-0624-CR01 | PS5-08-01LS-0623 | PAGA LOUDSPEAKER (EX) | GEN. ELECT. BLDG | PS5-08-01LS-0624 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2634 | Telecom | PS5-08-01LS-0625-CR01 | PS5-08-01LS-0624 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0625 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2635 | Telecom | PS5-08-01LS-0626-CR01 | PS5-08-01LS-0625 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0626 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2636 | Telecom | PS5-08-01LS-0627-CR01 | PS5-08-01LS-0626 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0627 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2637 | Telecom | PS5-08-01LS-0628-CR01 | PS5-08-01LS-0627 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0628 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2638 | Telecom | PS5-08-01LS-0629-CR01 | PS5-08-01LS-0628 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG | PS5-08-01LS-0629 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2639 | Telecom | PS5-08-01LS-0629-CR02 | PS5-08-01BT-1902 | PAGA JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-01LS-0629 | PAGA LOUDSPEAKER | GEN. ELECT. BLDG
2640 | Telecom | PS5-08-01BT-1201-CR01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1201 | PAGA JUNCTION BOX | OFFICE BLDG
2641 | Telecom | PS5-08-01BT-1201-CR02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1201 | PAGA JUNCTION BOX | OFFICE BLDG
2642 | Telecom | PS5-08-01LS-0701-CR01 | PS5-08-01BT-1201 | PAGA JUNCTION BOX | OFFICE BLDG | PS5-08-01LS-0701 | PAGA LOUDSPEAKER | OFFICE BLDG
2643 | Telecom | PS5-08-01LS-0702-CR01 | PS5-08-01LS-0701 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0702 | PAGA LOUDSPEAKER | OFFICE BLDG
2644 | Telecom | PS5-08-01LS-0704-CR01 | PS5-08-01LS-0702 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0704 | PAGA LOUDSPEAKER | OFFICE BLDG
2645 | Telecom | PS5-08-01LS-0703-CR01 | PS5-08-01LS-0704 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0703 | PAGA LOUDSPEAKER | OFFICE BLDG
2646 | Telecom | PS5-08-01LS-0705-CR01 | PS5-08-01BT-1201 | PAGA JUNCTION BOX | OFFICE BLDG | PS5-08-01LS-0705 | PAGA LOUDSPEAKER | OFFICE BLDG
2647 | Telecom | PS5-08-01LS-0706-CR01 | PS5-08-01LS-0703 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0706 | PAGA LOUDSPEAKER | OFFICE BLDG
2648 | Telecom | PS5-08-01LS-0707-CR01 | PS5-08-01LS-0706 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0707 | PAGA LOUDSPEAKER | OFFICE BLDG
2649 | Telecom | PS5-08-01LS-0708-CR01 | PS5-08-01LS-0707 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0708 | PAGA LOUDSPEAKER | OFFICE BLDG
2650 | Telecom | PS5-08-01LS-0709-CR01 | PS5-08-01LS-0708 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0709 | PAGA LOUDSPEAKER | OFFICE BLDG
2651 | Telecom | PS5-08-01LS-0710-CR01 | PS5-08-01LS-0709 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0710 | PAGA LOUDSPEAKER | OFFICE BLDG
2652 | Telecom | PS5-08-01LS-0711-CR01 | PS5-08-01LS-0710 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0711 | PAGA LOUDSPEAKER | OFFICE BLDG
2653 | Telecom | PS5-08-01LS-0712-CR01 | PS5-08-01BT-1201 | PAGA JUNCTION BOX | OFFICE BLDG | PS5-08-01LS-0712 | PAGA LOUDSPEAKER | OFFICE BLDG
2654 | Telecom | PS5-08-01LS-0713-CR01 | PS5-08-01LS-0712 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0713 | PAGA LOUDSPEAKER | OFFICE BLDG
2655 | Telecom | PS5-08-01LS-0714-CR01 | PS5-08-01LS-0711 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0714 | PAGA LOUDSPEAKER | OFFICE BLDG
2656 | Telecom | PS5-08-01LS-0715-CR01 | PS5-08-01LS-0714 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0715 | PAGA LOUDSPEAKER | OFFICE BLDG
2657 | Telecom | PS5-08-01LS-0716-CR01 | PS5-08-01LS-0715 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0716 | PAGA LOUDSPEAKER | OFFICE BLDG
2658 | Telecom | PS5-08-01LS-0716-CR02 | PS5-08-01BT-1201 | PAGA JUNCTION BOX | OFFICE BLDG | PS5-08-01LS-0716 | PAGA LOUDSPEAKER | OFFICE BLDG
2659 | Telecom | PS5-08-01BT-0001-CR01 | PS5-08-01BT-1201 | PAGA JUNCTION BOX | OFFICE BLDG | PS5-08-01BT-0001 | PAGA JUNCTION BOX | PRIMARY MUSTER AREA
2660 | Telecom | PS5-08-01BT-0001-CR02 | PS5-08-01OC-0001 | OVERRIDE CONTROL UNIT | PRIMARY MUSTER AREA | PS5-08-01BT-0001 | PAGA JUNCTION BOX | PRIMARY MUSTER AREA
2661 | Telecom | PS5-08-01LS-0719-CR01 | PS5-08-01OC-0001 | OVERRIDE CONTROL UNIT | PRIMARY MUSTER AREA | PS5-08-01LS-0719 | PAGA LOUDSPEAKER | PRIMARY MUSTER AREA
2662 | Telecom | PS5-08-01LS-0717-CR01 | PS5-08-01LS-0713 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0717 | PAGA LOUDSPEAKER | OFFICE BLDG
2663 | Telecom | PS5-08-01LS-0718-CR01 | PS5-08-01LS-0717 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0718 | PAGA LOUDSPEAKER | OFFICE BLDG
2664 | Telecom | PS5-08-01LS-0720-CR01 | PS5-08-01BT-0001 | PAGA JUNCTION BOX | PRIMARY MUSTER AREA | PS5-08-01LS-0720 | PAGA LOUDSPEAKER | FIELD
2665 | Telecom | PS5-08-01BT-1601-CR01 | PS5-08-01LS-0720 | PAGA LOUDSPEAKER | FIELD | PS5-08-01BT-1601 | PAGA JUNCTION BOX | WAREHOUSE/WORKSHOP
2666 | Telecom | PS5-08-01BT-1601-CR02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1601 | PAGA JUNCTION BOX | WAREHOUSE/WORKSHOP
2667 | Telecom | PS5-08-01LS-0721-CR01 | PS5-08-01BT-1601 | PAGA JUNCTION BOX | WAREHOUSE/WORKSHOP | PS5-08-01LS-0721 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2668 | Telecom | PS5-08-01LS-0722-CR01 | PS5-08-01LS-0721 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0722 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2669 | Telecom | PS5-08-01LS-0723-CR01 | PS5-08-01LS-0722 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0723 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2670 | Telecom | PS5-08-01LS-0724-CR01 | PS5-08-01LS-0723 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0724 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2671 | Telecom | PS5-08-01LS-0725-CR01 | PS5-08-01LS-0724 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0725 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2672 | Telecom | PS5-08-01LS-0726-CR01 | PS5-08-01LS-0725 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0726 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2673 | Telecom | PS5-08-01LS-0727-CR01 | PS5-08-01LS-0726 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0727 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2674 | Telecom | PS5-08-01LS-0728-CR01 | PS5-08-01LS-0727 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0728 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2675 | Telecom | PS5-08-01LS-0729-CR01 | PS5-08-01LS-0728 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0729 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2676 | Telecom | PS5-08-01LS-0730-CR01 | PS5-08-01LS-0729 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0730 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2677 | Telecom | PS5-08-01LS-0731-CR01 | PS5-08-01LS-0730 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0731 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2678 | Telecom | PS5-08-01LS-0732-CR01 | PS5-08-01LS-0731 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0732 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2679 | Telecom | PS5-08-01LS-0733-CR01 | PS5-08-01LS-0732 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0733 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2680 | Telecom | PS5-08-01LS-0733-CR02 | PS5-08-01BT-1601 | PAGA JUNCTION BOX | WAREHOUSE/WORKSHOP | PS5-08-01LS-0733 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2681 | Telecom | PS5-08-01BT-1202-CR01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1202 | PAGA JUNCTION BOX | OFFICE BLDG
2682 | Telecom | PS5-08-01BT-1202-CR02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1202 | PAGA JUNCTION BOX | OFFICE BLDG
2683 | Telecom | PS5-08-01LS-0804-CR01 | PS5-08-01BT-1202 | PAGA JUNCTION BOX | OFFICE BLDG | PS5-08-01LS-0804 | PAGA LOUDSPEAKER | OFFICE BLDG
2684 | Telecom | PS5-08-01LS-0801-CR01 | PS5-08-01BT-1202 | PAGA JUNCTION BOX | OFFICE BLDG | PS5-08-01LS-0801 | PAGA LOUDSPEAKER | OFFICE BLDG
2685 | Telecom | PS5-08-01LS-0802-CR01 | PS5-08-01LS-0801 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0802 | PAGA LOUDSPEAKER | OFFICE BLDG
2686 | Telecom | PS5-08-01LS-0803-CR01 | PS5-08-01LS-0802 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0803 | PAGA LOUDSPEAKER | OFFICE BLDG
2687 | Telecom | PS5-08-01LS-0805-CR01 | PS5-08-01LS-0803 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0805 | PAGA LOUDSPEAKER | OFFICE BLDG
2688 | Telecom | PS5-08-01LS-0806-CR01 | PS5-08-01LS-0805 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0806 | PAGA LOUDSPEAKER | OFFICE BLDG
2689 | Telecom | PS5-08-01LS-0807-CR01 | PS5-08-01LS-0806 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0807 | PAGA LOUDSPEAKER | OFFICE BLDG
2690 | Telecom | PS5-08-01LS-0808-CR01 | PS5-08-01LS-0807 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0808 | PAGA LOUDSPEAKER | OFFICE BLDG
2691 | Telecom | PS5-08-01LS-0809-CR01 | PS5-08-01LS-0808 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0809 | PAGA LOUDSPEAKER | OFFICE BLDG
2692 | Telecom | PS5-08-01LS-0810-CR01 | PS5-08-01LS-0809 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0810 | PAGA LOUDSPEAKER | OFFICE BLDG
2693 | Telecom | PS5-08-01LS-0813-CR01 | PS5-08-01LS-0810 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0813 | PAGA LOUDSPEAKER | OFFICE BLDG
2694 | Telecom | PS5-08-01LS-0814-CR01 | PS5-08-01LS-0813 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0814 | PAGA LOUDSPEAKER | OFFICE BLDG
2695 | Telecom | PS5-08-01LS-0815-CR01 | PS5-08-01LS-0814 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0815 | PAGA LOUDSPEAKER | OFFICE BLDG
2696 | Telecom | PS5-08-01LS-0816-CR01 | PS5-08-01LS-0815 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0816 | PAGA LOUDSPEAKER | OFFICE BLDG
2697 | Telecom | PS5-08-01LS-0816-CR02 | PS5-08-01BT-1202 | PAGA JUNCTION BOX | OFFICE BLDG | PS5-08-01LS-0816 | PAGA LOUDSPEAKER | OFFICE BLDG
2698 | Telecom | PS5-08-01LS-0811-CR01 | PS5-08-01BT-1202 | PAGA JUNCTION BOX | OFFICE BLDG | PS5-08-01LS-0811 | PAGA LOUDSPEAKER | OFFICE BLDG
2699 | Telecom | PS5-08-01LS-0812-CR01 | PS5-08-01LS-0811 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0812 | PAGA LOUDSPEAKER | OFFICE BLDG
2700 | Telecom | PS5-08-01LS-0817-CR01 | PS5-08-01LS-0812 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0817 | PAGA LOUDSPEAKER | OFFICE BLDG
2701 | Telecom | PS5-08-01LS-0818-CR01 | PS5-08-01LS-0817 | PAGA LOUDSPEAKER | OFFICE BLDG | PS5-08-01LS-0818 | PAGA LOUDSPEAKER | OFFICE BLDG
2702 | Telecom | PS5-08-01BT-0002-CR01 | PS5-08-01BT-1202 | PAGA JUNCTION BOX | OFFICE BLDG | PS5-08-01BT-0002 | PAGA JUNCTION BOX | PRIMARY MUSTER AREA
2703 | Telecom | PS5-08-01BT-0002-CR02 | PS5-08-01BT-0002 | PAGA JUNCTION BOX | PRIMARY MUSTER AREA | PS5-08-01OC-0001 | OVERRIDE CONTROL UNIT | PRIMARY MUSTER AREA
2704 | Telecom | PS5-08-01LS-0819-CR01 | PS5-08-01OC-0001 | OVERRIDE CONTROL UNIT | PRIMARY MUSTER AREA | PS5-08-01LS-0819 | PAGA LOUDSPEAKER | PRIMARY MUSTER AREA
2705 | Telecom | PS5-08-01BT-1602-CR01 | PS5-08-01BT-0002 | PAGA JUNCTION BOX | PRIMARY MUSTER AREA | PS5-08-01BT-1602 | PAGA JUNCTION BOX | WAREHOUSE/WORKSHOP
2706 | Telecom | PS5-08-01BT-1602-CR02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1602 | PAGA JUNCTION BOX | WAREHOUSE/WORKSHOP
2707 | Telecom | PS5-08-01LS-0820-CR01 | PS5-08-01BT-1602 | PAGA JUNCTION BOX | WAREHOUSE/WORKSHOP | PS5-08-01LS-0820 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2708 | Telecom | PS5-08-01LS-0821-CR01 | PS5-08-01LS-0820 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0821 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2709 | Telecom | PS5-08-01LS-0822-CR01 | PS5-08-01LS-0821 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0822 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2710 | Telecom | PS5-08-01LS-0823-CR01 | PS5-08-01LS-0822 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0823 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2711 | Telecom | PS5-08-01LS-0824-CR01 | PS5-08-01LS-0823 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0824 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2712 | Telecom | PS5-08-01LS-0825-CR01 | PS5-08-01LS-0824 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0825 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2713 | Telecom | PS5-08-01LS-0826-CR01 | PS5-08-01LS-0825 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0826 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2714 | Telecom | PS5-08-01LS-0827-CR01 | PS5-08-01LS-0826 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0827 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2715 | Telecom | PS5-08-01LS-0828-CR01 | PS5-08-01LS-0827 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0828 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2716 | Telecom | PS5-08-01LS-0829-CR01 | PS5-08-01LS-0828 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0829 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2717 | Telecom | PS5-08-01LS-0830-CR01 | PS5-08-01LS-0829 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0830 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2718 | Telecom | PS5-08-01LS-0831-CR01 | PS5-08-01LS-0830 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0831 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2719 | Telecom | PS5-08-01LS-0832-CR01 | PS5-08-01LS-0831 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0832 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2720 | Telecom | PS5-08-01LS-0833-CR01 | PS5-08-01LS-0832 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0833 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2721 | Telecom | PS5-08-01LS-0834-CR01 | PS5-08-01LS-0833 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP | PS5-08-01LS-0834 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2722 | Telecom | PS5-08-01LS-0834-CR02 | PS5-08-01BT-1602 | PAGA JUNCTION BOX | WAREHOUSE/WORKSHOP | PS5-08-01LS-0834 | PAGA LOUDSPEAKER | WAREHOUSE/WORKSHOP
2723 | Telecom | PS5-08-01OC-0001-CJ01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01OC-0001 | OVERRIDE CONTROL UNIT | PRIMARY MUSTER AREA
2724 | Telecom | PS5-08-01OC-0001-CJ02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01OC-0001 | OVERRIDE CONTROL UNIT | PRIMARY MUSTER AREA
2725 | Telecom | PS5-08-01OC-0001-CN01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01OC-0001 | OVERRIDE CONTROL UNIT | PRIMARY MUSTER AREA
2726 | Telecom | PS5-08-01OC-0001-CN02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01OC-0001 | OVERRIDE CONTROL UNIT | PRIMARY MUSTER AREA
2727 | Telecom | PS5-08-01OC-0002-CJ01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01OC-0002 | OVERRIDE CONTROL UNIT | SECONDARY MUSTER AREA
2728 | Telecom | PS5-08-01OC-0002-CJ02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01OC-0002 | OVERRIDE CONTROL UNIT | SECONDARY MUSTER AREA
2729 | Telecom | PS5-08-01OC-0002-CN01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01OC-0002 | OVERRIDE CONTROL UNIT | SECONDARY MUSTER AREA
2730 | Telecom | PS5-08-01OC-0002-CN02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01OC-0002 | OVERRIDE CONTROL UNIT | SECONDARY MUSTER AREA
2731 | Telecom | PS5-08-01BT-1503-CJ01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1503 | PAGA JUNCTION BOX | GUARD HOUSE
2732 | Telecom | PS5-08-01BT-1503-CJ02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1503 | PAGA JUNCTION BOX | GUARD HOUSE
2733 | Telecom | PS5-08-01BT-1203-CJ01 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1203 | PAGA JUNCTION BOX | OFFICE BLDG
2734 | Telecom | PS5-08-01BT-1203-CJ02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | FIELD | PS5-08-01BT-1203 | PAGA JUNCTION BOX | OFFICE BLDG
2735 | Telecom | PS5-08-85DC-0001-CJ01 | PS5-08-85BT-0017 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0001 | ACS GATE CONTACT | FIELD
2736 | Telecom | PS5-08-85ML-0001-CN01 | PS5-08-85BT-0017 | ACS JUNCTION BOX | FIELD | PS5-08-85ML-0001 | MAGNETIC DOORLOCK | FIELD
2737 | Telecom | PS5-08-85PB-0001-CJ01 | PS5-08-85BT-0017 | ACS JUNCTION BOX | FIELD | PS5-08-85PB-0001 | EXIT PUSHBUTTON | FIELD
2738 | Telecom | PS5-08-85BT-0017-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BT-0017 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2739 | Telecom | PS5-08-85BT-0017-CN01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-85BT-0017 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2740 | Telecom | PS5-08-85DC-0002-CJ01 | PS5-08-85BT-0001 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0002 | ACS GATE CONTACT | FIELD
2741 | Telecom | PS5-08-85DC-0024-CJ01 | PS5-08-85BT-0001 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0024 | ACS GATE CONTACT | FIELD
2742 | Telecom | PS5-08-85DC-0003-CJ01 | PS5-08-85BT-0019 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0003 | ACS GATE CONTACT | FIELD
2743 | Telecom | PS5-08-85BT-0019-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BT-0019 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2744 | Telecom | PS5-82-MGV-0002-CC01 | PS5-08-85BT-0019 | ACS JUNCTION BOX | FIELD | PS5-82-MGV-0002 | SLIDING GATE | FIELD
2745 | Telecom | PS5-08-85DC-0004-CJ01 | PS5-08-85BT-0002 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0004 | ACS GATE CONTACT | FIELD
2746 | Telecom | PS5-08-85BT-0002-CJ01 | PS5-08-15CP-0004 | CONTROL PANEL | FIELD | PS5-08-85BT-0002 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2747 | Telecom | PS5-08-85DC-0005-CJ01 | PS5-08-85BT-0003 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0005 | ACS GATE CONTACT | FIELD
2748 | Telecom | PS5-08-85BT-0003-CJ01 | PS5-08-15CP-0004 | CONTROL PANEL | FIELD | PS5-08-85BT-0003 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2749 | Telecom | PS5-08-85DC-0006-CJ01 | PS5-08-85BT-0004 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0006 | ACS GATE CONTACT | FIELD
2750 | Telecom | PS5-08-85BT-0004-CJ01 | PS5-08-15CP-0005 | CONTROL PANEL | FIELD | PS5-08-85BT-0004 | ACS JUNCTION BOX | FIELD
2751 | Telecom | PS5-08-85DC-0007-CJ01 | PS5-08-85BT-0005 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0007 | ACS GATE CONTACT | FIELD
2752 | Telecom | PS5-08-85BT-0005-CJ01 | PS5-08-15CP-0005 | CONTROL PANEL | FIELD | PS5-08-85BT-0005 | ACS JUNCTION BOX | FIELD | 2025-12-06 00:00:00 | CPP-RFI-68-65-05-0011
2753 | Telecom | PS5-08-85DC-0008-CJ01 | PS5-08-85BT-0006 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0008 | ACS GATE CONTACT | FIELD
2754 | Telecom | PS5-08-85BT-0006-CJ01 | PS5-08-15CP-0005 | CONTROL PANEL | FIELD | PS5-08-85BT-0006 | ACS JUNCTION BOX | FIELD
2755 | Telecom | PS5-08-85DC-0009-CJ01 | PS5-08-85BT-0007 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0009 | ACS GATE CONTACT | FIELD
2756 | Telecom | PS5-08-85BT-0007-CJ01 | PS5-08-15CP-0005 | CONTROL PANEL | FIELD | PS5-08-85BT-0007 | ACS JUNCTION BOX | FIELD | 2025-12-06 00:00:00 | CPP-RFI-68-65-05-0011
2757 | Telecom | PS5-08-85DC-0010-CJ01 | PS5-08-85BT-0008 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0010 | ACS GATE CONTACT | FIELD
2758 | Telecom | PS5-08-85BT-0008-CJ01 | PS5-08-15CP-0007 | CONTROL PANEL | FIELD | PS5-08-85BT-0008 | ACS JUNCTION BOX | FIELD
2759 | Telecom | PS5-08-85DC-0011-CJ01 | PS5-08-85BT-0010 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0011 | ACS GATE CONTACT | FIELD
2760 | Telecom | PS5-08-85BT-0010-CJ01 | PS5-08-15CP-0007 | CONTROL PANEL | FIELD | PS5-08-85BT-0010 | ACS JUNCTION BOX | FIELD | 2025-12-11 00:00:00 | CPP-RFI-68-65-05-0013
2761 | Telecom | PS5-08-85DC-0012-CJ01 | PS5-08-85BT-0009 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0012 | ACS GATE CONTACT | FIELD
2762 | Telecom | PS5-08-85DC-0025-CJ01 | PS5-08-85BT-0009 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0025 | ACS GATE CONTACT | FIELD
2763 | Telecom | PS5-08-85BT-0009-CJ01 | PS5-08-15CP-0007 | CONTROL PANEL | FIELD | PS5-08-85BT-0009 | ACS JUNCTION BOX | FIELD
2764 | Telecom | PS5-08-85DC-0013-CJ01 | PS5-08-85BT-0012 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0013 | ACS GATE CONTACT | FIELD
2765 | Telecom | PS5-08-85BT-0012-CJ01 | PS5-08-15CP-0007 | CONTROL PANEL | FIELD | PS5-08-85BT-0012 | ACS JUNCTION BOX | FIELD
2766 | Telecom | PS5-08-85DC-0014-CJ01 | PS5-08-85BT-0011 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0014 | ACS GATE CONTACT | FIELD
2767 | Telecom | PS5-08-85BT-0011-CJ01 | PS5-08-15CP-0007 | CONTROL PANEL | FIELD | PS5-08-85BT-0011 | ACS JUNCTION BOX | FIELD
2768 | Telecom | PS5-08-85DC-0015-CJ01 | PS5-08-85BT-0013 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0015 | ACS GATE CONTACT | FIELD
2769 | Telecom | PS5-08-85BT-0013-CJ01 | PS5-08-15CP-0002 | CONTROL PANEL | FIELD | PS5-08-85BT-0013 | ACS JUNCTION BOX | FIELD | 2025-12-15 00:00:00 | CPP-RFI-68-65-05-0015
2770 | Telecom | PS5-08-85DC-0016-CJ01 | PS5-08-85BT-0014 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0016 | ACS GATE CONTACT | FIELD
2771 | Telecom | PS5-08-85BT-0014-CJ01 | PS5-08-15CP-0002 | CONTROL PANEL | FIELD | PS5-08-85BT-0014 | ACS JUNCTION BOX | FIELD | 2026-04-10 00:00:00 | CPP-RFI-68-65-05-0023
2772 | Telecom | PS5-08-85DC-0017-CJ01 | PS5-08-85BT-0015 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0017 | ACS GATE CONTACT | FIELD
2773 | Telecom | PS5-08-85BT-0015-CJ01 | PS5-08-15CP-0002 | CONTROL PANEL | FIELD | PS5-08-85BT-0015 | ACS JUNCTION BOX | FIELD | 2025-12-15 00:00:00 | CPP-RFI-68-65-05-0015
2774 | Telecom | PS5-08-85DC-0018-CJ01 | PS5-08-85BT-0016 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0018 | ACS GATE CONTACT | FIELD
2775 | Telecom | PS5-08-85BT-0016-CJ01 | PS5-08-15CP-0002 | CONTROL PANEL | FIELD | PS5-08-85BT-0016 | ACS JUNCTION BOX | FIELD | 2026-07-01 00:00:00 | CPP-RFI-68-65-05-0034
2776 | Telecom | PS5-08-85DC-0019-CJ01 | PS5-08-85BT-0024 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0019 | ACS GATE CONTACT | FIELD
2777 | Telecom | PS5-08-85DC-0026-CJ01 | PS5-08-85BT-0024 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0026 | ACS GATE CONTACT | FIELD
2778 | Telecom | PS5-08-85BT-0024-CJ01 | PS5-08-15CP-0004 | CONTROL PANEL | FIELD | PS5-08-85BT-0024 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2779 | Telecom | PS5-08-85BT-0021-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BT-0021 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2780 | Telecom | PS5-82-MBA-0001-CC01 | PS5-08-85BT-0021 | ACS JUNCTION BOX | FIELD | PS5-82-MBA-0001 | VEHICLE BARRIER | FIELD
2781 | Telecom | PS5-08-85BR-0005-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BR-0005 | BADGE READER | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2782 | Telecom | PS5-08-85BR-0006-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BR-0006 | BADGE READER | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2783 | Telecom | PS5-08-85BT-0022-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BT-0022 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2784 | Telecom | PS5-82-MTL-0001-CC01 | PS5-08-85BT-0022 | ACS JUNCTION BOX | FIELD | PS5-82-MTL-0001 | TURNSTILE | FIELD
2785 | Telecom | PS5-08-85BR-0003-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BR-0003 | BADGE READER | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2786 | Telecom | PS5-08-85BR-0004-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BR-0004 | BADGE READER | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2787 | Telecom | PS5-08-85DC-0021-CJ01 | PS5-08-85BT-0025 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0021 | ACS GATE CONTACT | FIELD
2788 | Telecom | PS5-08-85DC-0027-CJ01 | PS5-08-85BT-0025 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0027 | ACS GATE CONTACT | FIELD
2789 | Telecom | PS5-08-85BT-0025-CJ01 | PS5-08-15CP-0004 | CONTROL PANEL | FIELD | PS5-08-85BT-0025 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2790 | Telecom | PS5-08-85BT-0020-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BT-0020 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2791 | Telecom | PS5-82-MBA-0003-CC01 | PS5-08-85BT-0020 | ACS JUNCTION BOX | FIELD | PS5-82-MBA-0003 | VEHICLE BARRIER | FIELD
2792 | Telecom | PS5-08-85BR-0001-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BR-0001 | BADGE READER | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2793 | Telecom | PS5-08-85BR-0002-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BR-0002 | BADGE READER | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2794 | Telecom | PS5-08-85DC-0022-CJ01 | PS5-08-85BT-0026 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0022 | ACS GATE CONTACT | FIELD
2795 | Telecom | PS5-08-85DC-0028-CJ01 | PS5-08-85BT-0026 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0028 | ACS GATE CONTACT | FIELD
2796 | Telecom | PS5-08-85BT-0026-CJ01 | PS5-08-15CP-0004 | CONTROL PANEL | FIELD | PS5-08-85BT-0026 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2797 | Telecom | PS5-08-85BT-0023-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BT-0023 | ACS JUNCTION BOX | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2798 | Telecom | PS5-08-85BR-0007-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BR-0007 | BADGE READER | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2799 | Telecom | PS5-08-85BR-0008-CC01 | PS5-08-85CP-1501 | CONTROL PANEL | GUARD HOUSE | PS5-08-85BR-0008 | BADGE READER | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2800 | Telecom | PS5-08-85DC-0023-CJ01 | PS5-08-85BT-0018 | ACS JUNCTION BOX | FIELD | PS5-08-85DC-0023 | ACS GATE CONTACT | FIELD
2801 | Telecom | PS5-08-85BT-0018-CJ01 | PS5-08-15CP-0004 | CONTROL PANEL | FIELD | PS5-08-85BT-0018 | ACS JUNCTION BOX | FIELD
2802 | Telecom | PS5-08-05IN-0001-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-05IN-0001 | INTERCOM | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2803 | Telecom | PS5-08-05IN-0002-CA01 | PS5-08-15CP-0004 | CONTROL PANEL | FIELD | PS5-08-05IN-0002 | INTERCOM | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2804 | Telecom | PS5-08-05IN-0003-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-05IN-0003 | INTERCOM | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2805 | Telecom | PS5-08-05IN-0004-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-05IN-0004 | INTERCOM | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2806 | Telecom | PS5-08-05IN-0005-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-05IN-0005 | INTERCOM | FIELD | 19-June-2026 | CPP-RFI-68-65-05-0032
2807 | Telecom | PS5-08-52CM-0001-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-52CM-0001 | CCTV OPTICAL CAMERA | MAIN ENTRANCE
2808 | Telecom | PS5-08-52CM-0002-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-52CM-0002 | CCTV OPTICAL CAMERA | MAIN ENTRANCE
2809 | Telecom | PS5-08-52CM-0003-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-52CM-0003 | CCTV OPTICAL CAMERA | MAIN ENTRANCE
2810 | Telecom | PS5-08-52CM-0004-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-52CM-0004 | CCTV OPTICAL CAMERA | MAIN ENTRANCE
2811 | Telecom | PS5-08-52CM-0005-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-52CM-0005 | CCTV OPTICAL CAMERA | MAIN ENTRANCE
2812 | Telecom | PS5-08-52CM-0034-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARD HOUSE | PS5-08-52CM-0034 | CCTV PANORAMIC CAMERA | MAIN ENTRANCE
2813 | Telecom | PS5-08-52CM-0931-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFF. & FACILITIES BLDG | PS5-08-52CM-0931 | CCTV SA PTZ CAMERA | TELECOM TOWER
2814 | Telecom | PS5-08-52TK-0931-CC01 | PS5-08-52CM-0931 | CCTV SA PTZ CAMERA | FIELD | PS5-08-52TK-0931 | CCTV WATER TANK | FIELD
2815 | Telecom | PS5-08-52CM-0131-CX01 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-52CM-0131 | CCTV SA PTZ CAMERA | FIELD | 11-May-2026 | CPP-RFI-68-65-05-0027
2816 | Telecom | PS5-08-52TK-0131-CC01 | PS5-08-52CM-0131 | CCTV SA PTZ CAMERA | FIELD | PS5-08-52TK-0131 | CCTV WATER TANK | FIELD
2817 | Telecom | PS5-08-52CM-0132-CX01 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-52CM-0132 | CCTV SA PTZ CAMERA | FIELD
2818 | Telecom | PS5-08-52TK-0132-CC01 | PS5-08-52CM-0132 | CCTV SA PTZ CAMERA | FIELD | PS5-08-52TK-0132 | CCTV WATER TANK | FIELD
2819 | Telecom | PS5-08-52CM-0133-CX01 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-52CM-0133 | CCTV SA PTZ CAMERA | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2820 | Telecom | PS5-08-52TK-0133-CC01 | PS5-08-52CM-0133 | CCTV SA PTZ CAMERA | FIELD | PS5-08-52TK-0133 | CCTV WATER TANK | FIELD
2821 | Telecom | PS5-08-52CM-0134-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-52CM-0134 | CCTV SA PTZ CAMERA | FIELD
2822 | Telecom | PS5-08-52TK-0134-CC01 | PS5-08-52CM-0134 | CCTV SA PTZ CAMERA | FIELD | PS5-08-52TK-0134 | CCTV WATER TANK | FIELD
2823 | Telecom | PS5-08-52CM-0138-CX01 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-52CM-0138 | CCTV SA PTZ CAMERA | FIELD
2824 | Telecom | PS5-08-52TK-0138-CC01 | PS5-08-52CM-0138 | CCTV SA PTZ CAMERA | FIELD | PS5-08-52TK-0138 | CCTV WATER TANK | FIELD
2825 | Telecom | PS5-08-52CM-0139-CX01 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-52CM-0139 | CCTV SA PTZ CAMERA | FIELD
2826 | Telecom | PS5-08-52TK-0139-CC01 | PS5-08-52CM-0139 | CCTV SA PTZ CAMERA | FIELD | PS5-08-52TK-0139 | CCTV WATER TANK | FIELD
2827 | Telecom | PS5-08-52CM-0031-CA01 | PS5-08-15CP-0002 | CONTROL PANEL | FIELD | PS5-08-52CM-0031 | CCTV SA PTZ CAMERA | FIELD
2828 | Telecom | PS5-08-52TK-0031-CC01 | PS5-08-52CM-0031 | CCTV SA PTZ CAMERA | FIELD | PS5-08-52TK-0031 | CCTV WATER TANK | FIELD
2829 | Telecom | PS5-08-52CM-0032-CA01 | PS5-08-15CP-0006 | CONTROL PANEL | FIELD | PS5-08-52CM-0032 | CCTV SA PTZ CAMERA | FIELD
2830 | Telecom | PS5-08-52TK-0032-CC01 | PS5-08-52CM-0032 | CCTV SA PTZ CAMERA | FIELD | PS5-08-52TK-0032 | CCTV WATER TANK | FIELD
2831 | Telecom | PS5-08-52CM-0033-CA01 | PS5-08-15CP-0008 | CONTROL PANEL | FIELD | PS5-08-52CM-0033 | CCTV SA PTZ CAMERA | FIELD
2832 | Telecom | PS5-08-52TK-0033-CC01 | PS5-08-52CM-0033 | CCTV SA PTZ CAMERA | FIELD | PS5-08-52TK-0033 | CCTV WATER TANK | FIELD
2833 | Telecom | PS5-08-15CP-0006-CX01 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG/ITR | PS5-08-15CP-0006 | CONTROL PANEL | FIELD
2834 | Telecom | PS5-08-15CP-0007-CX01 | PS5-08-15CP-0006 | CONTROL PANEL | FIELD | PS5-08-15CP-0007 | CONTROL PANEL | FIELD
2835 | Telecom | PS5-08-15CP-0008-CX01 | PS5-08-15CP-0007 | CONTROL PANEL | FIELD | PS5-08-15CP-0008 | CONTROL PANEL | FIELD
2836 | Telecom | PS5-08-15CP-0001-CX01 | PS5-08-15CP-0008 | CONTROL PANEL | FIELD | PS5-08-15CP-0001 | CONTROL PANEL | FIELD
2837 | Telecom | PS5-08-15CP-0002-CX01 | PS5-08-15CP-0001 | CONTROL PANEL | FIELD | PS5-08-15CP-0002 | CONTROL PANEL | FIELD | 2026-04-10 00:00:00 | CPP-RFI-68-65-05-0023
2838 | Telecom | PS5-08-15CP-0003-CX01 | PS5-08-15CP-0002 | CONTROL PANEL | FIELD | PS5-08-15CP-0003 | CONTROL PANEL | FIELD
2839 | Telecom | PS5-08-15CP-0004-CX01 | PS5-08-15CP-0003 | CONTROL PANEL | FIELD | PS5-08-15CP-0004 | CONTROL PANEL | FIELD
2840 | Telecom | PS5-08-15CP-0005-CX01 | PS5-08-15CP-0004 | CONTROL PANEL | FIELD | PS5-08-15CP-0005 | CONTROL PANEL | FIELD
2841 | Telecom | PS5-08-15CP-0005-CX02 | PS5-08-15CP-0005 | CONTROL PANEL | FIELD | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG/ITR
2842 | Telecom | PS5-08-85BT-0027-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFF. & FACILITIES BLDG | PS5-08-85BT-0027 | WAP JUNCTION BOX | PRIMARY MUSTER AREA
2843 | Telecom | PS5-08-85BT-0028-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFF. & FACILITIES BLDG | PS5-08-85BT-0028 | WAP JUNCTION BOX | PRIMARY MUSTER AREA
2844 | Telecom | PS5-08-85AP-0001-CA01 | PS5-08-85BT-0027 | WAP JUNCTION BOX | PRIMARY MUSTER AREA | PS5-08-85AP-0001 | WIRELESS ACCESS PONT | PRIMARY MUSTER AREA
2845 | Telecom | PS5-08-85AP-0002-CA01 | PS5-08-85BT-0028 | WAP JUNCTION BOX | PRIMARY MUSTER AREA | PS5-08-85AP-0002 | WIRELESS ACCESS PONT | PRIMARY MUSTER AREA
2846 | Telecom | PS5-08-85BR-0009-CC01 | PS5-08-85CP-1201 | CONTROL PANEL | OFF. & FACILITIES BLDG | PS5-08-85BR-0009 | POB BADGE READER | PRIMARY MUSTER AREA
2847 | Telecom | PS5-08-85BR-0010-CC01 | PS5-08-85CP-1202 | CONTROL PANEL | OFF. & FACILITIES BLDG | PS5-08-85BR-0010 | POB BADGE READER | PRIMARY MUSTER AREA
2848 | Telecom | PS5-08-85AP-0003-CA01 | PS5-08-85CP-0024 | CONTROL PANEL | SECONDARY MUSTER AREA | PS5-08-85AP-0003 | WIRELESS ACCESS POINT | SECONDARY MUSTER AREA
2849 | Telecom | PS5-08-85AP-0004-CA01 | PS5-08-85CP-0025 | CONTROL PANEL | SECONDARY MUSTER AREA | PS5-08-85AP-0004 | WIRELESS ACCESS POINT | SECONDARY MUSTER AREA
2850 | Telecom | PS5-08-85BR-0011-CC01 | PS5-08-85CP-0024 | CONTROL PANEL | SECONDARY MUSTER AREA | PS5-08-85BR-0011 | POB BADGE READER | SECONDARY MUSTER AREA
2851 | Telecom | PS5-08-85BR-0012-CC01 | PS5-08-85CP-0025 | CONTROL PANEL | SECONDARY MUSTER AREA | PS5-08-85BR-0012 | POB BADGE READER | SECONDARY MUSTER AREA
2852 | Telecom | PS5-08-85CP-0024-CX01 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-85CP-0024 | CONTROL PANEL | SECONDARY MUSTER AREA
2853 | Telecom | PS5-08-85CP-0025-CX01 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-85CP-0025 | CONTROL PANEL | SECONDARY MUSTER AREA
2854 | Telecom | PS5-08-85CP-0024-CX02 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-85CP-0024 | CONTROL PANEL | SECONDARY MUSTER AREA
2855 | Telecom | PS5-08-85CP-0025-CX02 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-85CP-0025 | CONTROL PANEL | SECONDARY MUSTER AREA
2856 | Telecom | PS5-08-12BT-0001-CX01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-12BT-0001 | WAP JUNCTION BOX | FIELD
2857 | Telecom | PS5-08-12BT-0002-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-12BT-0002 | WAP JUNCTION BOX | FIELD
2858 | Telecom | PS5-08-12BT-0003-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFF. & FACILITIES BLDG | PS5-08-12BT-0003 | WAP JUNCTION BOX | FIELD
2859 | Telecom | PS5-08-12BT-0101-CA01 | PS5-08-11CB-1901 | SIE CABINET | GENERATOR ELECTRIC BLDG | PS5-08-12BT-0101 | WAP JUNCTION BOX | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2860 | Telecom | PS5-08-12BT-0103-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-12BT-0103 | WAP JUNCTION BOX | FIELD
2861 | Telecom | PS5-08-12BT-0104-CX01 | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR | PS5-08-12BT-0104 | WAP JUNCTION BOX | FIELD | 11-May-2026 | CPP-RFI-68-65-05-0028
2862 | Telecom | PS5-08-12BT-0105-CX01 | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR | PS5-08-12BT-0105 | WAP JUNCTION BOX | FIELD
2863 | Telecom | PS5-08-12BT-0106-CX01 | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR | PS5-08-12BT-0106 | WAP JUNCTION BOX | FIELD
2864 | Telecom | PS5-08-12BT-0107-CX01 | PS5-08-11CB-1901 | SIE CABINET | GENERATOR ELECTRIC BLDG | PS5-08-12BT-0107 | WAP JUNCTION BOX | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2865 | Telecom | PS5-08-12AP-0001-CN01 | PS5-08-12BT-0001 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0001 | WIRELESS ACCESS POINT | FIELD
2866 | Telecom | PS5-08-12AP-0002-CA01 | PS5-08-12BT-0002 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0002 | WIRELESS ACCESS POINT | FIELD
2867 | Telecom | PS5-08-12AP-0003-CA01 | PS5-08-12BT-0003 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0003 | WIRELESS ACCESS POINT | FIELD
2868 | Telecom | PS5-08-12AP-0101-CA01 | PS5-08-12BT-0101 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0101 | WIRELESS ACCESS POINT | FIELD
2869 | Telecom | PS5-08-12AP-0103-CA01 | PS5-08-12BT-0103 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0103 | WIRELESS ACCESS POINT | FIELD
2870 | Telecom | PS5-08-12AP-0104-CN01 | PS5-08-12BT-0104 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0104 | WIRELESS ACCESS POINT | FIELD
2871 | Telecom | PS5-08-12AP-0105-CN01 | PS5-08-12BT-0105 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0105 | WIRELESS ACCESS POINT | FIELD
2872 | Telecom | PS5-08-12AP-0106-CN01 | PS5-08-12BT-0106 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0106 | WIRELESS ACCESS POINT | FIELD
2873 | Telecom | PS5-08-12AP-0107-CN01 | PS5-08-12BT-0107 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0107 | WIRELESS ACCESS POINT | FIELD
2874 | Telecom | PS5-08-12BT-0108-CX01 | PS5-08-11CB-1901 | SIE CABINET | GENERATOR ELECTRIC BLDG | PS5-08-12BT-0108 | WAP JUNCTION BOX | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2875 | Telecom | PS5-08-12AP-0108-CN01 | PS5-08-12BT-0108 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0108 | WIRELESS ACCESS POINT | FIELD
2876 | Telecom | PS5-08-12BT-0109-CX01 | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR | PS5-08-12BT-0109 | WAP JUNCTION BOX | FIELD
2877 | Telecom | PS5-08-12AP-0109-CN01 | PS5-08-12BT-0109 | WAP JUNCTION BOX | FIELD | PS5-08-12AP-0109 | WIRELESS ACCESS POINT | FIELD
2878 | Telecom | PS5-08-03TP-0001-CJ01 | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR | PS5-08-03TP-0001 | OUTDOOR TELEPHONE | FIELD | 06-July-2026 | CPP-RFI-68-65-05-0036
2879 | Telecom | PS5-08-03TP-0001-CJ02 | PS5-08-03TP-0001 | OUTDOOR TELEPHONE | FIELD | PS5-08-03FB-0001 | FLASHING BEACON/SOUNDER | FIELD
2880 | Telecom | PS5-08-03TP-0002-CJ01 | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR | PS5-08-03TP-0002 | OUTDOOR TELEPHONE | FIELD
2881 | Telecom | PS5-08-03TP-0002-CJ02 | PS5-08-03TP-0002 | OUTDOOR TELEPHONE | FIELD | PS5-08-03FB-0002 | FLASHING BEACON/SOUNDER | FIELD
2882 | Telecom | PS5-08-03TP-0003-CJ01 | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR | PS5-08-03TP-0003 | OUTDOOR TELEPHONE | PRIMARY MUSTER AREA
2883 | Telecom | PS5-08-03TP-0003-CJ02 | PS5-08-03TP-0003 | OUTDOOR TELEPHONE | FIELD | PS5-08-03FB-0003 | FLASHING BEACON/SOUNDER | FIELD
2884 | Telecom | PS5-08-03TP-0004-CJ01 | PS5-08-11CB-1901 | SIE CABINET | GENERATOR ELECTRIC BUILDING | PS5-08-03TP-0004 | OUTDOOR TELEPHONE | SECONDARY MUSTER AREA
2885 | Telecom | PS5-08-03TP-0004-CJ02 | PS5-08-03TP-0004 | OUTDOOR TELEPHONE | FIELD | PS5-08-03FB-0004 | FLASHING BEACON/SOUNDER | FIELD
2886 | Telecom | PS5-08-03TP-0101-CJ01 | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR | PS5-08-03TP-0101 | OUTDOOR TELEPHONE | FIELD
2887 | Telecom | PS5-08-03TP-0101-CJ02 | PS5-08-03TP-0101 | OUTDOOR TELEPHONE | FIELD | PS5-08-03FB-0101 | FLASHING BEACON/SOUNDER | FIELD
2888 | Telecom | PS5-08-03TP-0102-CJ01 | PS5-08-11CB-1901 | SIE CABINET | GENERATOR ELECTRIC BUILDING | PS5-08-03TP-0102 | OUTDOOR TELEPHONE | FIELD
2889 | Telecom | PS5-08-03TP-0102-CJ02 | PS5-08-03TP-0102 | OUTDOOR TELEPHONE | FIELD | PS5-08-03FB-0102 | FLASHING BEACON/SOUNDER | FIELD
2890 | Telecom | PS5-08-03TP-0103-CJ01 | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR | PS5-08-03TP-0103 | OUTDOOR TELEPHONE | FIELD | 11-May-2026 | CPP-RFI-68-65-05-0029
2891 | Telecom | PS5-08-03TP-0103-CJ02 | PS5-08-03TP-0103 | OUTDOOR TELEPHONE | FIELD | PS5-08-03FB-0103 | FLASHING BEACON/SOUNDER | FIELD
2892 | Telecom | PS5-08-61SN-0003-CZ01 | PS5-08-61SN-0003 | TEMP/HUMIDITY SENSOR | FIELD | PS5-08-61BT-0001 | METEOCEAN JB | FIELD
2893 | Telecom | PS5-08-61SN-0005-CZ01 | PS5-08-61SN-0005 | CLOUD SENSOR | FIELD | PS5-08-61BT-0002 | CLOUD SENSOR JB | FIELD
2894 | Telecom | PS5-08-61SN-0005-CZ02 | PS5-08-61SN-0005 | CLOUD SENSOR | FIELD | PS5-08-61BT-0002 | CLOUD SENSOR JB | FIELD
2895 | Telecom | PS5-08-61SN-0004-CZ01 | PS5-08-61SN-0004 | PRECIPITATION SENSOR | FIELD | PS5-08-61BT-0001 | METEOCEAN JB | FIELD
2896 | Telecom | PS5-08-61SN-0901-CZ01 | PS5-08-61SN-0901 | WIND SENSOR | TELECOM TOWER | PS5-08-61BT-0901 | WIND SENSOR JB | TELECOM TOWER
2897 | Telecom | PS5-08-61BT-0901-CC01 | PS5-08-61BT-0001 | METEOCEAN JUNCTION BOX | FIELD | PS5-08-61BT-0901 | METEOCEAN JUNCTION BOX | TELECOM TOWER
2898 | Telecom | PS5-08-61BT-0001-CC01 | PS5-08-14CB-1201 | SII SP1 CABINET | OFF. & FACILITIES BLDG | PS5-08-61BT-0001 | METEOCEAN JUNCTION BOX | FIELD
2899 | Telecom | PS5-08-61BT-0001-CC02 | PS5-08-14CB-1201 | SII SP1 CABINET | OFF. & FACILITIES BLDG | PS5-08-61BT-0001 | METEOCEAN JUNCTION BOX | FIELD
2900 | Telecom | PS5-08-61BT-0001-CN01 | PS5-08-14CB-1201 | SII SP1 CABINET | OFF. & FACILITIES BLDG | PS5-08-61BT-0001 | METEOCEAN JUNCTION BOX | FIELD
2901 | Telecom | PS5-08-61BT-0002-CC01 | PS5-08-14CB-1201 | SII SP1 CABINET | OFF. & FACILITIES BLDG | PS5-08-61BT-0002 | METEOCEAN JUNCTION BOX | FIELD
2902 | Telecom | PS5-08-83SP-0001-CX01 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-83SP-0001 | IDS MANHOLE | OUTDOOR
2903 | Telecom | PS5-08-83SP-0001-CX02 | PS5-08-15CB-1001 | SII SP3 SEC CABINET | EITS BLDG / ITR | PS5-08-83SP-0001 | IDS MANHOLE | OUTDOOR
2904 | Telecom | PS5-08-36SP-0101-CX02 | PS5-08-35CB-1001 | OTN CABINET | EITS BLDG / ITR | PS5-08-36SP-0101 | PIPELINE SPLICE BOX | STATION FOC CHAMBER
2905 | Telecom | PS5-08-36SP-0102-CX02 | PS5-08-35CB-1001 | OTN CABINET | EITS BLDG / ITR | PS5-08-36SP-0102 | PIPELINE SPLICE BOX | STATION FOC CHAMBER
2906 | Telecom | PS5-08-36SP-0101-CX06 | PS5-08-36MH-0001 | 3RD PARTY FOC CHAMBER | FIELD | PS5-08-36SP-0101 | PIPELINE SPLICE BOX | STATION FOC CHAMBER
2907 | Telecom | PS5-08-36SP-0102-CX06 | PS5-08-36MH-0001 | 3RD PARTY FOC CHAMBER | FIELD | PS5-08-36SP-0102 | PIPELINE SPLICE BOX | STATION FOC CHAMBER
2908 | Telecom | PS5-08-11CB-1201-CX01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR
2909 | Telecom | PS5-08-11CB-1501-CX01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR | 06-July-2026 | CPP-RFI-68-65-05-0036
2910 | Telecom | PS5-08-11CB-1601-CX01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR
2911 | Telecom | PS5-08-11CB-1901-CX01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-11CB-1001 | SIE CABINET | EITS BLDG / ITR
2912 | Telecom | PS5-82-MBA-0002-CC01 | PS5-08-85BT-0023 | ACS JUNCTION BOX | FIELD | PS5-82-MBA-0002 | VEHICLE BARRIER | FIELD
2913 | Telecom | PS5-08-85BT-0001-CJ01 | PS5-08-15CP-0004 | CONTROL PANEL | FIELD | PS5-08-85BT-0001 | ACS JUNCTION BOX | FIELD
2914 | Telecom | PS5-08-52CM-0071-CA01 | PS5-08-15CP-0001 | CONTROL PANEL | FIELD | PS5-08-52CM-0071 | CCTV THERMAL CAMERA | FIELD
2915 | Telecom | PS5-08-52CM-0072-CA01 | PS5-08-15CP-0002 | CONTROL PANEL | FIELD | PS5-08-52CM-0072 | CCTV THERMAL CAMERA | FIELD
2916 | Telecom | PS5-08-52CM-0073-CA01 | PS5-08-15CP-0003 | CONTROL PANEL | FIELD | PS5-08-52CM-0073 | CCTV THERMAL CAMERA | FIELD
2917 | Telecom | PS5-08-52CM-0074-CA01 | PS5-08-15CP-0004 | CONTROL PANEL | FIELD | PS5-08-52CM-0074 | CCTV THERMAL CAMERA | FIELD
2918 | Telecom | PS5-08-52CM-0075-CA01 | PS5-08-15CP-0005 | CONTROL PANEL | FIELD | PS5-08-52CM-0075 | CCTV THERMAL CAMERA | FIELD
2919 | Telecom | PS5-08-52CM-0076-CA01 | PS5-08-15CP-0006 | CONTROL PANEL | FIELD | PS5-08-52CM-0076 | CCTV THERMAL CAMERA | FIELD
2920 | Telecom | PS5-08-52CM-0077-CA01 | PS5-08-15CP-0007 | CONTROL PANEL | FIELD | PS5-08-52CM-0077 | CCTV THERMAL CAMERA | FIELD
2921 | Telecom | PS5-08-52CM-0078-CA01 | PS5-08-15CP-0008 | CONTROL PANEL | FIELD | PS5-08-52CM-0078 | CCTV THERMAL CAMERA | FIELD
2922 | Telecom | PS5-08-01LS-0418-CR02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | EITS BLDG | PS5-08-01LS-0418 | PAGA LOUDSPEAKER | EITS BLDG
2923 | Telecom | PS5-08-01LS-0318-CR02 | PS5-08-01MP-0001 | MARSHALLING ENCLOSURE | EITS BLDG | PS5-08-01LS-0318 | PAGA LOUDSPEAKER | EITS BLDG
2924 | Telecom | PS5-08-13CB-1201-CJ01 | PS5-08-13CB-1201 | SII SP3 SAF CABINET | OFFICE & FACILITY BUILDING | PS5-04-PMC-0006 | INSTRUMENTATION CABINET | EITS BUILDING
2925 | Telecom | PS5-08-01PA-1201-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE BLDG/TER | PS5-08-01PA-1201 | PAGA ACCESS UNIT | OFFICE
2926 | Telecom | PS5-08-01PA-1201-CC01 | PS5-08-01BT-1203 | PAGA JUNCTION BOX | OFFICE BLDG/TER | PS5-08-01PA-1201 | PAGA ACCESS UNIT | OFFICE
2927 | Telecom | PS5-08-01BT-1203-CN01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE BLDG/TER | PS5-08-01BT-1203 | PAGA JUNCTION BOX | OFFICE
2928 | Telecom | PS5-08-01BT-1203-CN02 | PS5-08-11CB-1201 | SIE CABINET | OFFICE BLDG/TER | PS5-08-01BT-1203 | PAGA JUNCTION BOX | OFFICE
2929 | Telecom | PS5-08-01BT-1201-CR03 | PS5-08-01BT-1203 | PAGA JUNCTION BOX | OFFICE BLDG/TER | PS5-08-01BT-1201 | PAGA JUNCTION BOX | OFFICE
2930 | Telecom | PS5-08-01BT-1202-CR03 | PS5-08-01BT-1203 | PAGA JUNCTION BOX | OFFICE BLDG/TER | PS5-08-01BT-1202 | PAGA JUNCTION BOX | OFFICE
2931 | Telecom | PS5-08-85BR-1201-CC01 | PS5-08-85CP-1202 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BR-1201 | BADGE READER | MAIN ENTRANCE
2932 | Telecom | PS5-08-85DC-1201-CJ01 | PS5-08-85BT-1201 | ACS JUNCTION BOX | MAIN ENTRANCE | PS5-08-85DC-1201 | ACS DOOR CONTACT | MAIN ENTRANCE
2933 | Telecom | PS5-08-85ML-1201-CN01 | PS5-08-85BT-1201 | ACS JUNCTION BOX | MAIN ENTRANCE | PS5-08-85ML-1201 | MAGNETIC DOORLOCK | MAIN ENTRANCE
2934 | Telecom | PS5-08-85PB-1201-CJ01 | PS5-08-85BT-1201 | ACS JUNCTION BOX | MAIN ENTRANCE | PS5-08-85PB-1201 | EXIT PUSHBUTTON | MAIN ENTRANCE
2935 | Telecom | PS5-08-85BG-1201-CC01 | PS5-08-85BT-1201 | ACS JUNCTION BOX | MAIN ENTRANCE | PS5-08-85BG-1201 | EMERGENCY BREAK GLASS | MAIN ENTRANCE
2936 | Telecom | PS5-08-85BT-1201-CN01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-85BT-1201 | ACS JUNCTION BOX | MAIN ENTRANCE
2937 | Telecom | PS5-08-85BT-1201-CC01 | PS5-08-85CP-1202 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BT-1201 | ACS JUNCTION BOX | MAIN ENTRANCE
2938 | Telecom | PS5-08-85BR-1202-CC01 | PS5-08-85CP-1202 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BR-1202 | BADGE READER | CLINIC ENTRANCE
2939 | Telecom | PS5-08-85DC-1202-CJ01 | PS5-08-85BT-1202 | ACS JUNCTION BOX | CLINIC ENTRANCE | PS5-08-85DC-1202 | ACS DOOR CONTACT | CLINIC ENTRANCE
2940 | Telecom | PS5-08-85DC-1203-CJ01 | PS5-08-85BT-1202 | ACS JUNCTION BOX | CLINIC ENTRANCE | PS5-08-85DC-1203 | ACS DOOR CONTACT | CLINIC ENTRANCE
2941 | Telecom | PS5-08-85ML-1202-CN01 | PS5-08-85BT-1202 | ACS JUNCTION BOX | CLINIC ENTRANCE | PS5-08-85ML-1202 | MAGNETIC DOORLOCK | CLINIC ENTRANCE
2942 | Telecom | PS5-08-85PB-1202-CJ01 | PS5-08-85BT-1202 | ACS JUNCTION BOX | CLINIC ENTRANCE | PS5-08-85PB-1202 | EXIT PUSHBUTTON | CLINIC ENTRANCE
2943 | Telecom | PS5-08-85BG-1202-CC01 | PS5-08-85BT-1202 | ACS JUNCTION BOX | CLINIC ENTRANCE | PS5-08-85BG-1202 | EMERGENCY BREAK GLASS | CLINIC ENTRANCE
2944 | Telecom | PS5-08-85BT-1202-CN01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-85BT-1202 | ACS JUNCTION BOX | MAIN ENTRANCE
2945 | Telecom | PS5-08-85BT-1202-CC01 | PS5-08-85CP-1202 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BT-1202 | ACS JUNCTION BOX | CLINIC ENTRANCE
2946 | Telecom | PS5-08-85BR-1203-CC01 | PS5-08-85CP-1202 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BR-1203 | BADGE READER | DINING AREA
2947 | Telecom | PS5-08-85DC-1204-CJ01 | PS5-08-85BT-1203 | ACS JUNCTION BOX | DINING AREA | PS5-08-85DC-1204 | ACS DOOR CONTACT | DINING AREA
2948 | Telecom | PS5-08-85ML-1203-CN01 | PS5-08-85BT-1203 | ACS JUNCTION BOX | DINING AREA | PS5-08-85ML-1203 | MAGNETIC DOORLOCK | DINING AREA
2949 | Telecom | PS5-08-85PB-1203-CJ01 | PS5-08-85BT-1203 | ACS JUNCTION BOX | DINING AREA | PS5-08-85PB-1203 | EXIT PUSHBUTTON | DINING AREA
2950 | Telecom | PS5-08-85BG-1203-CC01 | PS5-08-85BT-1203 | ACS JUNCTION BOX | DINING AREA | PS5-08-85BG-1203 | EMERGENCY BREAK GLASS | DINING AREA
2951 | Telecom | PS5-08-85BT-1203-CN01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-85BT-1203 | ACS JUNCTION BOX | MAIN ENTRANCE
2952 | Telecom | PS5-08-85BT-1203-CC01 | PS5-08-85CP-1202 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BT-1203 | ACS JUNCTION BOX | DINING AREA
2953 | Telecom | PS5-08-85DC-1205-CJ01 | PS5-08-85BT-1204 | ACS JUNCTION BOX | TELECOM ROOM | PS5-08-85DC-1205 | ACS DOOR CONTACT | TELECOM ROOM
2954 | Telecom | PS5-08-85DC-1206-CJ01 | PS5-08-85BT-1204 | ACS JUNCTION BOX | TELECOM ROOM | PS5-08-85DC-1206 | ACS DOOR CONTACT | TELECOM ROOM
2955 | Telecom | PS5-08-85BR-1204-CC01 | PS5-08-85CP-1202 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BR-1204 | BADGE READER | TELECOM ROOM
2956 | Telecom | PS5-08-85DC-1207-CJ01 | PS5-08-85BT-1205 | ACS JUNCTION BOX | TELECOM ROOM | PS5-08-85DC-1207 | ACS DOOR CONTACT | TELECOM ROOM
2957 | Telecom | PS5-08-85ML-1204-CN01 | PS5-08-85BT-1205 | ACS JUNCTION BOX | TELECOM ROOM | PS5-08-85ML-1204 | MAGNETIC DOORLOCK | TELECOM ROOM
2958 | Telecom | PS5-08-85PB-1204-CJ01 | PS5-08-85BT-1205 | ACS JUNCTION BOX | TELECOM ROOM | PS5-08-85PB-1204 | EXIT PUSHBUTTON | TELECOM ROOM
2959 | Telecom | PS5-08-85BT-1205-CN01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-85BT-1205 | ACS JUNCTION BOX | MAIN ENTRANCE
2960 | Telecom | PS5-08-85BG-1204-CC01 | PS5-08-85BT-1205 | ACS JUNCTION BOX | TELECOM ROOM | PS5-08-85BG-1204 | EMERGENCY BREAK GLASS | TELECOM ROOM
2961 | Telecom | PS5-08-85BT-1205-CC01 | PS5-08-85CP-1202 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BT-1205 | ACS JUNCTION BOX | TELECOM ROOM
2962 | Telecom | PS5-08-85BT-1204-CJ01 | PS5-08-85CP-1201 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BT-1204 | ACS JUNCTION BOX | TELECOM ROOM
2963 | Telecom | PS5-08-85CP-1201-CA01 | PS5-08-11CB-1201 | SIE CABINET | TELECOM ROOM | PS5-08-85CP-1201 | ACS CONTROL PANEL | TELECOM ROOM
2964 | Telecom | PS5-08-85CP-1202-CA01 | PS5-08-11CB-1201 | SIE CABINET | TELECOM ROOM | PS5-08-85CP-1202 | ACS CONTROL PANEL | TELECOM ROOM
2965 | Telecom | PS5-08-52CM-1201-CA01 | PS5-08-11CB-1201 | SIE CABINET | TELECOM ROOM | PS5-08-52CM-1201 | OUTDOOR CAMERA | MAIN ENTRANCE
2966 | Telecom | PS5-08-52CM-1202-CA01 | PS5-08-11CB-1201 | SIE CABINET | TELECOM ROOM | PS5-08-52CM-1202 | OUTDOOR CAMERA | CLINIC ENTRANCE
2967 | Telecom | PS5-08-85BR-1205-CC01 | PS5-08-85CP-1201 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BR-1205 | POB CARD READER | SAFE HAVEN
2968 | Telecom | PS5-08-85BR-1206-CC01 | PS5-08-85CP-1202 | CONTROL PANEL | TELECOM ROOM | PS5-08-85BR-1206 | POB CARD READER | SAFE HAVEN
2969 | Telecom | PS5-08-85AP-1201-CA01 | PS5-08-71SK-1237 | RJ45 DATA SOCKET | OFFICE | PS5-08-85AP-1201 | WIRELESS ACCESS PONT | SAFE HAVEN
2970 | Telecom | PS5-08-85AP-1202-CA01 | PS5-08-71SK-1238 | RJ45 DATA SOCKET | OFFICE | PS5-08-85AP-1202 | WIRELESS ACCESS PONT | SAFE HAVEN
2971 | Telecom | PS5-08-71SK-1201-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1201 | RJ45 DATA SOCKET | OFFICE
2972 | Telecom | PS5-08-71SK-1202-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1202 | RJ45 DATA SOCKET | OFFICE
2973 | Telecom | PS5-08-71SK-1203-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1203 | RJ45 DATA SOCKET | OFFICE
2974 | Telecom | PS5-08-71SK-1204-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1204 | RJ45 DATA SOCKET | OFFICE
2975 | Telecom | PS5-08-71SK-1205-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1205 | RJ45 DATA SOCKET | OFFICE
2976 | Telecom | PS5-08-71SK-1206A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1206A | RJ45 DATA SOCKET | OFFICE
2977 | Telecom | PS5-08-71SK-1207-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1207 | RJ45 DATA SOCKET | OFFICE
2978 | Telecom | PS5-08-71SK-1208-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1208 | RJ45 DATA SOCKET | OFFICE
2979 | Telecom | PS5-08-71SK-1209-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1209 | RJ45 DATA SOCKET | OFFICE
2980 | Telecom | PS5-08-71SK-1210-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1210 | RJ45 DATA SOCKET | OFFICE
2981 | Telecom | PS5-08-71SK-1211-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1211 | RJ45 DATA SOCKET | OFFICE
2982 | Telecom | PS5-08-71SK-1212A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1212A | RJ45 DATA SOCKET | OFFICE
2983 | Telecom | PS5-08-71SK-1213-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1213 | RJ45 DATA SOCKET | OFFICE
2984 | Telecom | PS5-08-71SK-1213B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1213B | RJ45 DATA SOCKET | OFFICE
2985 | Telecom | PS5-08-71SK-1214A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1214A | RJ45 DATA SOCKET | OFFICE
2986 | Telecom | PS5-08-71SK-1214B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1214B | RJ45 DATA SOCKET | OFFICE
2987 | Telecom | PS5-08-71SK-1215A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1215A | RJ45 DATA SOCKET | OFFICE
2988 | Telecom | PS5-08-71SK-1215B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1215B | RJ45 DATA SOCKET | OFFICE
2989 | Telecom | PS5-08-71SK-1216A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1216A | RJ45 DATA SOCKET | OFFICE
2990 | Telecom | PS5-08-71SK-1216B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1216B | RJ45 DATA SOCKET | OFFICE
2991 | Telecom | PS5-08-71SK-1217A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1217A | RJ45 DATA SOCKET | OFFICE
2992 | Telecom | PS5-08-71SK-1217B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1217B | RJ45 DATA SOCKET | OFFICE
2993 | Telecom | PS5-08-71SK-1218A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1218A | RJ45 DATA SOCKET | OFFICE
2994 | Telecom | PS5-08-71SK-1218B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1218B | RJ45 DATA SOCKET | OFFICE
2995 | Telecom | PS5-08-71SK-1219A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1219A | RJ45 DATA SOCKET | OFFICE
2996 | Telecom | PS5-08-71SK-1219B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1219B | RJ45 DATA SOCKET | OFFICE
2997 | Telecom | PS5-08-71SK-1219C-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1219C | RJ45 DATA SOCKET | OFFICE
2998 | Telecom | PS5-08-71SK-1219D-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1219D | RJ45 DATA SOCKET | OFFICE
2999 | Telecom | PS5-08-71SK-1220A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1220A | RJ45 DATA SOCKET | OFFICE
3000 | Telecom | PS5-08-71SK-1220B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1220B | RJ45 DATA SOCKET | OFFICE
3001 | Telecom | PS5-08-71SK-1221A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1221A | RJ45 DATA SOCKET | OFFICE
3002 | Telecom | PS5-08-71SK-1221B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1221B | RJ45 DATA SOCKET | OFFICE
3003 | Telecom | PS5-08-71SK-1222A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1222A | RJ45 DATA SOCKET | OFFICE
3004 | Telecom | PS5-08-71SK-1222B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1222B | RJ45 DATA SOCKET | OFFICE
3005 | Telecom | PS5-08-71SK-1223A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1223A | RJ45 DATA SOCKET | OFFICE
3006 | Telecom | PS5-08-71SK-1223B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1223B | RJ45 DATA SOCKET | OFFICE
3007 | Telecom | PS5-08-71SK-1224A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1224A | RJ45 DATA SOCKET | OFFICE
3008 | Telecom | PS5-08-71SK-1224B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1224B | RJ45 DATA SOCKET | OFFICE
3009 | Telecom | PS5-08-71SK-1225A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1225A | RJ45 DATA SOCKET | OFFICE
3010 | Telecom | PS5-08-71SK-1226A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1226A | RJ45 DATA SOCKET | OFFICE
3011 | Telecom | PS5-08-71SK-1227A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1227A | RJ45 DATA SOCKET | OFFICE
3012 | Telecom | PS5-08-71SK-1227B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1227B | RJ45 DATA SOCKET | OFFICE
3013 | Telecom | PS5-08-71SK-1228A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1228A | RJ45 DATA SOCKET | OFFICE
3014 | Telecom | PS5-08-71SK-1229-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1229 | RJ45 DATA SOCKET | OFFICE
3015 | Telecom | PS5-08-71SK-1229B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1229B | RJ45 DATA SOCKET | OFFICE
3016 | Telecom | PS5-08-71SK-1230A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1230A | RJ45 DATA SOCKET | OFFICE
3017 | Telecom | PS5-08-71SK-1230B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1230B | RJ45 DATA SOCKET | OFFICE
3018 | Telecom | PS5-08-71SK-1231-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1231 | RJ45 DATA SOCKET | OFFICE
3019 | Telecom | PS5-08-71SK-1231B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1231B | RJ45 DATA SOCKET | OFFICE
3020 | Telecom | PS5-08-71SK-1232A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1232A | RJ45 DATA SOCKET | OFFICE
3021 | Telecom | PS5-08-71SK-1233A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1233A | RJ45 DATA SOCKET | OFFICE
3022 | Telecom | PS5-08-71SK-1234-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1234 | RJ45 DATA SOCKET | OFFICE
3023 | Telecom | PS5-08-71SK-1235-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1235 | RJ45 DATA SOCKET | OFFICE
3024 | Telecom | PS5-08-71SK-1236A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1236A | RJ45 DATA SOCKET | OFFICE
3025 | Telecom | PS5-08-71SK-1237-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1237 | RJ45 DATA SOCKET | OFFICE
3026 | Telecom | PS5-08-71SK-1238-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1238 | RJ45 DATA SOCKET | OFFICE
3027 | Telecom | PS5-08-71SK-1239-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1239 | RJ45 DATA SOCKET | OFFICE
3028 | Telecom | PS5-08-71SK-1240-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1240 | RJ45 DATA SOCKET | OFFICE
3029 | Telecom | PS5-08-71SK-1241A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1241A | RJ45 DATA SOCKET | OFFICE
3030 | Telecom | PS5-08-71SK-1241B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1241B | RJ45 DATA SOCKET | OFFICE
3031 | Telecom | PS5-08-71SK-1242A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1242A | RJ45 DATA SOCKET | OFFICE
3032 | Telecom | PS5-08-71SK-1243A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1243A | RJ45 DATA SOCKET | OFFICE
3033 | Telecom | PS5-08-71SK-1244A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1244A | RJ45 DATA SOCKET | OFFICE
3034 | Telecom | PS5-08-71SK-1245A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1245A | RJ45 DATA SOCKET | OFFICE
3035 | Telecom | PS5-08-71SK-1246A-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1246A | RJ45 DATA SOCKET | OFFICE
3036 | Telecom | PS5-08-71SK-1246B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1246B | RJ45 DATA SOCKET | OFFICE
3037 | Telecom | PS5-08-71SK-1247-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1247 | RJ45 DATA SOCKET | OFFICE
3038 | Telecom | PS5-08-71SK-1248-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1248 | RJ45 DATA SOCKET | OFFICE
3039 | Telecom | PS5-08-03AF-1201-CA01 | PS5-08-71SK-1228A | RJ45 DATA SOCKET | OFFICE | PS5-08-03AF-1201 | AUDIO CONFERENCE PHONE | OFFICE
3040 | Telecom | PS5-08-55VF-1201-CA01 | PS5-08-71SK-1230A | RJ45 DATA SOCKET | OFFICE | PS5-08-55VF-1201 | VIDEO CONFERENCE UNIT | OFFICE
3041 | Telecom | PS5-08-23LA-1201-CV01 | PS5-08-23BS-1201 | RADIO BASESTATION | OFFICE | PS5-08-23LA-1201 | LIGHTNING ARRESTOR | OFFICE
3042 | Telecom | PS5-08-23AN-0001-CV01 | PS5-08-23LA-1201 | LIGHTNING ARRESTOR | OFFICE | PS5-08-23AN-0001 | VHF ANTENNA | OFFICE
3043 | Telecom | PS5-08-23LA-1202-CV01 | PS5-08-13CB-1201 | SII SP3 SAF CABINET | OFFICE | PS5-08-23LA-1202 | LIGHTNING ARRESTOR | OFFICE
3044 | Telecom | PS5-08-23AN-0901-CV01 | PS5-08-23LA-1202 | LIGHTNING ARRESTOR | OFFICE | PS5-08-23AN-0901 | VHF ANTENNA | TELECOM TOWER
3045 | Telecom | PS5-08-23AN-1201-CV01 | PS5-08-13CB-1201 | SII SP3 SAF CABINET | OFFICE | PS5-08-23AN-1201 | INDOOR ANTENNA | OFFICE
3046 | Telecom | PS5-08-34LA-1201-CV01 | PS5-08-34DS-1211 | SAT. PHONE BIAS BOX | OFFICE | PS5-08-34LA-1201 | LIGHTNING ARRESTOR | OFFICE
3047 | Telecom | PS5-08-34AN-0001-CV01 | PS5-08-34LA-1201 | LIGHTNING ARRESTOR | OFFICE | PS5-08-34AN-0001 | SAT. PHONE ANTENNA | OFFICE
3048 | Telecom | PS5-08-51SK-1201-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51SK-1201 | ENTERTAINMENT TV SOCKET | OFFICE
3049 | Telecom | PS5-08-51SK-1202-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51SK-1202 | ENTERTAINMENT TV SOCKET | OFFICE
3050 | Telecom | PS5-08-51SK-1203-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51SK-1203 | ENTERTAINMENT TV SOCKET | OFFICE
3051 | Telecom | PS5-08-51SK-1204-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51SK-1204 | ENTERTAINMENT TV SOCKET | OFFICE
3052 | Telecom | PS5-08-51SK-1205-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51SK-1205 | ENTERTAINMENT TV SOCKET | OFFICE
3053 | Telecom | PS5-08-51SK-1206-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51SK-1206 | ENTERTAINMENT TV SOCKET | OFFICE
3054 | Telecom | PS5-08-51SK-1207-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51SK-1207 | ENTERTAINMENT TV SOCKET | OFFICE
3055 | Telecom | PS5-08-51SK-1208-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51SK-1208 | ENTERTAINMENT TV SOCKET | OFFICE
3056 | Telecom | PS5-08-51SK-1209-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51SK-1209 | ENTERTAINMENT TV SOCKET | OFFICE
3057 | Telecom | PS5-08-51SK-1210-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51SK-1210 | ENTERTAINMENT TV SOCKET | OFFICE
3058 | Telecom | PS5-08-51LA-1201-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51LA-1201 | LIGHTNING ARRESTOR | OFFICE
3059 | Telecom | PS5-08-51AN-0001-CV01 | PS5-08-51LA-1201 | LIGHTNING ARRESTOR | OFFICE | PS5-08-51AN-0001 | SATELLITE ANTENNA | OFFICE
3060 | Telecom | PS5-08-51LA-1202-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51LA-1202 | LIGHTNING ARRESTOR | OFFICE
3061 | Telecom | PS5-08-51AN-0001-CV02 | PS5-08-51LA-1202 | LIGHTNING ARRESTOR | OFFICE | PS5-08-51AN-0001 | SATELLITE ANTENNA | OFFICE
3062 | Telecom | PS5-08-51LA-1203-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51LA-1203 | LIGHTNING ARRESTOR | OFFICE
3063 | Telecom | PS5-08-51AN-0001-CV03 | PS5-08-51LA-1203 | LIGHTNING ARRESTOR | OFFICE | PS5-08-51AN-0001 | SATELLITE ANTENNA | OFFICE
3064 | Telecom | PS5-08-51LA-1204-CV01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-51LA-1204 | LIGHTNING ARRESTOR | OFFICE
3065 | Telecom | PS5-08-51AN-0001-CV04 | PS5-08-51LA-1204 | LIGHTNING ARRESTOR | OFFICE | PS5-08-51AN-0001 | SATELLITE ANTENNA | OFFICE
3066 | Telecom | PS5-08-01BT-1202-CN01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-01BT-1202 | PAGA JUNCTION BOX | OFFICE
3067 | Telecom | PS5-08-01BT-1201-CN01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-01BT-1201 | PAGA JUNCTION BOX | OFFICE
3068 | Telecom | PS5-08-13CB-1201-CX01 | PS5-08-11CB-1601 | SIE CABINET | OFFICE | PS5-08-13CB-1201 | SII SP3 SAF CABINET | OFFICE
3069 | Telecom | PS5-08-14CB-1201-CX01 | PS5-08-11CB-1601 | SIE CABINET | OFFICE | PS5-08-14CB-1201 | SII SP1 CABINET | OFFICE
3070 | Telecom | PS5-08-71SK-1206B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1206B | RJ45 DATA SOCKET | OFFICE
3071 | Telecom | PS5-08-71SK-1212B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1212B | RJ45 DATA SOCKET | OFFICE
3072 | Telecom | PS5-08-71SK-1214C-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1214C | RJ45 DATA SOCKET | OFFICE
3073 | Telecom | PS5-08-71SK-1214D-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1214D | RJ45 DATA SOCKET | OFFICE
3074 | Telecom | PS5-08-71SK-1225B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1225B | RJ45 DATA SOCKET | OFFICE
3075 | Telecom | PS5-08-71SK-1226B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1226B | RJ45 DATA SOCKET | OFFICE
3076 | Telecom | PS5-08-71SK-1228B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1228B | RJ45 DATA SOCKET | OFFICE
3077 | Telecom | PS5-08-71SK-1232B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1232B | RJ45 DATA SOCKET | OFFICE
3078 | Telecom | PS5-08-71SK-1233B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1233B | RJ45 DATA SOCKET | OFFICE
3079 | Telecom | PS5-08-71SK-1236B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1236B | RJ45 DATA SOCKET | OFFICE
3080 | Telecom | PS5-08-71SK-1242B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1242B | RJ45 DATA SOCKET | OFFICE
3081 | Telecom | PS5-08-71SK-1243B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1243B | RJ45 DATA SOCKET | OFFICE
3082 | Telecom | PS5-08-71SK-1244B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1244B | RJ45 DATA SOCKET | OFFICE
3083 | Telecom | PS5-08-71SK-1245B-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-71SK-1245B | RJ45 DATA SOCKET | OFFICE
3084 | Telecom | PS5-08-71SK-1249A-CA01 | PS5-08-11CB-1201 | SIE / SII SP3 SEC CABINET | TELECOM ROOM | PS5-08-71SK-1249A | RJ45 DATA SOCKET | OFFICE
3085 | Telecom | PS5-08-71SK-1249B-CA01 | PS5-08-11CB-1201 | SIE / SII SP3 SEC CABINET | TELECOM ROOM | PS5-08-71SK-1249B | RJ45 DATA SOCKET | OFFICE
3086 | Telecom | PS5-08-71SK-1249C-CA01 | PS5-08-11CB-1201 | SIE / SII SP3 SEC CABINET | TELECOM ROOM | PS5-08-71SK-1249C | RJ45 DATA SOCKET | OFFICE
3087 | Telecom | PS5-08-71SK-1249D-CA01 | PS5-08-11CB-1201 | SIE / SII SP3 SEC CABINET | TELECOM ROOM | PS5-08-71SK-1249D | RJ45 DATA SOCKET | OFFICE
3088 | Telecom | PS5-08-71SK-1250A-CA01 | PS5-08-11CB-1201 | SIE / SII SP3 SEC CABINET | TELECOM ROOM | PS5-08-71SK-1250A | RJ45 DATA SOCKET | OFFICE
3089 | Telecom | PS5-08-71SK-1250B-CA01 | PS5-08-11CB-1201 | SIE / SII SP3 SEC CABINET | TELECOM ROOM | PS5-08-71SK-1250B | RJ45 DATA SOCKET | OFFICE
3090 | Telecom | PS5-08-13CB-1201-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-13CB-1201 | SP3 SAF CABINET | OFFICE
3091 | Telecom | PS5-08-13CB-1201-CA02 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-13CB-1201 | SP3 SAF CABINET | OFFICE
3092 | Telecom | PS5-08-13CB-1201-CA03 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-13CB-1201 | SP3 SAF CABINET | OFFICE
3093 | Telecom | PS5-08-13CB-1201-CA04 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-13CB-1201 | SP3 SAF CABINET | OFFICE
3094 | Telecom | PS5-08-13CB-1201-CA05 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-13CB-1201 | SP3 SAF CABINET | OFFICE
3095 | Telecom | PS5-08-13CB-1201-CA06 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-13CB-1201 | SP3 SAF CABINET | OFFICE
3096 | Telecom | PS5-08-14CB-1201-CA01 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-14CB-1201 | SII SP1 CABINET | OFFICE
3097 | Telecom | PS5-08-14CB-1201-CA02 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-14CB-1201 | SII SP1 CABINET | OFFICE
3098 | Telecom | PS5-08-14CB-1201-CA03 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-14CB-1201 | SII SP1 CABINET | OFFICE
3099 | Telecom | PS5-08-14CB-1201-CA04 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-14CB-1201 | SII SP1 CABINET | OFFICE
3100 | Telecom | PS5-08-14CB-1201-CA05 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-14CB-1201 | SII SP1 CABINET | OFFICE
3101 | Telecom | PS5-08-14CB-1201-CA06 | PS5-08-11CB-1201 | SIE CABINET | OFFICE | PS5-08-14CB-1201 | SII SP1 CABINET | OFFICE
3102 | Telecom | PS5-08-13CB-1201-CC01 | PS5-08-13CB-1201 | SII SP3 SAF CABINET | OFFICE | PS5-08-14CB-1201 | SII SP1 CABINET | OFFICE
3103 | Telecom | PS5-08-01PA-1501-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-01PA-1501 | PAGA ACCESS UNIT | GUARDHOUSE
3104 | Telecom | PS5-08-01PA-1501-CC01 | PS5-08-01BT-1503 | PAGA JUNCTION BOX | GUARDHOUSE | PS5-08-01PA-1501 | PAGA ACCESS UNIT | GUARDHOUSE
3105 | Telecom | PS5-08-01BT-1503-CN01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-01BT-1503 | PAGA JUNCTION BOX | GUARDHOUSE
3106 | Telecom | PS5-08-01BT-1503-CN02 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-01BT-1503 | PAGA JUNCTION BOX | GUARDHOUSE
3107 | Telecom | PS5-08-01BT-1501-CR02 | PS5-08-01BT-1503 | PAGA JUNCTION BOX | GUARDHOUSE | PS5-08-01BT-1501 | PAGA JUNCTION BOX | GUARDHOUSE
3108 | Telecom | PS5-08-01BT-1502-CR02 | PS5-08-01BT-1503 | PAGA JUNCTION BOX | GUARDHOUSE | PS5-08-01BT-1502 | PAGA JUNCTION BOX | GUARDHOUSE
3109 | Telecom | PS5-08-85DC-1501-CJ01 | PS5-08-85BT-1501 | ACS JUNCTION BOX | EMERGENCY EXIT | PS5-08-85DC-1501 | ACS DOOR CONTACT | EMERGENCY EXIT
3110 | Telecom | PS5-08-85BT-1501-CJ01 | PS5-08-85CP-1501 | ACS CONTROL PANEL | SAFE HAVEN | PS5-08-85BT-1501 | ACS JUNCTION BOX | EMERGENCY EXIT
3111 | Telecom | PS5-08-85DC-1502-CJ01 | PS5-08-85BT-1502 | ACS JUNCTION BOX | ENTRANCE | PS5-08-85DC-1502 | ACS DOOR CONTACT | ENTRANCE
3112 | Telecom | PS5-08-85BT-1502-CJ01 | PS5-08-85CP-1501 | ACS CONTROL PANEL | SAFE HAVEN | PS5-08-85BT-1502 | ACS JUNCTION BOX | ENTRANCE
3113 | Telecom | PS5-08-85BR-1501-CC01 | PS5-08-85CP-1501 | ACS CONTROL PANEL | SECURITY ROOM | PS5-08-85BR-1501 | BADGE READER | SAFE HAVEN
3114 | Telecom | PS5-08-85BR-1502-CC01 | PS5-08-85CP-1501 | ACS CONTROL PANEL | SECURITY ROOM | PS5-08-85BR-1502 | BADGE READER | SAFE HAVEN
3115 | Telecom | PS5-08-85DC-1503-CJ01 | PS5-08-85BT-1503 | ACS JUNCTION BOX | SAFE HAVEN | PS5-08-85DC-1503 | ACS DOOR CONTACT | SAFE HAVEN
3116 | Telecom | PS5-08-85ML-1501-CN01 | PS5-08-85BT-1503 | ACS JUNCTION BOX | SAFE HAVEN | PS5-08-85ML-1501 | MAGNETIC DOORLOCK | SAFE HAVEN
3117 | Telecom | PS5-08-85BG-1501-CC01 | PS5-08-85BT-1503 | ACS JUNCTION BOX | SAFE HAVEN | PS5-08-85BG-1501 | EMERGENCY BREAK GLASS | SAFE HAVEN
3118 | Telecom | PS5-08-85BT-1503-CN01 | PS5-08-11CB-1501 | SIE CABINET | SECURITY ROOM | PS5-08-85BT-1503 | ACS JUNCTION BOX | SAFE HAVEN
3119 | Telecom | PS5-08-85BT-1503-CC01 | PS5-08-85CP-1501 | ACS CONTROL PANEL | SECURITY ROOM | PS5-08-85BT-1503 | ACS JUNCTION BOX | SAFE HAVEN
3120 | Telecom | PS5-08-85PB-1501-CJ01 | PS5-08-85CP-1501 | ACS CONTROL PANEL | SECURITY ROOM | PS5-08-85PB-1501 | PANIC PUSHBUTTON | SECURITY ROOM
3121 | Telecom | PS5-08-85CP-1501-CA01 | PS5-08-11CB-1501 | SIE CABINET | SECURITY ROOM | PS5-08-85CP-1501 | ACS CONTROL PANEL | SECURITY ROOM
3122 | Telecom | PS5-08-71SK-1501A-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1501A | RJ45 DATA SOCKET | GUARDHOUSE
3123 | Telecom | PS5-08-71SK-1501B-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1501B | RJ45 DATA SOCKET | GUARDHOUSE
3124 | Telecom | PS5-08-71SK-1502A-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1502A | RJ45 DATA SOCKET | GUARDHOUSE
3125 | Telecom | PS5-08-71SK-1502B-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1502B | RJ45 DATA SOCKET | GUARDHOUSE
3126 | Telecom | PS5-08-71SK-1503A-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1503A | RJ45 DATA SOCKET | GUARDHOUSE
3127 | Telecom | PS5-08-71SK-1503B-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1503B | RJ45 DATA SOCKET | GUARDHOUSE
3128 | Telecom | PS5-08-71SK-1504A-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1504A | RJ45 DATA SOCKET | GUARDHOUSE
3129 | Telecom | PS5-08-71SK-1504B-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1504B | RJ45 DATA SOCKET | GUARDHOUSE
3130 | Telecom | PS5-08-71SK-1505-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1505 | RJ45 DATA SOCKET | GUARDHOUSE
3131 | Telecom | PS5-08-71SK-1506-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1506 | RJ45 DATA SOCKET | GUARDHOUSE
3132 | Telecom | PS5-08-71SK-1507-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1507 | RJ45 DATA SOCKET | GUARDHOUSE
3133 | Telecom | PS5-08-71SK-1508-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1508 | RJ45 DATA SOCKET | GUARDHOUSE
3134 | Telecom | PS5-08-71SK-1509-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1509 | RJ45 DATA SOCKET | GUARDHOUSE
3135 | Telecom | PS5-08-71SK-1511A-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1511A | RJ45 DATA SOCKET | GUARDHOUSE
3136 | Telecom | PS5-08-71SK-1511B-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1511B | RJ45 DATA SOCKET | GUARDHOUSE
3137 | Telecom | PS5-08-71SK-1512-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1512 | RJ45 DATA SOCKET | GUARDHOUSE
3138 | Telecom | PS5-08-71SK-1513-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1513 | RJ45 DATA SOCKET | GUARDHOUSE
3139 | Telecom | PS5-08-71SK-1514A-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1514A | RJ45 DATA SOCKET | GUARDHOUSE
3140 | Telecom | PS5-08-71SK-1514B-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1514B | RJ45 DATA SOCKET | GUARDHOUSE
3141 | Telecom | PS5-08-34LA-1501-CV01 | PS5-08-34DS-1511 | SAT. PHONE BIAS BOX | GUARDHOUSE | PS5-08-34LA-1501 | LIGHTNING ARRESTOR | GUARDHOUSE
3142 | Telecom | PS5-08-34AN-0002-CV01 | PS5-08-34LA-1501 | LIGHTNING ARRESTOR | GUARDHOUSE | PS5-08-34AN-0002 | SAT. PHONE ANTENNA | GUARDHOUSE
3143 | Telecom | PS5-08-23LA-1501-CV01 | PS5-08-23BS-1501 | VHF RADIO BASESTATION | GUARDHOUSE | PS5-08-23LA-1501 | LIGHTNING ARRESTOR | GUARDHOUSE
3144 | Telecom | PS5-08-23AN-0002-CV01 | PS5-08-23LA-1501 | LIGHTNING ARRESTOR | GUARDHOUSE | PS5-08-23AN-0002 | VHF ANTENNA | GUARDHOUSE
3145 | Telecom | PS5-08-71SK-1510A-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1510A | RJ45 DATA SOCKET | GUARDHOUSE
3146 | Telecom | PS5-08-71SK-1510B-CA01 | PS5-08-11CB-1501 | SIE CABINET | GUARDHOUSE | PS5-08-71SK-1510B | RJ45 DATA SOCKET | GUARDHOUSE
3147 | Telecom | PS5-08-85DC-1601-CJ01 | PS5-08-85BT-1601 | ACS JUNCTION BOX | WAREHOUSE RAMP | PS5-08-85DC-1601 | ACS DOOR CONTACT | WAREHOUSE RAMP
3148 | Telecom | PS5-08-85BT-1601-CJ01 | PS5-08-85CP-1601 | CONTROL PANEL | ELECT./TELECOM ROOM | PS5-08-85BT-1601 | ACS JUNCTION BOX | WAREHOUSE RAMP
3149 | Telecom | PS5-08-85DC-1602-CJ01 | PS5-08-85BT-1602 | ACS JUNCTION BOX | WAREHOUSE EMERGENCY | PS5-08-85DC-1602 | ACS DOOR CONTACT | WAREHOUSE EMERGENCY
3150 | Telecom | PS5-08-85BT-1602-CJ01 | PS5-08-85CP-1601 | CONTROL PANEL | ELECT./TELECOM ROOM | PS5-08-85BT-1602 | ACS JUNCTION BOX | WAREHOUSE EMERGENCY
3151 | Telecom | PS5-08-85DC-1603-CJ01 | PS5-08-85BT-1603 | ACS JUNCTION BOX | WORKSHOP/WAREHOUSE | PS5-08-85DC-1603 | ACS DOOR CONTACT | WAREHOUSE ACCESS
3152 | Telecom | PS5-08-85DC-1604-CJ01 | PS5-08-85BT-1603 | ACS JUNCTION BOX | WORKSHOP/WAREHOUSE | PS5-08-85DC-1604 | ACS DOOR CONTACT | WAREHOUSE ACCESS
3153 | Telecom | PS5-08-85ML-1601-CN01 | PS5-08-85BT-1603 | ACS JUNCTION BOX | WORKSHOP/WAREHOUSE | PS5-08-85ML-1601 | MAGNETIC DOORLOCK | WAREHOUSE ACCESS
3154 | Telecom | PS5-08-85PB-1601-CJ01 | PS5-08-85BT-1603 | ACS JUNCTION BOX | WORKSHOP/WAREHOUSE | PS5-08-85PB-1601 | EXIT PUSHBUTTON | WAREHOUSE ACCESS
3155 | Telecom | PS5-08-85BG-1601-CC01 | PS5-08-85BT-1603 | ACS JUNCTION BOX | WORKSHOP/WAREHOUSE | PS5-08-85BG-1601 | EMERGENCY BREAK GLASS | WAREHOUSE ACCESS
3156 | Telecom | PS5-08-85BT-1603-CC01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1603 | ACS JUNCTION BOX | WAREHOUSE ACCESS
3157 | Telecom | PS5-08-85BR-1601-CC01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BR-1601 | BADGE READER | WORKSHOP/WAREHOUSE
3158 | Telecom | PS5-08-85BT-1603-CN01 | PS5-08-11CB-1601 | SIE CABINET | ELECT./TELECOM ROOM | PS5-08-85BT-1603 | ACS JUNCTION BOX | WORKSHOP/WAREHOUSE
3159 | Telecom | PS5-08-85DC-1605-CJ01 | PS5-08-85BT-1604 | ACS JUNCTION BOX | WORKSHOP/WAREHOUSE | PS5-08-85DC-1605 | ACS DOOR CONTACT | WORKSHOP/WAREHOUSE
3160 | Telecom | PS5-08-85DC-1606-CJ01 | PS5-08-85BT-1604 | ACS JUNCTION BOX | WORKSHOP/WAREHOUSE | PS5-08-85DC-1606 | ACS DOOR CONTACT | WORKSHOP/WAREHOUSE
3161 | Telecom | PS5-08-85BT-1604-CJ01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1604 | ACS JUNCTION BOX | WORKSHOP/WAREHOUSE
3162 | Telecom | PS5-08-85BR-1604-CC01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BR-1604 | BADGE READER | WORKSHOP/WAREHOUSE
3163 | Telecom | PS5-08-85DC-1607-CJ01 | PS5-08-85BT-1607 | ACS JUNCTION BOX | AC CONTROLLED STORE | PS5-08-85DC-1607 | ACS DOOR CONTACT | WORKSHOP/WAREHOUSE
3164 | Telecom | PS5-08-85ML-1605-CN01 | PS5-08-85BT-1607 | ACS JUNCTION BOX | AC CONTROLLED STORE | PS5-08-85ML-1605 | MAGNETIC DOORLOCK | WORKSHOP/WAREHOUSE
3165 | Telecom | PS5-08-85PB-1604-CJ01 | PS5-08-85BT-1607 | ACS JUNCTION BOX | AC CONTROLLED STORE | PS5-08-85PB-1604 | EXIT PUSHBUTTON | WORKSHOP/WAREHOUSE
3166 | Telecom | PS5-08-85BG-1604-CC01 | PS5-08-85BT-1607 | ACS JUNCTION BOX | AC CONTROLLED STORE | PS5-08-85BG-1604 | EMERGENCY BREAK GLASS | WORKSHOP/WAREHOUSE
3167 | Telecom | PS5-08-85BT-1607-CC01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1607 | ACS JUNCTION BOX | WORKSHOP/WAREHOUSE
3168 | Telecom | PS5-08-85BT-1607-CN01 | PS5-08-11CB-1601 | SIE CABINET | ELECT./TELECOM ROOM | PS5-08-85BT-1607 | ACS JUNCTION BOX | AC CONTROLLED STORE
3169 | Telecom | PS5-08-85BR-1603-CC01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BR-1603 | BADGE READER | ELEC. INS. STORE ENTRANCE
3170 | Telecom | PS5-08-85DC-1608-CJ01 | PS5-08-85BT-1606 | ACS JUNCTION BOX | ELEC. INS. STORE ENTRANCE | PS5-08-85DC-1608 | ACS DOOR CONTACT | ELEC. INS. STORE ENTRANCE
3171 | Telecom | PS5-08-85DC-1609-CJ01 | PS5-08-85BT-1606 | ACS JUNCTION BOX | ELEC. INS. STORE ENTRANCE | PS5-08-85DC-1609 | ACS DOOR CONTACT | ELEC. INS. STORE ENTRANCE
3172 | Telecom | PS5-08-85ML-1603-CN01 | PS5-08-85BT-1606 | ACS JUNCTION BOX | ELEC. INS. STORE ENTRANCE | PS5-08-85ML-1603 | MAGNETIC DOORLOCK | ELEC. INS. STORE ENTRANCE
3173 | Telecom | PS5-08-85PB-1603-CJ01 | PS5-08-85BT-1606 | ACS JUNCTION BOX | ELEC. INS. STORE ENTRANCE | PS5-08-85PB-1603 | EXIT PUSHBUTTON | ELEC. INS. STORE ENTRANCE
3174 | Telecom | PS5-08-85BG-1603-CC01 | PS5-08-85BT-1606 | ACS JUNCTION BOX | ELEC. INS. STORE ENTRANCE | PS5-08-85BG-1603 | EMERGENCY BREAK GLASS | ELEC. INS. STORE ENTRANCE
3175 | Telecom | PS5-08-85BT-1606-CC01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1606 | ACS JUNCTION BOX | ELEC. INS. STORE ENTRANCE
3176 | Telecom | PS5-08-85BT-1606-CN01 | PS5-08-11CB-1601 | SIE CABINET | ELECT./TELECOM ROOM | PS5-08-85BT-1606 | ACS JUNCTION BOX | ELEC. INS. STORE ENTRANCE
3177 | Telecom | PS5-08-85BR-1602-CC01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BR-1602 | BADGE READER | WAREHOUSE OFFICE ENTRANCE
3178 | Telecom | PS5-08-85DC-1617-CJ01 | PS5-08-85BT-1605 | ACS JUNCTION BOX | WAREHOUSE OFFICE ENTRANCE | PS5-08-85DC-1617 | ACS DOOR CONTACT | WAREHOUSE OFFICE ENTRANCE
3179 | Telecom | PS5-08-85ML-1602-CN01 | PS5-08-85BT-1605 | ACS JUNCTION BOX | WAREHOUSE OFFICE ENTRANCE | PS5-08-85ML-1602 | MAGNETIC DOORLOCK | WAREHOUSE OFFICE ENTRANCE
3180 | Telecom | PS5-08-85PB-1602-CJ01 | PS5-08-85BT-1605 | ACS JUNCTION BOX | WAREHOUSE OFFICE ENTRANCE | PS5-08-85PB-1602 | EXIT PUSHBUTTON | WAREHOUSE OFFICE ENTRANCE
3181 | Telecom | PS5-08-85BG-1602-CC01 | PS5-08-85BT-1605 | ACS JUNCTION BOX | WAREHOUSE OFFICE ENTRANCE | PS5-08-85BG-1602 | EMERGENCY BREAK GLASS | WAREHOUSE OFFICE ENTRANCE
3182 | Telecom | PS5-08-85BT-1605-CC01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1605 | ACS JUNCTION BOX | WAREHOUSE OFFICE ENTRANCE
3183 | Telecom | PS5-08-85BT-1605-CN01 | PS5-08-11CB-1601 | SIE CABINET | ELECT./TELECOM ROOM | PS5-08-85BT-1605 | ACS JUNCTION BOX | WAREHOUSE OFFICE ENTRANCE
3184 | Telecom | PS5-08-85DC-1610-CJ01 | PS5-08-85BT-1614 | ACS JUNCTION BOX | WORKSHOP EMERG. ESCAPE | PS5-08-85DC-1610 | ACS DOOR CONTACT | WORKSHOP EMERG. ESCAPE
3185 | Telecom | PS5-08-85BT-1614-CJ01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1614 | ACS JUNCTION BOX | WORKSHOP EMERG. ESCAPE
3186 | Telecom | PS5-08-85DC-1611-CJ01 | PS5-08-85BT-1613 | ACS JUNCTION BOX | OIL SPILL RESPONSE STORE | PS5-08-85DC-1611 | ACS DOOR CONTACT | OIL SPILL RESPONSE STORE
3187 | Telecom | PS5-08-85DC-1612-CJ01 | PS5-08-85BT-1613 | ACS JUNCTION BOX | OIL SPILL RESPONSE STORE | PS5-08-85DC-1612 | ACS DOOR CONTACT | OIL SPILL RESPONSE STORE
3188 | Telecom | PS5-08-85BT-1613-CJ01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1613 | ACS JUNCTION BOX | OIL SPILL RESPONSE STORE
3189 | Telecom | PS5-08-85DC-1613-CJ01 | PS5-08-85BT-1612 | ACS JUNCTION BOX | AC CTRL. STORE EMERG. ESCAPE | PS5-08-85DC-1613 | ACS DOOR CONTACT | AC CTRL. STORE EMERG. ESCAPE
3190 | Telecom | PS5-08-85BT-1612-CJ01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1612 | ACS JUNCTION BOX | AC CTRL. STORE EMERG. ESCAPE
3191 | Telecom | PS5-08-85DC-1614-CJ01 | PS5-08-85BT-1611 | ACS JUNCTION BOX | WORKSHOP EMERG. ESCAPE | PS5-08-85DC-1614 | ACS DOOR CONTACT | WORKSHOP EMERG. ESCAPE
3192 | Telecom | PS5-08-85BT-1611-CJ01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1611 | ACS JUNCTION BOX | WORKSHOP EMERG. ESCAPE
3193 | Telecom | PS5-08-85DC-1615-CJ01 | PS5-08-85BT-1610 | ACS JUNCTION BOX | WORKSHOP RAMP | PS5-08-85DC-1615 | ACS DOOR CONTACT | WORKSHOP RAMP
3194 | Telecom | PS5-08-85BT-1610-CJ01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1610 | ACS JUNCTION BOX | WORKSHOP RAMP
3195 | Telecom | PS5-08-85DC-1616-CJ01 | PS5-08-85BT-1609 | ACS JUNCTION BOX | WORKSHOP ENTRANCE | PS5-08-85DC-1616 | ACS DOOR CONTACT | WORKSHOP ENTRANCE
3196 | Telecom | PS5-08-85BT-1609-CJ01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BT-1609 | ACS JUNCTION BOX | WORKSHOP ENTRANCE
3197 | Telecom | PS5-08-85BR-1605-CC01 | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE | PS5-08-85BR-1605 | BADGE READER | ELEC. INS. WORKSHOP ENTRANCE
3198 | Telecom | PS5-08-85DC-1618-CJ01 | PS5-08-85BT-1608 | ACS JUNCTION BOX | ELEC. INS. WORKSHOP ENTRANCE | PS5-08-85DC-1618 | ACS DOOR CONTACT | ELEC. INS. WORKSHOP ENTRANCE
3199 | Telecom | PS5-08-85ML-1604-CN01 | PS5-08-85BT-1608 | ACS JUNCTION BOX | ELEC. INS. WORKSHOP ENTRANCE | PS5-08-85ML-1604 | MAGNETIC DOORLOCK | ELEC. INS. WORKSHOP ENTRANCE
3200 | Telecom | PS5-08-85PB-1605-CJ01 | PS5-08-85BT-1608 | ACS JUNCTION BOX | ELEC. INS. WORKSHOP ENTRANCE | PS5-08-85PB-1605 | EXIT PUSHBUTTON | ELEC. INS. WORKSHOP ENTRANCE
3201 | Telecom | PS5-08-85BG-1605-CC01 | PS5-08-85BT-1608 | ACS JUNCTION BOX | ELEC. INS. WORKSHOP ENTRANCE | PS5-08-85BG-1605 | EMERGENCY BREAK GLASS | ELEC. INS. WORKSHOP ENTRANCE
3202 | Telecom | PS5-08-85BT-1608-CC01 | PS5-08-85CP-1601 | CONTROL PANEL | ELEC. INS. WORKSHOP ENTRANCE | PS5-08-85BT-1608 | ACS JUNCTION BOX | ELEC. INS. WORKSHOP ENTRANCE
3203 | Telecom | PS5-08-85CP-1601-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-85CP-1601 | CONTROL PANEL | WORKSHOP/WAREHOUSE
3204 | Telecom | PS5-08-85BT-1608-CN01 | PS5-08-11CB-1601 | SIE CABINET | ELECT./TELECOM ROOM | PS5-08-85BT-1608 | ACS JUNCTION BOX | ELEC. INS. STORE ENTRANCE
3205 | Telecom | PS5-08-71SK-1601A-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1601A | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3206 | Telecom | PS5-08-71SK-1601B-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1601B | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3207 | Telecom | PS5-08-71SK-1602A-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1602A | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3208 | Telecom | PS5-08-71SK-1602B-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1602B | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3209 | Telecom | PS5-08-71SK-1603A-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1603A | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3210 | Telecom | PS5-08-71SK-1603B-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1603B | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3211 | Telecom | PS5-08-71SK-1604A-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1604A | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3212 | Telecom | PS5-08-71SK-1604B-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1604B | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3213 | Telecom | PS5-08-71SK-1605A-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1605A | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3214 | Telecom | PS5-08-71SK-1605B-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1605B | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3215 | Telecom | PS5-08-71SK-1606-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1606 | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3216 | Telecom | PS5-08-71SK-1607-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1607 | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3217 | Telecom | PS5-08-71SK-1608-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1608 | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3218 | Telecom | PS5-08-71SK-1609-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1609 | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3219 | Telecom | PS5-08-71SK-1610-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1610 | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3220 | Telecom | PS5-08-71SK-1611-CA01 | PS5-08-11CB-1601 | SIE CABINET | WORKSHOP/WAREHOUSE | PS5-08-71SK-1611 | RJ45 DATA SOCKET | WORKSHOP/WAREHOUSE
3221 | Telecom | PS5-08-23AN-1601-CV01 | PS5-08-23LA-1601 | LIGHTNING ARRESTOR | WORKSHOP/WAREHOUSE | PS5-08-23AN-1601 | FLAT PANELANTENNA | WORKSHOP/WAREHOUSE
3222 | Telecom | PS5-08-23AN-0003-CV01 | PS5-08-23LA-1601 | LIGHTNING ARRESTOR | WORKSHOP/WAREHOUSE | PS5-08-23AN-0003 | INDOOR ANTENNA | WORKSHOP/WAREHOUSE
3223 | Telecom | PS5-08-85DC-1901-CJ01 | PS5-08-85BT-1903 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1901 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3224 | Telecom | PS5-08-85DC-1902-CJ01 | PS5-08-85BT-1903 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1902 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3225 | Telecom | PS5-08-85BT-1903-CJ01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1903 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3226 | Telecom | PS5-08-85DC-1903-CJ01 | PS5-08-85BT-1904 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1903 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3227 | Telecom | PS5-08-85DC-1904-CJ01 | PS5-08-85BT-1904 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1904 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3228 | Telecom | PS5-08-85BT-1904-CJ01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1904 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3229 | Telecom | PS5-08-85DC-1905-CJ01 | PS5-08-85BT-1905 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1905 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3230 | Telecom | PS5-08-85DC-1906-CJ01 | PS5-08-85BT-1905 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1906 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3231 | Telecom | PS5-08-85BT-1905-CJ01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1905 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3232 | Telecom | PS5-08-85DC-1907-CJ01 | PS5-08-85BT-1906 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1907 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3233 | Telecom | PS5-08-85DC-1908-CJ01 | PS5-08-85BT-1906 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1908 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3234 | Telecom | PS5-08-85BT-1906-CJ01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1906 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3235 | Telecom | PS5-08-85DC-1909-CJ01 | PS5-08-85BT-1907 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1909 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3236 | Telecom | PS5-08-85DC-1910-CJ01 | PS5-08-85BT-1907 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1910 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3237 | Telecom | PS5-08-85BT-1907-CJ01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1907 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3238 | Telecom | PS5-08-85DC-1911-CJ01 | PS5-08-85BT-1901 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1911 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3239 | Telecom | PS5-08-85ML-1901-CN01 | PS5-08-85BT-1901 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85ML-1901 | MAGNETIC DOORLOCK | GEN. ELECT. BLDG
3240 | Telecom | PS5-08-85PB-1901-CJ01 | PS5-08-85BT-1901 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85PB-1901 | EXIT PUSHBUTTON | GEN. ELECT. BLDG
3241 | Telecom | PS5-08-85BG-1901-CC01 | PS5-08-85BT-1901 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85BG-1901 | EMERGENCY BREAK GLASS | GEN. ELECT. BLDG
3242 | Telecom | PS5-08-85BR-1901-CC01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BR-1901 | BADGE READER | GEN. ELECT. BLDG
3243 | Telecom | PS5-08-85BT-1901-CN01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-85BT-1901 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3244 | Telecom | PS5-08-85BT-1901-CC01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1901 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3245 | Telecom | PS5-08-85BT-1901-CJ01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1901 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3246 | Telecom | PS5-08-85DC-1912-CJ01 | PS5-08-85BT-1902 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1912 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3247 | Telecom | PS5-08-85ML-1902-CN01 | PS5-08-85BT-1902 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85ML-1902 | MAGNETIC DOORLOCK | GEN. ELECT. BLDG
3248 | Telecom | PS5-08-85PB-1902-CJ01 | PS5-08-85BT-1902 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85PB-1902 | EXIT PUSHBUTTON | GEN. ELECT. BLDG
3249 | Telecom | PS5-08-85BG-1902-CC01 | PS5-08-85BT-1902 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85BG-1902 | EMERGENCY BREAK GLASS | GEN. ELECT. BLDG
3250 | Telecom | PS5-08-85BR-1902-CC01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BR-1902 | BADGE READER | GEN. ELECT. BLDG
3251 | Telecom | PS5-08-85BT-1902-CN01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-85BT-1902 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3252 | Telecom | PS5-08-85BT-1902-CC01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1902 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3253 | Telecom | PS5-08-85BT-1912-CJ01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1912 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3254 | Telecom | PS5-08-85DC-1913-CJ01 | PS5-08-85BT-1908 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1913 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3255 | Telecom | PS5-08-85DC-1914-CJ01 | PS5-08-85BT-1908 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1914 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3256 | Telecom | PS5-08-85DC-1915-CJ01 | PS5-08-85BT-1908 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1915 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3257 | Telecom | PS5-08-85BT-1908-CJ01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1908 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3258 | Telecom | PS5-08-85CP-1901-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG
3259 | Telecom | PS5-08-71SK-1901-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-71SK-1901 | RJ45 DATA SOCKET | GEN. ELECT. BLDG
3260 | Telecom | PS5-08-71SK-1903A-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-71SK-1903A | RJ45 DATA SOCKET | GEN. ELECT. BLDG
3261 | Telecom | PS5-08-71SK-1903B-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-71SK-1903B | RJ45 DATA SOCKET | GEN. ELECT. BLDG
3262 | Telecom | PS5-08-71SK-1904A-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-71SK-1904A | RJ45 DATA SOCKET | GEN. ELECT. BLDG
3263 | Telecom | PS5-08-71SK-1904B-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-71SK-1904B | RJ45 DATA SOCKET | GEN. ELECT. BLDG
3264 | Telecom | PS5-08-71SK-1905A-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-71SK-1905A | RJ45 DATA SOCKET | GEN. ELECT. BLDG
3265 | Telecom | PS5-08-71SK-1905B-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-71SK-1905B | RJ45 DATA SOCKET | GEN. ELECT. BLDG
3266 | Telecom | PS5-08-52CM-1901-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-52CM-1901 | DOME CAMERA | GEN. ELECT. BLDG
3267 | Telecom | PS5-08-52CM-1902-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-52CM-1902 | DUAL DOME CAMERA-1 | GEN. ELECT. BLDG
3268 | Telecom | PS5-08-52CM-1903-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-52CM-1903 | DUAL DOME CAMERA-2 | GEN. ELECT. BLDG
3269 | Telecom | PS5-08-23AN-1901-CV01 | PS5-08-23LA-1901 | LIGHTNING ARRESTOR | GEN. ELECT. BLDG | PS5-08-23AN-1901 | FLAT PANELANTENNA | GEN. ELECT. BLDG
3270 | Telecom | PS5-08-23AN-0005-CV01 | PS5-08-23LA-1901 | LIGHTNING ARRESTOR | GEN. ELECT. BLDG | PS5-08-23AN-0005 | INDOOR ANTENNA | GEN. ELECT. BLDG
3271 | Telecom | PS5-08-85DC-1916-CJ01 | PS5-08-85BT-1909 | ACS JUNCTION BOX | GEN. ELECT. BLDG | PS5-08-85DC-1916 | ACS DOOR CONTACT | GEN. ELECT. BLDG
3272 | Telecom | PS5-08-85BT-1909-CJ01 | PS5-08-85CP-1901 | CONTROL PANEL | GEN. ELECT. BLDG | PS5-08-85BT-1909 | ACS JUNCTION BOX | GEN. ELECT. BLDG
3273 | Telecom | PS5-08-12BT-1903-CX01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-12BT-1903 | WAP JUNCTION BOX | POWER GENERATOR BLDG
3274 | Telecom | PS5-08-12AP-1903-CN01 | PS5-08-12BT-1903 | WAP JUNCTION BOX | POWER GENERATOR BLDG | PS5-08-12AP-1903 | WIRELESS ACCESS POINT | POWER GENERATOR BLDG
3275 | Telecom | PS5-08-12BT-1904-CX01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-12BT-1904 | WAP JUNCTION BOX | POWER GENERATOR BLDG
3276 | Telecom | PS5-08-12AP-1904-CN01 | PS5-08-12BT-1904 | WAP JUNCTION BOX | POWER GENERATOR BLDG | PS5-08-12AP-1904 | WIRELESS ACCESS POINT | POWER GENERATOR BLDG
3277 | Telecom | PS5-08-03TP-1903-CJ01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-03TP-1903 | OUTDOOR TELEPHONE | POWER GENERATOR BLDG
3278 | Telecom | PS5-08-03TP-1903-CJ02 | PS5-08-03FB-1903 | FLASHING BEACON/SOUNDER | FIELD | PS5-08-03TP-1903 | OUTDOOR TELEPHONE | POWER GENERATOR BLDG
3279 | Telecom | PS5-08-03TP-1904-CJ01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-03TP-1904 | OUTDOOR TELEPHONE | POWER GENERATOR BLDG
3280 | Telecom | PS5-08-03TP-1904-CJ02 | PS5-08-03FB-1904 | FLASHING BEACON/SOUNDER | FIELD | PS5-08-03TP-1904 | OUTDOOR TELEPHONE | POWER GENERATOR BLDG
3281 | Telecom | PS5-08-52CM-0135-CX01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-52CM-0135 | CCTV SA PTZ CAMERA | POWER GENERATOR BLDG
3282 | Telecom | PS5-08-52TK-0135-CC01 | PS5-08-52CM-0135 | CCTV SA PTZ CAMERA | POWER GENERATOR BLDG | PS5-08-52TK-0135 | CCTV WATER TANK | POWER GENERATOR BLDG
3283 | Telecom | PS5-08-52CM-0136-CX01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-52CM-0136 | CCTV SA PTZ CAMERA | POWER GENERATOR BLDG
3284 | Telecom | PS5-08-52TK-0136-CC01 | PS5-08-52CM-0136 | CCTV SA PTZ CAMERA | POWER GENERATOR BLDG | PS5-08-52TK-0136 | CCTV WATER TANK | POWER GENERATOR BLDG
3285 | Telecom | PS5-08-52CM-0137-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-52CM-0137 | CCTV SA PTZ CAMERA | POWER GENERATOR BLDG
3286 | Telecom | PS5-08-52TK-0137-CC01 | PS5-08-52CM-0137 | CCTV SA PTZ CAMERA | POWER GENERATOR BLDG | PS5-08-52TK-0137 | CCTV WATER TANK | POWER GENERATOR BLDG
3287 | Telecom | PS5-08-52CM-0140-CA01 | PS5-08-11CB-1901 | SIE CABINET | GEN. ELECT. BLDG | PS5-08-52CM-0140 | CCTV SA PTZ CAMERA | POWER GENERATOR BLDG
3288 | Telecom | PS5-08-52TK-0140-CC01 | PS5-08-52CM-0140 | CCTV SA PTZ CAMERA | POWER GENERATOR BLDG | PS5-08-52TK-0140 | CCTV WATER TANK | POWER GENERATOR BLDG
3289 | Trace Heating | PS5-79-IG-0001-CL01 | PS5-79-IV-0001 | 63 kVA Transformer | Outdoor | PS5-79-IG-0001 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3290 | Trace Heating | PS5-79-IG-0002-CL01 | PS5-79-IV-0002 | 100 kVA Transformer | Outdoor | PS5-79-IG-0002 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3291 | Trace Heating | PS5-79-IG-0003-CL01 | PS5-79-IV-0003 | 63 kVA Transformer | Outdoor | PS5-79-IG-0003 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3292 | Trace Heating | PS5-79-IG-0004-CL01 | PS5-79-IV-0004 | 63 kVA Transformer | Outdoor | PS5-79-IG-0004 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3293 | Trace Heating | PS5-79-IG-0005-CL01 | PS5-79-IV-0005 | 100 kVA Transformer | Outdoor | PS5-79-IG-0005 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3294 | Trace Heating | PS5-79-IG-0006-CL01 | PS5-79-IV-0006 | 63 kVA Transformer | Outdoor | PS5-79-IG-0006 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3295 | Trace Heating | PS5-79-IG-0007-CL01 | PS5-79-IV-0007 | 100 kVA Transformer | Outdoor | PS5-79-IG-0007 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3296 | Trace Heating | PS5-79-IG-0008-CL01 | PS5-79-IV-0008 | 100 kVA Transformer | Outdoor | PS5-79-IG-0008 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3297 | Trace Heating | PS5-79-IG-0009-CL01 | PS5-79-IV-0009 | 100 kVA Transformer | Outdoor | PS5-79-IG-0009 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3298 | Trace Heating | PS5-79-IG-0010-CL01 | PS5-79-IV-0010 | 100 kVA Transformer | Outdoor | PS5-79-IG-0010 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3299 | Trace Heating | PS5-79-IG-0011-CL01 | PS5-79-IV-0011 | 100 kVA Transformer | Outdoor | PS5-79-IG-0011 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3300 | Trace Heating | PS5-79-IG-0012-CL01 | PS5-79-IV-0012 | 100 kVA Transformer | Outdoor | PS5-79-IG-0012 | Heat Tracing Panel | Field
3301 | Trace Heating | PS5-79-IG-0001-CG01 | PS5-79-IV-0001 | 63 kVA Transformer | Outdoor | PS5-79-IG-0001 | Heat Tracing Panel | Field
3302 | Trace Heating | PS5-79-IG-0002-CG01 | PS5-79-IV-0002 | 100 kVA Transformer | Outdoor | PS5-79-IG-0002 | Heat Tracing Panel | Field
3303 | Trace Heating | PS5-79-IG-0003-CG01 | PS5-79-IV-0003 | 63 kVA Transformer | Outdoor | PS5-79-IG-0003 | Heat Tracing Panel | Field
3304 | Trace Heating | PS5-79-IG-0004-CG01 | PS5-79-IV-0004 | 63 kVA Transformer | Outdoor | PS5-79-IG-0004 | Heat Tracing Panel | Field
3305 | Trace Heating | PS5-79-IG-0005-CG01 | PS5-79-IV-0005 | 100 kVA Transformer | Outdoor | PS5-79-IG-0005 | Heat Tracing Panel | Field
3306 | Trace Heating | PS5-79-IG-0006-CG01 | PS5-79-IV-0006 | 63 kVA Transformer | Outdoor | PS5-79-IG-0006 | Heat Tracing Panel | Field
3307 | Trace Heating | PS5-79-IG-0007-CG01 | PS5-79-IV-0007 | 100 kVA Transformer | Outdoor | PS5-79-IG-0007 | Heat Tracing Panel | Field
3308 | Trace Heating | PS5-79-IG-0008-CG01 | PS5-79-IV-0008 | 100 kVA Transformer | Outdoor | PS5-79-IG-0008 | Heat Tracing Panel | Field
3309 | Trace Heating | PS5-79-IG-0009-CG01 | PS5-79-IV-0009 | 100 kVA Transformer | Outdoor | PS5-79-IG-0009 | Heat Tracing Panel | Field
3310 | Trace Heating | PS5-79-IG-0010-CG01 | PS5-79-IV-0010 | 100 kVA Transformer | Outdoor | PS5-79-IG-0010 | Heat Tracing Panel | Field
3311 | Trace Heating | PS5-79-IG-0011-CG01 | PS5-79-IV-0011 | 100 kVA Transformer | Outdoor | PS5-79-IG-0011 | Heat Tracing Panel | Field
3312 | Trace Heating | PS5-79-IG-0012-CG01 | PS5-79-IV-0012 | 100 kVA Transformer | Outdoor | PS5-79-IG-0012 | Heat Tracing Panel | Field
3313 | Trace Heating | PS5-79-IG-0001-CD01 | PS5-79-IV-0001 | 63 kVA Transformer | Outdoor | PS5-79-IG-0001 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3314 | Trace Heating | PS5-79-IG-0002-CD01 | PS5-79-IV-0002 | 100 kVA Transformer | Outdoor | PS5-79-IG-0002 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3315 | Trace Heating | PS5-79-IG-0003-CD01 | PS5-79-IV-0003 | 63 kVA Transformer | Outdoor | PS5-79-IG-0003 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3316 | Trace Heating | PS5-79-IG-0004-CD01 | PS5-79-IV-0004 | 63 kVA Transformer | Outdoor | PS5-79-IG-0004 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3317 | Trace Heating | PS5-79-IG-0005-CD01 | PS5-79-IV-0005 | 100 kVA Transformer | Outdoor | PS5-79-IG-0005 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3318 | Trace Heating | PS5-79-IG-0006-CD01 | PS5-79-IV-0006 | 63 kVA Transformer | Outdoor | PS5-79-IG-0006 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3319 | Trace Heating | PS5-79-IG-0007-CD01 | PS5-79-IV-0007 | 100 kVA Transformer | Outdoor | PS5-79-IG-0007 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3320 | Trace Heating | PS5-79-IG-0008-CD01 | PS5-79-IV-0008 | 100 kVA Transformer | Outdoor | PS5-79-IG-0008 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3321 | Trace Heating | PS5-79-IG-0009-CD01 | PS5-79-IV-0009 | 100 kVA Transformer | Outdoor | PS5-79-IG-0009 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3322 | Trace Heating | PS5-79-IG-0010-CD01 | PS5-79-IV-0010 | 100 kVA Transformer | Outdoor | PS5-79-IG-0010 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3323 | Trace Heating | PS5-79-IG-0011-CD01 | PS5-79-IV-0011 | 100 kVA Transformer | Outdoor | PS5-79-IG-0011 | Heat Tracing Panel | Field | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
3324 | Trace Heating | PS5-79-IG-0012-CD01 | PS5-79-IV-0012 | 100 kVA Transformer | Outdoor | PS5-79-IG-0012 | Heat Tracing Panel | Field
3325 | Trace Heating | PS5-79-BE-0316-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0316 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3326 | Trace Heating | PS5-79-BE-0315-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0315 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3327 | Trace Heating | PS5-79-BE-0168-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0168 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3328 | Trace Heating | PS5-79-BE-0170-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0170 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3329 | Trace Heating | PS5-79-BE-0163-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0163 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3330 | Trace Heating | PS5-79-BE-0167-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0167 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3331 | Trace Heating | PS5-79-SP-0167-CL01 | PS5-79-BE-0167 | Heat Tracing Junction Box | Outdoor | PS5-79-SP-0167 | Heat Tracing Junction Box | Field
3332 | Trace Heating | PS5-79-BE-0169-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0169 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3333 | Trace Heating | PS5-79-SP-0169-CL01 | PS5-79-BE-0169 | Heat Tracing Junction Box | Outdoor | PS5-79-SP-0169 | Heat Tracing Junction Box | Field
3334 | Trace Heating | PS5-79-BE-0159-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0159 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3335 | Trace Heating | PS5-79-BE-0164-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0164 | Heat Tracing Junction Box | Field
3336 | Trace Heating | PS5-79-BE-0151-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0151 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3337 | Trace Heating | PS5-79-BE-0356-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0356 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3338 | Trace Heating | PS5-79-BE-0206-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0206 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3339 | Trace Heating | PS5-79-BE-0148-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0148 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3340 | Trace Heating | PS5-79-BE-0314-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0314 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3341 | Trace Heating | PS5-79-BE-0149-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0149 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3342 | Trace Heating | PS5-79-BE-0234-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0234 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3343 | Trace Heating | PS5-79-BE-0114-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0114 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3344 | Trace Heating | PS5-79-BE-0165-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0165 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3345 | Trace Heating | PS5-79-BE-0166-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0166 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3346 | Trace Heating | PS5-79-BE-0157-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0157 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3347 | Trace Heating | PS5-79-BE-0153-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0153 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3348 | Trace Heating | PS5-79-BE-0313-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0313 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3349 | Trace Heating | PS5-79-BE-0188-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0188 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3350 | Trace Heating | PS5-79-BE-0202-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0202 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3351 | Trace Heating | PS5-79-BE-0103-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0103 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3352 | Trace Heating | PS5-79-BE-0317-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0317 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3353 | Trace Heating | PS5-79-BE-0306-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0306 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
3354 | Trace Heating | PS5-79-BE-0197-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-BE-0197 | Heat Tracing Junction Box | Field
3355 | Trace Heating | PS5-71-BE-0361-CL01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-71-BE-0361 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
3356 | Trace Heating | PS5-79-BE-0181-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0181 | Heat Tracing Junction Box | Field
3357 | Trace Heating | PS5-79-BE-0184-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0184 | Heat Tracing Junction Box | Field
3358 | Trace Heating | PS5-79-BE-0302-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0302 | Heat Tracing Junction Box | Field
3359 | Trace Heating | PS5-79-BE-0185-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0185 | Heat Tracing Junction Box | Field
3360 | Trace Heating | PS5-79-BE-0182-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0182 | Heat Tracing Junction Box | Field
3361 | Trace Heating | PS5-79-BE-0303-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0303 | Heat Tracing Junction Box | Field
3362 | Trace Heating | PS5-79-BE-0304-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0304 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3363 | Trace Heating | PS5-79-BE-0325-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0325 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3364 | Trace Heating | PS5-79-BE-0311-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0311 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3365 | Trace Heating | PS5-79-BE-0312-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0312 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3366 | Trace Heating | PS5-79-BE-0173-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0173 | Heat Tracing Junction Box | Field
3367 | Trace Heating | PS5-79-BE-0183-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0183 | Heat Tracing Junction Box | Field
3368 | Trace Heating | PS5-79-BE-0355-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0355 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3369 | Trace Heating | PS5-79-BE-0354-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0354 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3370 | Trace Heating | PS5-79-BE-0201-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0201 | Heat Tracing Junction Box | Field
3371 | Trace Heating | PS5-79-BE-0193-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0193 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3372 | Trace Heating | PS5-79-BE-0322-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0322 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3373 | Trace Heating | PS5-79-BE-0192-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0192 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3374 | Trace Heating | PS5-79-BE-0191-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0191 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3375 | Trace Heating | PS5-79-BE-0346-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0346 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3376 | Trace Heating | PS5-79-BE-0172-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0172 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3377 | Trace Heating | PS5-79-BE-0179-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0179 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3378 | Trace Heating | PS5-79-BE-0326-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0326 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3379 | Trace Heating | PS5-79-BE-0180-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0180 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3380 | Trace Heating | PS5-79-BE-0174-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0174 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3381 | Trace Heating | PS5-79-BE-0305-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0305 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3382 | Trace Heating | PS5-79-BE-0199-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0199 | Heat Tracing Junction Box | Field
3383 | Trace Heating | PS5-79-BE-0187-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0187 | Heat Tracing Junction Box | Field
3384 | Trace Heating | PS5-79-BE-0190-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-BE-0190 | Heat Tracing Junction Box | Field
3385 | Trace Heating | PS5-71-BE-0363-CL01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-71-BE-0363 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3386 | Trace Heating | PS5-79-BE-0023-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0023 | Heat Tracing Junction Box | Field
3387 | Trace Heating | PS5-79-BE-0278-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0278 | Heat Tracing Junction Box | Field
3388 | Trace Heating | PS5-79-BE-0307-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0307 | Heat Tracing Junction Box | Field
3389 | Trace Heating | PS5-79-BE-0198-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0198 | Heat Tracing Junction Box | Field
3390 | Trace Heating | PS5-79-BE-0046-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0046 | Heat Tracing Junction Box | Field
3391 | Trace Heating | PS5-79-BE-0195-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0195 | Heat Tracing Junction Box | Field
3392 | Trace Heating | PS5-79-BE-0252-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0252 | Heat Tracing Junction Box | Field
3393 | Trace Heating | PS5-79-BE-0253-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0253 | Heat Tracing Junction Box | Field
3394 | Trace Heating | PS5-79-BE-0200-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0200 | Heat Tracing Junction Box | Field
3395 | Trace Heating | PS5-79-BE-0194-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0194 | Heat Tracing Junction Box | Field
3396 | Trace Heating | PS5-79-BE-0246-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0246 | Heat Tracing Junction Box | Field
3397 | Trace Heating | PS5-79-BE-0189-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0189 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
3398 | Trace Heating | PS5-79-BE-0210-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0210 | Heat Tracing Junction Box | Field
3399 | Trace Heating | PS5-79-BE-0186-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0186 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
3400 | Trace Heating | PS5-79-BE-0279-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0279 | Heat Tracing Junction Box | Field
3401 | Trace Heating | PS5-79-BE-0260-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0260 | Heat Tracing Junction Box | Field
3402 | Trace Heating | PS5-79-BE-0211-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0211 | Heat Tracing Junction Box | Field
3403 | Trace Heating | PS5-79-BE-0196-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0196 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
3404 | Trace Heating | PS5-79-BE-0244-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0244 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
3405 | Trace Heating | PS5-79-BE-0238-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0238 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
3406 | Trace Heating | PS5-79-BE-0348-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0348 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
3407 | Trace Heating | PS5-79-BE-0352-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0352 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
3408 | Trace Heating | PS5-79-BE-0242-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0242 | Heat Tracing Junction Box | Field
3409 | Trace Heating | PS5-79-BE-0109-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0109 | Heat Tracing Junction Box | Field
3410 | Trace Heating | PS5-79-BE-0113-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0113 | Heat Tracing Junction Box | Field
3411 | Trace Heating | PS5-79-BE-0106-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0106 | Heat Tracing Junction Box | Field
3412 | Trace Heating | PS5-79-BE-0351-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0351 | Heat Tracing Junction Box | Field
3413 | Trace Heating | PS5-79-BE-0243-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-BE-0243 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
3414 | Trace Heating | PS5-60-BE-0365-CL01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-60-BE-0365 | Heat Tracing Junction Box | Field
3415 | Trace Heating | PS5-79-BE-0280-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0280 | Heat Tracing Junction Box | Field
3416 | Trace Heating | PS5-79-BE-0331-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0331 | Heat Tracing Junction Box | Field
3417 | Trace Heating | PS5-79-BE-0327-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0327 | Heat Tracing Junction Box | Field
3418 | Trace Heating | PS5-79-BE-0266-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0266 | Heat Tracing Junction Box | Field
3419 | Trace Heating | PS5-79-BE-0265-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0265 | Heat Tracing Junction Box | Field
3420 | Trace Heating | PS5-79-BE-0212-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0212 | Heat Tracing Junction Box | Field
3421 | Trace Heating | PS5-79-BE-0049-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0049 | Heat Tracing Junction Box | Field
3422 | Trace Heating | PS5-79-BE-0329-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0329 | Heat Tracing Junction Box | Field
3423 | Trace Heating | PS5-79-BE-0285-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0285 | Heat Tracing Junction Box | Field
3424 | Trace Heating | PS5-79-BE-0220-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0220 | Heat Tracing Junction Box | Field
3425 | Trace Heating | PS5-79-BE-0217-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0217 | Heat Tracing Junction Box | Field
3426 | Trace Heating | PS5-79-BE-0219-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0219 | Heat Tracing Junction Box | Field
3427 | Trace Heating | PS5-79-BE-0237-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0237 | Heat Tracing Junction Box | Field
3428 | Trace Heating | PS5-79-SP-0237-CL01 | PS5-79-BE-0237 | Heat Tracing Junction Box | Outdoor | PS5-79-SP-0237 | Heat Tracing Junction Box | Field
3429 | Trace Heating | PS5-79-BE-0282-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0282 | Heat Tracing Junction Box | Field
3430 | Trace Heating | PS5-79-BE-0213-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0213 | Heat Tracing Junction Box | Field
3431 | Trace Heating | PS5-79-BE-0086-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0086 | Heat Tracing Junction Box | Field
3432 | Trace Heating | PS5-79-BE-0214-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0214 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3433 | Trace Heating | PS5-79-BE-0283-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0283 | Heat Tracing Junction Box | Field
3434 | Trace Heating | PS5-79-BE-0092-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0092 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
3435 | Trace Heating | PS5-79-BE-0216-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0216 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
3436 | Trace Heating | PS5-79-BE-0215-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0215 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3437 | Trace Heating | PS5-79-BE-0099-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0099 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3438 | Trace Heating | PS5-79-BE-0171-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0171 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3439 | Trace Heating | PS5-79-BE-0264-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0264 | Heat Tracing Junction Box | Field
3440 | Trace Heating | PS5-79-BE-0281-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0281 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3441 | Trace Heating | PS5-79-BE-0284-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-BE-0284 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3442 | Trace Heating | PS5-60-BE-0366-CL01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-60-BE-0366 | Heat Tracing Junction Box | Field
3443 | Trace Heating | PS5-79-BE-0332-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0332 | Heat Tracing Junction Box | Field
3444 | Trace Heating | PS5-79-BE-0330-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0330 | Heat Tracing Junction Box | Field
3445 | Trace Heating | PS5-79-BE-0269-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0269 | Heat Tracing Junction Box | Field
3446 | Trace Heating | PS5-79-BE-0267-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0267 | Heat Tracing Junction Box | Field
3447 | Trace Heating | PS5-79-BE-0268-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0268 | Heat Tracing Junction Box | Field
3448 | Trace Heating | PS5-79-BE-0334-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0334 | Heat Tracing Junction Box | Field
3449 | Trace Heating | PS5-79-BE-0333-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0333 | Heat Tracing Junction Box | Field
3450 | Trace Heating | PS5-79-BE-0272-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0272 | Heat Tracing Junction Box | Field
3451 | Trace Heating | PS5-79-BE-0270-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0270 | Heat Tracing Junction Box | Field
3452 | Trace Heating | PS5-79-BE-0271-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0271 | Heat Tracing Junction Box | Field
3453 | Trace Heating | PS5-79-BE-0335-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0335 | Heat Tracing Junction Box | Field
3454 | Trace Heating | PS5-79-BE-0339-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0339 | Heat Tracing Junction Box | Field
3455 | Trace Heating | PS5-79-BE-0275-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0275 | Heat Tracing Junction Box | Field
3456 | Trace Heating | PS5-79-BE-0273-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0273 | Heat Tracing Junction Box | Field
3457 | Trace Heating | PS5-79-BE-0274-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0274 | Heat Tracing Junction Box | Field
3458 | Trace Heating | PS5-79-BE-0328-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0328 | Heat Tracing Junction Box | Field
3459 | Trace Heating | PS5-79-BE-0061-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0061 | Heat Tracing Junction Box | Field
3460 | Trace Heating | PS5-79-BE-0218-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0218 | Heat Tracing Junction Box | Field
3461 | Trace Heating | PS5-79-BE-0229-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0229 | Heat Tracing Junction Box | Field
3462 | Trace Heating | PS5-79-BE-0223-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0223 | Heat Tracing Junction Box | Field
3463 | Trace Heating | PS5-79-BE-0224-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0224 | Heat Tracing Junction Box | Field
3464 | Trace Heating | PS5-79-BE-0221-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0221 | Heat Tracing Junction Box | Field
3465 | Trace Heating | PS5-79-BE-0235-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0235 | Heat Tracing Junction Box | Field
3466 | Trace Heating | PS5-79-BE-0222-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0222 | Heat Tracing Junction Box | Field
3467 | Trace Heating | PS5-79-BE-0350-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0350 | Heat Tracing Junction Box | Field
3468 | Trace Heating | PS5-79-BE-0228-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0228 | Heat Tracing Junction Box | Field
3469 | Trace Heating | PS5-79-BE-0236-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-BE-0236 | Heat Tracing Junction Box | Field
3470 | Trace Heating | PS5-60-BE-0367-CL01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-60-BE-0367 | Heat Tracing Junction Box | Field
3471 | Trace Heating | PS5-79-BE-0136-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0136 | Heat Tracing Junction Box | Field
3472 | Trace Heating | PS5-79-BE-0027-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0027 | Heat Tracing Junction Box | Field
3473 | Trace Heating | PS5-79-BE-0039-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0039 | Heat Tracing Junction Box | Field
3474 | Trace Heating | PS5-79-BE-0037-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0037 | Heat Tracing Junction Box | Field
3475 | Trace Heating | PS5-79-BE-0025-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0025 | Heat Tracing Junction Box | Field
3476 | Trace Heating | PS5-79-BE-0343-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0343 | Heat Tracing Junction Box | Field
3477 | Trace Heating | PS5-79-BE-0118-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0118 | Heat Tracing Junction Box | Field
3478 | Trace Heating | PS5-79-BE-0137-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0137 | Heat Tracing Junction Box | Field
3479 | Trace Heating | PS5-79-BE-0024-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0024 | Heat Tracing Junction Box | Field
3480 | Trace Heating | PS5-79-BE-0150-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0150 | Heat Tracing Junction Box | Field
3481 | Trace Heating | PS5-79-BE-0203-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0203 | Heat Tracing Junction Box | Field
3482 | Trace Heating | PS5-79-BE-0204-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0204 | Heat Tracing Junction Box | Field
3483 | Trace Heating | PS5-79-BE-0262-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0262 | Heat Tracing Junction Box | Field
3484 | Trace Heating | PS5-79-BE-0102-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0102 | Heat Tracing Junction Box | Field
3485 | Trace Heating | PS5-79-BE-0081-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0081 | Heat Tracing Junction Box | Field
3486 | Trace Heating | PS5-79-BE-0036-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0036 | Heat Tracing Junction Box | Field
3487 | Trace Heating | PS5-79-BE-0066-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0066 | Heat Tracing Junction Box | Field
3488 | Trace Heating | PS5-79-BE-0067-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0067 | Heat Tracing Junction Box | Field
3489 | Trace Heating | PS5-79-BE-0245-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0245 | Heat Tracing Junction Box | Field
3490 | Trace Heating | PS5-79-BE-0134-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0134 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3491 | Trace Heating | PS5-79-BE-0063-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0063 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3492 | Trace Heating | PS5-79-BE-0154-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0154 | Heat Tracing Junction Box | Field
3493 | Trace Heating | PS5-79-BE-0319-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0319 | Heat Tracing Junction Box | Field
3494 | Trace Heating | PS5-79-BE-0290-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0290 | Heat Tracing Junction Box | Field
3495 | Trace Heating | PS5-79-BE-0152-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0152 | Heat Tracing Junction Box | Field
3496 | Trace Heating | PS5-79-BE-0002-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0002 | Heat Tracing Junction Box | Field
3497 | Trace Heating | PS5-79-BE-0005-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0005 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3498 | Trace Heating | PS5-79-BE-0146-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0146 | Heat Tracing Junction Box | Field
3499 | Trace Heating | PS5-79-BE-0041-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0041 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3500 | Trace Heating | PS5-79-BE-0135-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0135 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3501 | Trace Heating | PS5-79-BE-0239-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0239 | Heat Tracing Junction Box | Field
3502 | Trace Heating | PS5-79-IP-9901-CL01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-IP-9901 | Marshalling Box | Field
3503 | Trace Heating | PS5-79-IP-9101-CL01 | PS5-79-IP-9901 | Marshalling Box | Outdoor | PS5-79-IP-9101 | ETS-05 | Field
3504 | Trace Heating | PS5-79-IP-9102-CL01 | PS5-79-IP-9901 | Marshalling Box | Outdoor | PS5-79-IP-9102 | ETS-05 | Field
3505 | Trace Heating | PS5-79-BE-0247-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0247 | Heat Tracing Junction Box | Field
3506 | Trace Heating | PS5-79-BE-0084-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0084 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0007
3507 | Trace Heating | PS5-79-BE-0090-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0090 | Heat Tracing Junction Box | Field
3508 | Trace Heating | PS5-79-BE-0085-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0085 | Heat Tracing Junction Box | Field
3509 | Trace Heating | PS5-79-BE-0082-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0082 | Heat Tracing Junction Box | Field
3510 | Trace Heating | PS5-79-BE-0101-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0101 | Heat Tracing Junction Box | Field
3511 | Trace Heating | PS5-79-BE-0156-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0156 | Heat Tracing Junction Box | Field
3512 | Trace Heating | PS5-79-BE-0107-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0107 | Heat Tracing Junction Box | Field
3513 | Trace Heating | PS5-79-BE-0020-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0020 | Heat Tracing Junction Box | Field
3514 | Trace Heating | PS5-79-BE-0147-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0147 | Heat Tracing Junction Box | Field
3515 | Trace Heating | PS5-79-BE-0043-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0043 | Heat Tracing Junction Box | Field
3516 | Trace Heating | PS5-79-BE-0344-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0344 | Heat Tracing Junction Box | Field
3517 | Trace Heating | PS5-79-BE-0019-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0019 | Heat Tracing Junction Box | Field
3518 | Trace Heating | PS5-79-BE-0100-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0100 | Heat Tracing Junction Box | Field
3519 | Trace Heating | PS5-79-BE-0112-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0112 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3520 | Trace Heating | PS5-79-BE-0068-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0068 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3521 | Trace Heating | PS5-79-BE-0042-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0042 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3522 | Trace Heating | PS5-79-BE-0121-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0121 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3523 | Trace Heating | PS5-79-BE-0072-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0072 | Heat Tracing Junction Box | Field
3524 | Trace Heating | PS5-79-BE-0116-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0116 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3525 | Trace Heating | PS5-79-BE-0145-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0145 | Heat Tracing Junction Box | Field
3526 | Trace Heating | PS5-79-BE-0155-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0155 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3527 | Trace Heating | PS5-79-BE-0071-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0071 | Heat Tracing Junction Box | Field
3528 | Trace Heating | PS5-79-BE-0083-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0083 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3529 | Trace Heating | PS5-79-BE-0291-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0291 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3530 | Trace Heating | PS5-79-BE-0003-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0003 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3531 | Trace Heating | PS5-79-BE-0143-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0143 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3532 | Trace Heating | PS5-79-BE-0059-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0059 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3533 | Trace Heating | PS5-79-BE-0006-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0006 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3534 | Trace Heating | PS5-79-BE-0144-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0144 | Heat Tracing Junction Box | Field
3535 | Trace Heating | PS5-79-BE-0240-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0240 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3536 | Trace Heating | PS5-79-IP-9902-CL01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-IP-9902 | Marshalling Box | Field
3537 | Trace Heating | PS5-79-IP-9103-CL01 | PS5-79-IP-9902 | Marshalling Box | Outdoor | PS5-79-IP-9103 | ETS-05 | Field
3538 | Trace Heating | PS5-79-IP-9104-CL01 | PS5-79-IP-9902 | Marshalling Box | Outdoor | PS5-79-IP-9104 | ETS-05 | Field
3539 | Trace Heating | PS5-79-BE-0241-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0241 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
3540 | Trace Heating | PS5-79-BE-0208-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0208 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3541 | Trace Heating | PS5-79-BE-0292-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0292 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
3542 | Trace Heating | PS5-79-BE-0058-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0058 | Heat Tracing Junction Box | Field
3543 | Trace Heating | PS5-79-BE-0140-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0140 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
3544 | Trace Heating | PS5-79-BE-0004-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0004 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
3545 | Trace Heating | PS5-79-BE-0007-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0007 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
3546 | Trace Heating | PS5-79-BE-0161-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0161 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3547 | Trace Heating | PS5-79-BE-0139-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0139 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
3548 | Trace Heating | PS5-79-BE-0162-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0162 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3549 | Trace Heating | PS5-79-BE-0074-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0074 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3550 | Trace Heating | PS5-79-BE-0142-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0142 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
3551 | Trace Heating | PS5-79-BE-0160-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0160 | Heat Tracing Junction Box | Field
3552 | Trace Heating | PS5-79-BE-0077-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0077 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3553 | Trace Heating | PS5-79-BE-0075-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0075 | Heat Tracing Junction Box | Field
3554 | Trace Heating | PS5-79-BE-0053-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0053 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3555 | Trace Heating | PS5-79-BE-0076-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0076 | Heat Tracing Junction Box | Field
3556 | Trace Heating | PS5-79-BE-0070-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0070 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3557 | Trace Heating | PS5-79-BE-0158-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0158 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3558 | Trace Heating | PS5-79-BE-0060-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0060 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3559 | Trace Heating | PS5-79-BE-0115-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0115 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3560 | Trace Heating | PS5-79-BE-0108-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0108 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3561 | Trace Heating | PS5-79-BE-0111-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0111 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3562 | Trace Heating | PS5-79-BE-0062-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0062 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3563 | Trace Heating | PS5-79-BE-0141-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0141 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
3564 | Trace Heating | PS5-79-BE-0207-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0207 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3565 | Trace Heating | PS5-79-BE-0205-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0205 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3566 | Trace Heating | PS5-79-BE-0044-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0044 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3567 | Trace Heating | PS5-79-BE-0045-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0045 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3568 | Trace Heating | PS5-79-BE-0261-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0261 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3569 | Trace Heating | PS5-79-BE-0209-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0209 | Heat Tracing Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
3570 | Trace Heating | PS5-79-IP-9903-CL01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-IP-9903 | Marshalling Box | Field
3571 | Trace Heating | PS5-79-IP-9105-CL01 | PS5-79-IP-9903 | Marshalling Box | Outdoor | PS5-79-IP-9105 | ETS-05 | Field
3572 | Trace Heating | PS5-79-IP-9106-CL01 | PS5-79-IP-9903 | Marshalling Box | Outdoor | PS5-79-IP-9106 | ETS-05 | Field
3573 | Trace Heating | PS5-79-BE-0064-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0064 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0006
3574 | Trace Heating | PS5-79-BE-0057-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0057 | Heat Tracing Junction Box | Field
3575 | Trace Heating | PS5-79-BE-0021-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0021 | Heat Tracing Junction Box | Field
3576 | Trace Heating | PS5-79-BE-0128-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0128 | Heat Tracing Junction Box | Field
3577 | Trace Heating | PS5-79-BE-0008-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0008 | Heat Tracing Junction Box | Field
3578 | Trace Heating | PS5-79-SP-0008-CL01 | PS5-79-BE-0008 | Heat Tracing Junction Box | Outdoor | PS5-79-SP-0008 | Heat Tracing Junction Box | Field
3579 | Trace Heating | PS5-79-BE-0047-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0047 | Heat Tracing Junction Box | Field
3580 | Trace Heating | PS5-79-BE-0052-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0052 | Heat Tracing Junction Box | Field
3581 | Trace Heating | PS5-79-BE-0056-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0056 | Heat Tracing Junction Box | Field
3582 | Trace Heating | PS5-79-BE-0055-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0055 | Heat Tracing Junction Box | Field
3583 | Trace Heating | PS5-79-BE-0028-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0028 | Heat Tracing Junction Box | Field
3584 | Trace Heating | PS5-79-BE-0294-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0294 | Heat Tracing Junction Box | Field
3585 | Trace Heating | PS5-79-BE-0293-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0293 | Heat Tracing Junction Box | Field
3586 | Trace Heating | PS5-79-BE-0129-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0129 | Heat Tracing Junction Box | Field
3587 | Trace Heating | PS5-79-BE-0073-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0073 | Heat Tracing Junction Box | Field
3588 | Trace Heating | PS5-79-BE-0010-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0010 | Heat Tracing Junction Box | Field
3589 | Trace Heating | PS5-79-SP-0010-CL01 | PS5-79-BE-0010 | Heat Tracing Junction Box | Outdoor | PS5-79-SP-0010 | Heat Tracing Junction Box | Field
3590 | Trace Heating | PS5-79-BE-0124-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0124 | Heat Tracing Junction Box | Field
3591 | Trace Heating | PS5-79-BE-0295-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0295 | Heat Tracing Junction Box | Field
3592 | Trace Heating | PS5-79-BE-0030-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0030 | Heat Tracing Junction Box | Field
3593 | Trace Heating | PS5-79-BE-0127-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0127 | Heat Tracing Junction Box | Field
3594 | Trace Heating | PS5-79-BE-0051-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0051 | Heat Tracing Junction Box | Field
3595 | Trace Heating | PS5-79-BE-0032-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0032 | Heat Tracing Junction Box | Field
3596 | Trace Heating | PS5-79-BE-0033-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0033 | Heat Tracing Junction Box | Field
3597 | Trace Heating | PS5-79-BE-0126-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0126 | Heat Tracing Junction Box | Field
3598 | Trace Heating | PS5-79-BE-0125-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0125 | Heat Tracing Junction Box | Field
3599 | Trace Heating | PS5-79-BE-0011-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0011 | Heat Tracing Junction Box | Field
3600 | Trace Heating | PS5-79-BE-0301-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0301 | Heat Tracing Junction Box | Field
3601 | Trace Heating | PS5-79-BE-0001-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0001 | Heat Tracing Junction Box | Field
3602 | Trace Heating | PS5-79-BE-0009-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0009 | Heat Tracing Junction Box | Field
3603 | Trace Heating | PS5-79-BE-0014-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0014 | Heat Tracing Junction Box | Field
3604 | Trace Heating | PS5-79-BE-0034-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0034 | Heat Tracing Junction Box | Field
3605 | Trace Heating | PS5-79-BE-0353-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-BE-0353 | Heat Tracing Junction Box | Field
3606 | Trace Heating | PS5-71-BE-0362-CL01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-71-BE-0362 | Heat Tracing Junction Box | Field
3607 | Trace Heating | PS5-79-BE-0132-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0132 | Heat Tracing Junction Box | Field
3608 | Trace Heating | PS5-79-BE-0131-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0131 | Heat Tracing Junction Box | Field
3609 | Trace Heating | PS5-79-BE-0040-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0040 | Heat Tracing Junction Box | Field
3610 | Trace Heating | PS5-79-BE-0233-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0233 | Heat Tracing Junction Box | Field
3611 | Trace Heating | PS5-79-BE-0054-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0054 | Heat Tracing Junction Box | Field
3612 | Trace Heating | PS5-79-BE-0022-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0022 | Heat Tracing Junction Box | Field
3613 | Trace Heating | PS5-79-BE-0078-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0078 | Heat Tracing Junction Box | Field
3614 | Trace Heating | PS5-79-BE-0105-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0105 | Heat Tracing Junction Box | Field
3615 | Trace Heating | PS5-79-BE-0029-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0029 | Heat Tracing Junction Box | Field
3616 | Trace Heating | PS5-79-BE-0035-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0035 | Heat Tracing Junction Box | Field
3617 | Trace Heating | PS5-79-BE-0094-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0094 | Heat Tracing Junction Box | Field
3618 | Trace Heating | PS5-79-BE-0120-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0120 | Heat Tracing Junction Box | Field
3619 | Trace Heating | PS5-79-BE-0095-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0095 | Heat Tracing Junction Box | Field
3620 | Trace Heating | PS5-79-BE-0087-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0087 | Heat Tracing Junction Box | Field
3621 | Trace Heating | PS5-79-BE-0119-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0119 | Heat Tracing Junction Box | Field
3622 | Trace Heating | PS5-79-BE-0117-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0117 | Heat Tracing Junction Box | Field
3623 | Trace Heating | PS5-79-BE-0323-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0323 | Heat Tracing Junction Box | Field
3624 | Trace Heating | PS5-79-BE-0096-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0096 | Heat Tracing Junction Box | Field
3625 | Trace Heating | PS5-79-BE-0079-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0079 | Heat Tracing Junction Box | Field
3626 | Trace Heating | PS5-79-BE-0345-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0345 | Heat Tracing Junction Box | Field
3627 | Trace Heating | PS5-79-BE-0104-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0104 | Heat Tracing Junction Box | Field
3628 | Trace Heating | PS5-79-BE-0230-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0230 | Heat Tracing Junction Box | Field
3629 | Trace Heating | PS5-79-BE-0093-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0093 | Heat Tracing Junction Box | Field
3630 | Trace Heating | PS5-79-BE-0088-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0088 | Heat Tracing Junction Box | Field
3631 | Trace Heating | PS5-79-BE-0089-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0089 | Heat Tracing Junction Box | Field
3632 | Trace Heating | PS5-79-BE-0091-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0091 | Heat Tracing Junction Box | Field
3633 | Trace Heating | PS5-79-BE-0097-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0097 | Heat Tracing Junction Box | Field
3634 | Trace Heating | PS5-79-BE-0321-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0321 | Heat Tracing Junction Box | Field
3635 | Trace Heating | PS5-79-BE-0227-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-BE-0227 | Heat Tracing Junction Box | Field
3636 | Trace Heating | PS5-60-BE-0364-CL01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-60-BE-0364 | Heat Tracing Junction Box | Field
3637 | Trace Heating | PS5-79-BE-0286-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0286 | Heat Tracing Junction Box | Field
3638 | Trace Heating | PS5-79-BE-0347-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0347 | Heat Tracing Junction Box | Field
3639 | Trace Heating | PS5-79-BE-0289-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0289 | Heat Tracing Junction Box | Field
3640 | Trace Heating | PS5-79-BE-0342-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0342 | Heat Tracing Junction Box | Field
3641 | Trace Heating | PS5-79-BE-0232-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0232 | Heat Tracing Junction Box | Field
3642 | Trace Heating | PS5-79-BE-0231-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0231 | Heat Tracing Junction Box | Field
3643 | Trace Heating | PS5-79-BE-0288-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0288 | Heat Tracing Junction Box | Field
3644 | Trace Heating | PS5-79-BE-0225-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0225 | Heat Tracing Junction Box | Field
3645 | Trace Heating | PS5-79-BE-0324-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0324 | Heat Tracing Junction Box | Field
3646 | Trace Heating | PS5-79-BE-0080-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0080 | Heat Tracing Junction Box | Field
3647 | Trace Heating | PS5-79-BE-0065-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0065 | Heat Tracing Junction Box | Field
3648 | Trace Heating | PS5-79-BE-0287-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0287 | Heat Tracing Junction Box | Field
3649 | Trace Heating | PS5-79-BE-0277-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0277 | Heat Tracing Junction Box | Field
3650 | Trace Heating | PS5-79-BE-0276-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0276 | Heat Tracing Junction Box | Field
3651 | Trace Heating | PS5-79-BE-0226-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0226 | Heat Tracing Junction Box | Field
3652 | Trace Heating | PS5-79-BE-0340-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0340 | Heat Tracing Junction Box | Field
3653 | Trace Heating | PS5-79-BE-0336-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0336 | Heat Tracing Junction Box | Field
3654 | Trace Heating | PS5-79-BE-0031-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0031 | Heat Tracing Junction Box | Field
3655 | Trace Heating | PS5-79-BE-0016-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0016 | Heat Tracing Junction Box | Field
3656 | Trace Heating | PS5-79-BE-0038-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0038 | Heat Tracing Junction Box | Field
3657 | Trace Heating | PS5-79-BE-0341-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0341 | Heat Tracing Junction Box | Field
3658 | Trace Heating | PS5-79-BE-0337-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0337 | Heat Tracing Junction Box | Field
3659 | Trace Heating | PS5-79-BE-0050-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0050 | Heat Tracing Junction Box | Field
3660 | Trace Heating | PS5-79-BE-0048-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0048 | Heat Tracing Junction Box | Field
3661 | Trace Heating | PS5-79-BE-0069-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0069 | Heat Tracing Junction Box | Field
3662 | Trace Heating | PS5-79-BE-0349-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0349 | Heat Tracing Junction Box | Field
3663 | Trace Heating | PS5-79-BE-0338-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-BE-0338 | Heat Tracing Junction Box | Field
3664 | Trace Heating | PS5-60-BE-0368-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-60-BE-0368 | Heat Tracing Junction Box | Field
3665 | Trace Heating | PS5-60-BE-0369-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-60-BE-0369 | Heat Tracing Junction Box | Field
3666 | Trace Heating | PS5-60-BE-0370-CL01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-60-BE-0370 | Heat Tracing Junction Box | Field
3667 | Trace Heating | PS5-79-BE-0251-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0251 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3668 | Trace Heating | PS5-79-BE-0297-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0297 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3669 | Trace Heating | PS5-79-BE-0296-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0296 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3670 | Trace Heating | PS5-79-BE-0012-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0012 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
3671 | Trace Heating | PS5-79-BE-0259-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0259 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
3672 | Trace Heating | PS5-79-BE-0257-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0257 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
3673 | Trace Heating | PS5-79-BE-0258-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0258 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3674 | Trace Heating | PS5-79-BE-0098-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0098 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3675 | Trace Heating | PS5-79-BE-0300-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0300 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3676 | Trace Heating | PS5-79-BE-0123-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0123 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3677 | Trace Heating | PS5-79-BE-0248-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0248 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3678 | Trace Heating | PS5-79-BE-0254-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0254 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
3679 | Trace Heating | PS5-79-BE-0310-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0310 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
3680 | Trace Heating | PS5-79-BE-0263-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0263 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
3681 | Trace Heating | PS5-79-BE-0122-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0122 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
3682 | Trace Heating | PS5-79-BE-0110-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0110 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
3683 | Trace Heating | PS5-79-BE-0256-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0256 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
3684 | Trace Heating | PS5-79-BE-0320-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0320 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
3685 | Trace Heating | PS5-79-BE-0255-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0255 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
3686 | Trace Heating | PS5-79-BE-0017-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0017 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
3687 | Trace Heating | PS5-79-BE-0250-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0250 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
3688 | Trace Heating | PS5-79-BE-0249-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0249 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
3689 | Trace Heating | PS5-79-BE-0318-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0318 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
3690 | Trace Heating | PS5-79-BE-0309-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0309 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3691 | Trace Heating | PS5-79-BE-0018-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0018 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3692 | Trace Heating | PS5-79-SP-0018-CL01 | PS5-79-BE-0018 | Heat Tracing Junction Box | Outdoor | PS5-79-SP-0018 | Heat Tracing Junction Box | Field
3693 | Trace Heating | PS5-79-BE-0130-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0130 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3694 | Trace Heating | PS5-79-BE-0299-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0299 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
3695 | Trace Heating | PS5-79-BE-0308-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0308 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
3696 | Trace Heating | PS5-79-BE-0013-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0013 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.; TZ-MID-68-NVS1-150359 Cable shortage at field side coiled only 2 Meter
3697 | Trace Heating | PS5-79-BE-0015-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0015 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3698 | Trace Heating | PS5-79-BE-0133-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0133 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3699 | Trace Heating | PS5-79-SP-0133-CL01 | PS5-79-BE-0133 | Heat Tracing Junction Box | Outdoor | PS5-79-SP-0133 | Heat Tracing Junction Box | Field
3700 | Trace Heating | PS5-79-BE-0298-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0298 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3701 | Trace Heating | PS5-79-BE-0026-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0026 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
3702 | Trace Heating | PS5-79-BE-0138-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-BE-0138 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
3703 | Trace Heating | PS5-25-BE-0364-CL01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-25-BE-0364 | Heat Tracing Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
3704 | Trace Heating | PS5-79-TE-0316-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0316 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3705 | Trace Heating | PS5-79-TE-0315-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0315 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3706 | Trace Heating | PS5-79-TE-0168-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0168 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3707 | Trace Heating | PS5-79-TE-0170-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0170 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3708 | Trace Heating | PS5-79-TE-0163-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0163 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3709 | Trace Heating | PS5-79-TE-0167-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0167 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3710 | Trace Heating | PS5-79-TE-0169-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0169 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3711 | Trace Heating | PS5-79-TE-0159-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0159 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3712 | Trace Heating | PS5-79-TE-0164-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0164 | PT100 Junction Box | Field
3713 | Trace Heating | PS5-79-TE-0151-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0151 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3714 | Trace Heating | PS5-79-TE-0356-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0356 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3715 | Trace Heating | PS5-79-TE-0206-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0206 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3716 | Trace Heating | PS5-79-TE-0148-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0148 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3717 | Trace Heating | PS5-79-TE-0314-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0314 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3718 | Trace Heating | PS5-79-TE-0149-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0149 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3719 | Trace Heating | PS5-79-TE-0234-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0234 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3720 | Trace Heating | PS5-79-TE-0114-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0114 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3721 | Trace Heating | PS5-79-TE-0165-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0165 | PT100 Junction Box | Field
3722 | Trace Heating | PS5-79-TE-0166-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0166 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3723 | Trace Heating | PS5-79-TE-0157-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0157 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3724 | Trace Heating | PS5-79-TE-0153-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0153 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3725 | Trace Heating | PS5-79-TE-0313-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0313 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3726 | Trace Heating | PS5-79-TE-0188-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0188 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3727 | Trace Heating | PS5-79-TE-0202-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0202 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3728 | Trace Heating | PS5-79-TE-0103-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0103 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3729 | Trace Heating | PS5-79-TE-0317-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0317 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3730 | Trace Heating | PS5-79-TE-0306-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0306 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
3731 | Trace Heating | PS5-79-TE-0197-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-79-TE-0197 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3732 | Trace Heating | PS5-71-TE-0361-CD01 | PS5-79-IG-0001 | Heat Tracing Panel | Outdoor | PS5-71-TE-0361 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
3733 | Trace Heating | PS5-79-TE-0181-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0181 | PT100 Junction Box | Field
3734 | Trace Heating | PS5-79-TE-0184-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0184 | PT100 Junction Box | Field
3735 | Trace Heating | PS5-79-TE-0302-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0302 | PT100 Junction Box | Field
3736 | Trace Heating | PS5-79-TE-0185-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0185 | PT100 Junction Box | Field
3737 | Trace Heating | PS5-79-TE-0182-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0182 | PT100 Junction Box | Field
3738 | Trace Heating | PS5-79-TE-0303-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0303 | PT100 Junction Box | Field
3739 | Trace Heating | PS5-79-TE-0304-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0304 | PT100 Junction Box | Field
3740 | Trace Heating | PS5-79-TE-0325-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0325 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3741 | Trace Heating | PS5-79-TE-0311-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0311 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3742 | Trace Heating | PS5-79-TE-0312-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0312 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3743 | Trace Heating | PS5-79-TE-0173-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0173 | PT100 Junction Box | Field
3744 | Trace Heating | PS5-79-TE-0183-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0183 | PT100 Junction Box | Field
3745 | Trace Heating | PS5-79-TE-0355-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0355 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3746 | Trace Heating | PS5-79-TE-0354-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0354 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3747 | Trace Heating | PS5-79-TE-0201-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0201 | PT100 Junction Box | Field
3748 | Trace Heating | PS5-79-TE-0193-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0193 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3749 | Trace Heating | PS5-79-TE-0322-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0322 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3750 | Trace Heating | PS5-79-TE-0192-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0192 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3751 | Trace Heating | PS5-79-TE-0191-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0191 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3752 | Trace Heating | PS5-79-TE-0346-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0346 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3753 | Trace Heating | PS5-79-TE-0172-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0172 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3754 | Trace Heating | PS5-79-TE-0179-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0179 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3755 | Trace Heating | PS5-79-TE-0326-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0326 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3756 | Trace Heating | PS5-79-TE-0180-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0180 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3757 | Trace Heating | PS5-79-TE-0174-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0174 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3758 | Trace Heating | PS5-79-TE-0305-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0305 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
3759 | Trace Heating | PS5-79-TE-0199-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0199 | PT100 Junction Box | Field
3760 | Trace Heating | PS5-79-TE-0187-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0187 | PT100 Junction Box | Field
3761 | Trace Heating | PS5-79-TE-0190-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-79-TE-0190 | PT100 Junction Box | Field
3762 | Trace Heating | PS5-71-TE-0363-CD01 | PS5-79-IG-0002 | Heat Tracing Panel | Outdoor | PS5-71-TE-0363 | PT100 Junction Box | Field
3763 | Trace Heating | PS5-79-TE-0023-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0023 | PT100 Junction Box | Field
3764 | Trace Heating | PS5-79-TE-0278-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0278 | PT100 Junction Box | Field
3765 | Trace Heating | PS5-79-TE-0307-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0307 | PT100 Junction Box | Field
3766 | Trace Heating | PS5-79-TE-0198-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0198 | PT100 Junction Box | Field
3767 | Trace Heating | PS5-79-TE-0046-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0046 | PT100 Junction Box | Field
3768 | Trace Heating | PS5-79-TE-0195-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0195 | PT100 Junction Box | Field
3769 | Trace Heating | PS5-79-TE-0252-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0252 | PT100 Junction Box | Field
3770 | Trace Heating | PS5-79-TE-0253-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0253 | PT100 Junction Box | Field
3771 | Trace Heating | PS5-79-TE-0200-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0200 | PT100 Junction Box | Field
3772 | Trace Heating | PS5-79-TE-0194-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0194 | PT100 Junction Box | Field
3773 | Trace Heating | PS5-79-TE-0246-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0246 | PT100 Junction Box | Field
3774 | Trace Heating | PS5-79-TE-0189-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0189 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
3775 | Trace Heating | PS5-79-TE-0210-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0210 | PT100 Junction Box | Field
3776 | Trace Heating | PS5-79-TE-0186-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0186 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
3777 | Trace Heating | PS5-79-TE-0279-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0279 | PT100 Junction Box | Field
3778 | Trace Heating | PS5-79-TE-0260-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0260 | PT100 Junction Box | Field
3779 | Trace Heating | PS5-79-TE-0211-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0211 | PT100 Junction Box | Field
3780 | Trace Heating | PS5-79-TE-0196-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0196 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
3781 | Trace Heating | PS5-79-TE-0244-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0244 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
3782 | Trace Heating | PS5-79-TE-0238-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0238 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
3783 | Trace Heating | PS5-79-TE-0348-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0348 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
3784 | Trace Heating | PS5-79-TE-0352-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0352 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
3785 | Trace Heating | PS5-79-TE-0242-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0242 | PT100 Junction Box | Field
3786 | Trace Heating | PS5-79-TE-0109-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0109 | PT100 Junction Box | Field
3787 | Trace Heating | PS5-79-TE-0113-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0113 | PT100 Junction Box | Field
3788 | Trace Heating | PS5-79-TE-0106-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0106 | PT100 Junction Box | Field
3789 | Trace Heating | PS5-79-TE-0351-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0351 | PT100 Junction Box | Field
3790 | Trace Heating | PS5-79-TE-0243-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-79-TE-0243 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
3791 | Trace Heating | PS5-60-TE-0365-CD01 | PS5-79-IG-0003 | Heat Tracing Panel | Outdoor | PS5-60-TE-0365 | PT100 Junction Box | Field
3792 | Trace Heating | PS5-79-TE-0280-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0280 | PT100 Junction Box | Field
3793 | Trace Heating | PS5-79-TE-0331-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0331 | PT100 Junction Box | Field
3794 | Trace Heating | PS5-79-TE-0327-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0327 | PT100 Junction Box | Field
3795 | Trace Heating | PS5-79-TE-0266-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0266 | PT100 Junction Box | Field
3796 | Trace Heating | PS5-79-TE-0265-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0265 | PT100 Junction Box | Field
3797 | Trace Heating | PS5-79-TE-0212-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0212 | PT100 Junction Box | Field
3798 | Trace Heating | PS5-79-TE-0049-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0049 | PT100 Junction Box | Field
3799 | Trace Heating | PS5-79-TE-0329-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0329 | PT100 Junction Box | Field
3800 | Trace Heating | PS5-79-TE-0285-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0285 | PT100 Junction Box | Field
3801 | Trace Heating | PS5-79-TE-0220-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0220 | PT100 Junction Box | Field
3802 | Trace Heating | PS5-79-TE-0217-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0217 | PT100 Junction Box | Field
3803 | Trace Heating | PS5-79-TE-0219-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0219 | PT100 Junction Box | Field
3804 | Trace Heating | PS5-79-TE-0237-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0237 | PT100 Junction Box | Field
3805 | Trace Heating | PS5-79-TE-0282-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0282 | PT100 Junction Box | Field
3806 | Trace Heating | PS5-79-TE-0213-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0213 | PT100 Junction Box | Field
3807 | Trace Heating | PS5-79-TE-0086-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0086 | PT100 Junction Box | Field
3808 | Trace Heating | PS5-79-TE-0214-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0214 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3809 | Trace Heating | PS5-79-TE-0283-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0283 | PT100 Junction Box | Field
3810 | Trace Heating | PS5-79-TE-0092-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0092 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
3811 | Trace Heating | PS5-79-TE-0216-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0216 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3812 | Trace Heating | PS5-79-TE-0215-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0215 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3813 | Trace Heating | PS5-79-TE-0099-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0099 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3814 | Trace Heating | PS5-79-TE-0171-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0171 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3815 | Trace Heating | PS5-79-TE-0264-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0264 | PT100 Junction Box | Field
3816 | Trace Heating | PS5-79-TE-0281-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0281 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3817 | Trace Heating | PS5-79-TE-0284-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-79-TE-0284 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
3818 | Trace Heating | PS5-60-TE-0366-CD01 | PS5-79-IG-0004 | Heat Tracing Panel | Outdoor | PS5-60-TE-0366 | PT100 Junction Box | Field
3819 | Trace Heating | PS5-79-TE-0332-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0332 | PT100 Junction Box | Field
3820 | Trace Heating | PS5-79-TE-0330-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0330 | PT100 Junction Box | Field
3821 | Trace Heating | PS5-79-TE-0269-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0269 | PT100 Junction Box | Field
3822 | Trace Heating | PS5-79-TE-0267-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0267 | PT100 Junction Box | Field
3823 | Trace Heating | PS5-79-TE-0268-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0268 | PT100 Junction Box | Field
3824 | Trace Heating | PS5-79-TE-0334-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0334 | PT100 Junction Box | Field
3825 | Trace Heating | PS5-79-TE-0333-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0333 | PT100 Junction Box | Field
3826 | Trace Heating | PS5-79-TE-0272-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0272 | PT100 Junction Box | Field
3827 | Trace Heating | PS5-79-TE-0270-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0270 | PT100 Junction Box | Field
3828 | Trace Heating | PS5-79-TE-0271-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0271 | PT100 Junction Box | Field
3829 | Trace Heating | PS5-79-TE-0335-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0335 | PT100 Junction Box | Field
3830 | Trace Heating | PS5-79-TE-0339-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0339 | PT100 Junction Box | Field
3831 | Trace Heating | PS5-79-TE-0275-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0275 | PT100 Junction Box | Field
3832 | Trace Heating | PS5-79-TE-0273-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0273 | PT100 Junction Box | Field
3833 | Trace Heating | PS5-79-TE-0274-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0274 | PT100 Junction Box | Field
3834 | Trace Heating | PS5-79-TE-0328-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0328 | PT100 Junction Box | Field
3835 | Trace Heating | PS5-79-TE-0061-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0061 | PT100 Junction Box | Field
3836 | Trace Heating | PS5-79-TE-0218-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0218 | PT100 Junction Box | Field
3837 | Trace Heating | PS5-79-TE-0229-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0229 | PT100 Junction Box | Field
3838 | Trace Heating | PS5-79-TE-0223-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0223 | PT100 Junction Box | Field
3839 | Trace Heating | PS5-79-TE-0224-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0224 | PT100 Junction Box | Field
3840 | Trace Heating | PS5-79-TE-0221-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0221 | PT100 Junction Box | Field
3841 | Trace Heating | PS5-79-TE-0235-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0235 | PT100 Junction Box | Field
3842 | Trace Heating | PS5-79-TE-0222-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0222 | PT100 Junction Box | Field
3843 | Trace Heating | PS5-79-TE-0350-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0350 | PT100 Junction Box | Field
3844 | Trace Heating | PS5-79-TE-0228-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0228 | PT100 Junction Box | Field
3845 | Trace Heating | PS5-79-TE-0236-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-79-TE-0236 | PT100 Junction Box | Field
3846 | Trace Heating | PS5-60-TE-0367-CD01 | PS5-79-IG-0005 | Heat Tracing Panel | Outdoor | PS5-60-TE-0367 | PT100 Junction Box | Field
3847 | Trace Heating | PS5-79-TE-0136-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0136 | PT100 Junction Box | Field
3848 | Trace Heating | PS5-79-TE-0027-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0027 | PT100 Junction Box | Field
3849 | Trace Heating | PS5-79-TE-0039-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0039 | PT100 Junction Box | Field
3850 | Trace Heating | PS5-79-TE-0037-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0037 | PT100 Junction Box | Field
3851 | Trace Heating | PS5-79-TE-0025-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0025 | PT100 Junction Box | Field
3852 | Trace Heating | PS5-79-TE-0343-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0343 | PT100 Junction Box | Field
3853 | Trace Heating | PS5-79-TE-0118-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0118 | PT100 Junction Box | Field
3854 | Trace Heating | PS5-79-TE-0137-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0137 | PT100 Junction Box | Field
3855 | Trace Heating | PS5-79-TE-0024-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0024 | PT100 Junction Box | Field
3856 | Trace Heating | PS5-79-TE-0150-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0150 | PT100 Junction Box | Field
3857 | Trace Heating | PS5-79-TE-0203-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0203 | PT100 Junction Box | Field
3858 | Trace Heating | PS5-79-TE-0204-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0204 | PT100 Junction Box | Field
3859 | Trace Heating | PS5-79-TE-0262-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0262 | PT100 Junction Box | Field
3860 | Trace Heating | PS5-79-TE-0102-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0102 | PT100 Junction Box | Field
3861 | Trace Heating | PS5-79-TE-0081-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0081 | PT100 Junction Box | Field
3862 | Trace Heating | PS5-79-TE-0036-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0036 | PT100 Junction Box | Field
3863 | Trace Heating | PS5-79-TE-0066-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0066 | PT100 Junction Box | Field
3864 | Trace Heating | PS5-79-TE-0067-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0067 | PT100 Junction Box | Field
3865 | Trace Heating | PS5-79-TE-0245-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0245 | PT100 Junction Box | Field
3866 | Trace Heating | PS5-79-TE-0134-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0134 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3867 | Trace Heating | PS5-79-TE-0063-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0063 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3868 | Trace Heating | PS5-79-TE-0154-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0154 | PT100 Junction Box | Field
3869 | Trace Heating | PS5-79-TE-0319-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0319 | PT100 Junction Box | Field
3870 | Trace Heating | PS5-79-TE-0290-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0290 | PT100 Junction Box | Field
3871 | Trace Heating | PS5-79-TE-0152-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0152 | PT100 Junction Box | Field
3872 | Trace Heating | PS5-79-TE-0002-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0002 | PT100 Junction Box | Field
3873 | Trace Heating | PS5-79-TE-0005-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0005 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3874 | Trace Heating | PS5-79-TE-0146-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0146 | PT100 Junction Box | Field
3875 | Trace Heating | PS5-79-TE-0041-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0041 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3876 | Trace Heating | PS5-79-TE-0135-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0135 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3877 | Trace Heating | PS5-79-TE-0239-CD01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-TE-0239 | PT100 Junction Box | Field
3878 | Trace Heating | PS5-79-TE-0247-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0247 | PT100 Junction Box | Field
3879 | Trace Heating | PS5-79-TE-0084-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0084 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
3880 | Trace Heating | PS5-79-TE-0090-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0090 | PT100 Junction Box | Field
3881 | Trace Heating | PS5-79-TE-0085-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0085 | PT100 Junction Box | Field
3882 | Trace Heating | PS5-79-TE-0082-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0082 | PT100 Junction Box | Field
3883 | Trace Heating | PS5-79-TE-0101-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0101 | PT100 Junction Box | Field
3884 | Trace Heating | PS5-79-TE-0156-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0156 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3885 | Trace Heating | PS5-79-TE-0107-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0107 | PT100 Junction Box | Field
3886 | Trace Heating | PS5-79-TE-0020-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0020 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0007)
3887 | Trace Heating | PS5-79-TE-0147-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0147 | PT100 Junction Box | Field
3888 | Trace Heating | PS5-79-TE-0043-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0043 | PT100 Junction Box | Field
3889 | Trace Heating | PS5-79-TE-0344-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0344 | PT100 Junction Box | Field
3890 | Trace Heating | PS5-79-TE-0019-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0019 | PT100 Junction Box | Field
3891 | Trace Heating | PS5-79-TE-0100-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0100 | PT100 Junction Box | Field
3892 | Trace Heating | PS5-79-TE-0112-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0112 | PT100 Junction Box | Field
3893 | Trace Heating | PS5-79-TE-0068-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0068 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3894 | Trace Heating | PS5-79-TE-0042-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0042 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3895 | Trace Heating | PS5-79-TE-0121-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0121 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3896 | Trace Heating | PS5-79-TE-0072-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0072 | PT100 Junction Box | Field
3897 | Trace Heating | PS5-79-TE-0116-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0116 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3898 | Trace Heating | PS5-79-TE-0145-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0145 | PT100 Junction Box | Field
3899 | Trace Heating | PS5-79-TE-0155-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0155 | PT100 Junction Box | Field
3900 | Trace Heating | PS5-79-TE-0071-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0071 | PT100 Junction Box | Field
3901 | Trace Heating | PS5-79-TE-0083-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0083 | PT100 Junction Box | Field
3902 | Trace Heating | PS5-79-TE-0291-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0291 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3903 | Trace Heating | PS5-79-TE-0003-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0003 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3904 | Trace Heating | PS5-79-TE-0143-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0143 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3905 | Trace Heating | PS5-79-TE-0059-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0059 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3906 | Trace Heating | PS5-79-TE-0006-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0006 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3907 | Trace Heating | PS5-79-TE-0144-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0144 | PT100 Junction Box | Field
3908 | Trace Heating | PS5-79-TE-0240-CD01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-TE-0240 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
3909 | Trace Heating | PS5-79-TE-0241-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0241 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
3910 | Trace Heating | PS5-79-TE-0208-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0208 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3911 | Trace Heating | PS5-79-TE-0292-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0292 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
3912 | Trace Heating | PS5-79-TE-0058-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0058 | PT100 Junction Box | Field
3913 | Trace Heating | PS5-79-TE-0140-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0140 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
3914 | Trace Heating | PS5-79-TE-0004-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0004 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
3915 | Trace Heating | PS5-79-TE-0007-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0007 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
3916 | Trace Heating | PS5-79-TE-0161-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0161 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3917 | Trace Heating | PS5-79-TE-0139-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0139 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
3918 | Trace Heating | PS5-79-TE-0162-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0162 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3919 | Trace Heating | PS5-79-TE-0074-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0074 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3920 | Trace Heating | PS5-79-TE-0142-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0142 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
3921 | Trace Heating | PS5-79-TE-0160-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0160 | PT100 Junction Box | Field
3922 | Trace Heating | PS5-79-TE-0077-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0077 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
3923 | Trace Heating | PS5-79-TE-0075-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0075 | PT100 Junction Box | Field
3924 | Trace Heating | PS5-79-TE-0053-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0053 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3925 | Trace Heating | PS5-79-TE-0076-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0076 | PT100 Junction Box | Field
3926 | Trace Heating | PS5-79-TE-0070-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0070 | PT100 Junction Box | Field
3927 | Trace Heating | PS5-79-TE-0158-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0158 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3928 | Trace Heating | PS5-79-TE-0060-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0060 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3929 | Trace Heating | PS5-79-TE-0115-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0115 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3930 | Trace Heating | PS5-79-TE-0108-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0108 | PT100 Junction Box | Field
3931 | Trace Heating | PS5-79-TE-0111-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0111 | PT100 Junction Box | Field
3932 | Trace Heating | PS5-79-TE-0062-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0062 | PT100 Junction Box | Field
3933 | Trace Heating | PS5-79-TE-0141-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0141 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3934 | Trace Heating | PS5-79-TE-0207-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0207 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3935 | Trace Heating | PS5-79-TE-0205-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0205 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3936 | Trace Heating | PS5-79-TE-0044-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0044 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3937 | Trace Heating | PS5-79-TE-0045-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0045 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3938 | Trace Heating | PS5-79-TE-0261-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0261 | PT100 Junction Box | Field | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
3939 | Trace Heating | PS5-79-TE-0209-CD01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-TE-0209 | PT100 Junction Box | Field
3940 | Trace Heating | PS5-79-TE-0064-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0064 | PT100 Junction Box | Field
3941 | Trace Heating | PS5-79-TE-0057-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0057 | PT100 Junction Box | Field
3942 | Trace Heating | PS5-79-TE-0021-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0021 | PT100 Junction Box | Field
3943 | Trace Heating | PS5-79-TE-0128-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0128 | PT100 Junction Box | Field
3944 | Trace Heating | PS5-79-TE-0008-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0008 | PT100 Junction Box | Field
3945 | Trace Heating | PS5-79-TE-0047-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0047 | PT100 Junction Box | Field
3946 | Trace Heating | PS5-79-TE-0052-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0052 | PT100 Junction Box | Field
3947 | Trace Heating | PS5-79-TE-0056-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0056 | PT100 Junction Box | Field
3948 | Trace Heating | PS5-79-TE-0055-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0055 | PT100 Junction Box | Field
3949 | Trace Heating | PS5-79-TE-0028-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0028 | PT100 Junction Box | Field
3950 | Trace Heating | PS5-79-TE-0294-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0294 | PT100 Junction Box | Field
3951 | Trace Heating | PS5-79-TE-0293-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0293 | PT100 Junction Box | Field
3952 | Trace Heating | PS5-79-TE-0129-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0129 | PT100 Junction Box | Field
3953 | Trace Heating | PS5-79-TE-0073-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0073 | PT100 Junction Box | Field
3954 | Trace Heating | PS5-79-TE-0010-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0010 | PT100 Junction Box | Field
3955 | Trace Heating | PS5-79-TE-0124-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0124 | PT100 Junction Box | Field
3956 | Trace Heating | PS5-79-TE-0295-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0295 | PT100 Junction Box | Field
3957 | Trace Heating | PS5-79-TE-0030-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0030 | PT100 Junction Box | Field
3958 | Trace Heating | PS5-79-TE-0127-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0127 | PT100 Junction Box | Field
3959 | Trace Heating | PS5-79-TE-0051-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0051 | PT100 Junction Box | Field
3960 | Trace Heating | PS5-79-TE-0032-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0032 | PT100 Junction Box | Field
3961 | Trace Heating | PS5-79-TE-0033-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0033 | PT100 Junction Box | Field
3962 | Trace Heating | PS5-79-TE-0126-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0126 | PT100 Junction Box | Field
3963 | Trace Heating | PS5-79-TE-0125-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0125 | PT100 Junction Box | Field
3964 | Trace Heating | PS5-79-TE-0011-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0011 | PT100 Junction Box | Field
3965 | Trace Heating | PS5-79-TE-0301-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0301 | PT100 Junction Box | Field
3966 | Trace Heating | PS5-79-TE-0001-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0001 | PT100 Junction Box | Field
3967 | Trace Heating | PS5-79-TE-0009-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0009 | PT100 Junction Box | Field
3968 | Trace Heating | PS5-79-TE-0014-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0014 | PT100 Junction Box | Field
3969 | Trace Heating | PS5-79-TE-0034-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0034 | PT100 Junction Box | Field
3970 | Trace Heating | PS5-79-TE-0353-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0353 | PT100 Junction Box | Field
3971 | Trace Heating | PS5-71-TE-0362-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-71-TE-0362 | PT100 Junction Box | Field
3972 | Trace Heating | PS5-79-TE-0132-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0132 | PT100 Junction Box | Field
3973 | Trace Heating | PS5-79-TE-0131-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0131 | PT100 Junction Box | Field
3974 | Trace Heating | PS5-79-TE-0040-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0040 | PT100 Junction Box | Field
3975 | Trace Heating | PS5-79-TE-0233-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0233 | PT100 Junction Box | Field
3976 | Trace Heating | PS5-79-TE-0054-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0054 | PT100 Junction Box | Field
3977 | Trace Heating | PS5-79-TE-0022-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0022 | PT100 Junction Box | Field
3978 | Trace Heating | PS5-79-TE-0078-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0078 | PT100 Junction Box | Field
3979 | Trace Heating | PS5-79-TE-0105-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0105 | PT100 Junction Box | Field
3980 | Trace Heating | PS5-79-TE-0029-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0029 | PT100 Junction Box | Field
3981 | Trace Heating | PS5-79-TE-0035-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0035 | PT100 Junction Box | Field
3982 | Trace Heating | PS5-79-TE-0094-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0094 | PT100 Junction Box | Field
3983 | Trace Heating | PS5-79-TE-0120-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0120 | PT100 Junction Box | Field
3984 | Trace Heating | PS5-79-TE-0095-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0095 | PT100 Junction Box | Field
3985 | Trace Heating | PS5-79-TE-0087-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0087 | PT100 Junction Box | Field
3986 | Trace Heating | PS5-79-TE-0119-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0119 | PT100 Junction Box | Field
3987 | Trace Heating | PS5-79-TE-0117-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0117 | PT100 Junction Box | Field
3988 | Trace Heating | PS5-79-TE-0323-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0323 | PT100 Junction Box | Field
3989 | Trace Heating | PS5-79-TE-0096-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0096 | PT100 Junction Box | Field
3990 | Trace Heating | PS5-79-TE-0079-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0079 | PT100 Junction Box | Field
3991 | Trace Heating | PS5-79-TE-0345-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0345 | PT100 Junction Box | Field
3992 | Trace Heating | PS5-79-TE-0104-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0104 | PT100 Junction Box | Field
3993 | Trace Heating | PS5-79-TE-0230-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0230 | PT100 Junction Box | Field
3994 | Trace Heating | PS5-79-TE-0093-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0093 | PT100 Junction Box | Field
3995 | Trace Heating | PS5-79-TE-0088-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0088 | PT100 Junction Box | Field
3996 | Trace Heating | PS5-79-TE-0089-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0089 | PT100 Junction Box | Field
3997 | Trace Heating | PS5-79-TE-0091-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0091 | PT100 Junction Box | Field
3998 | Trace Heating | PS5-79-TE-0097-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0097 | PT100 Junction Box | Field
3999 | Trace Heating | PS5-79-TE-0321-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0321 | PT100 Junction Box | Field
4000 | Trace Heating | PS5-79-TE-0227-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-79-TE-0227 | PT100 Junction Box | Field
4001 | Trace Heating | PS5-60-TE-0364-CD01 | PS5-79-IG-0010 | Heat Tracing Panel | Outdoor | PS5-60-TE-0364 | PT100 Junction Box | Field
4002 | Trace Heating | PS5-79-TE-0286-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0286 | PT100 Junction Box | Field
4003 | Trace Heating | PS5-79-TE-0347-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0347 | PT100 Junction Box | Field
4004 | Trace Heating | PS5-79-TE-0289-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0289 | PT100 Junction Box | Field
4005 | Trace Heating | PS5-79-TE-0342-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0342 | PT100 Junction Box | Field
4006 | Trace Heating | PS5-79-TE-0232-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0232 | PT100 Junction Box | Field
4007 | Trace Heating | PS5-79-TE-0231-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0231 | PT100 Junction Box | Field
4008 | Trace Heating | PS5-79-TE-0288-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0288 | PT100 Junction Box | Field
4009 | Trace Heating | PS5-79-TE-0225-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0225 | PT100 Junction Box | Field
4010 | Trace Heating | PS5-79-TE-0324-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0324 | PT100 Junction Box | Field
4011 | Trace Heating | PS5-79-TE-0080-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0080 | PT100 Junction Box | Field
4012 | Trace Heating | PS5-79-TE-0065-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0065 | PT100 Junction Box | Field
4013 | Trace Heating | PS5-79-TE-0287-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0287 | PT100 Junction Box | Field
4014 | Trace Heating | PS5-79-TE-0277-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0277 | PT100 Junction Box | Field
4015 | Trace Heating | PS5-79-TE-0276-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0276 | PT100 Junction Box | Field
4016 | Trace Heating | PS5-79-TE-0226-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0226 | PT100 Junction Box | Field
4017 | Trace Heating | PS5-79-TE-0340-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0340 | PT100 Junction Box | Field
4018 | Trace Heating | PS5-79-TE-0336-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0336 | PT100 Junction Box | Field
4019 | Trace Heating | PS5-79-TE-0031-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0031 | PT100 Junction Box | Field
4020 | Trace Heating | PS5-79-TE-0016-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0016 | PT100 Junction Box | Field
4021 | Trace Heating | PS5-79-TE-0038-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0038 | PT100 Junction Box | Field
4022 | Trace Heating | PS5-79-TE-0341-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0341 | PT100 Junction Box | Field
4023 | Trace Heating | PS5-79-TE-0337-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0337 | PT100 Junction Box | Field
4024 | Trace Heating | PS5-79-TE-0050-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0050 | PT100 Junction Box | Field
4025 | Trace Heating | PS5-79-TE-0048-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0048 | PT100 Junction Box | Field
4026 | Trace Heating | PS5-79-TE-0069-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0069 | PT100 Junction Box | Field
4027 | Trace Heating | PS5-79-TE-0349-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0349 | PT100 Junction Box | Field
4028 | Trace Heating | PS5-79-TE-0338-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-79-TE-0338 | PT100 Junction Box | Field
4029 | Trace Heating | PS5-60-TE-0368-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-60-TE-0368 | PT100 Junction Box | Field
4030 | Trace Heating | PS5-60-TE-0369-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-60-TE-0369 | PT100 Junction Box | Field
4031 | Trace Heating | PS5-60-TE-0370-CD01 | PS5-79-IG-0011 | Heat Tracing Panel | Outdoor | PS5-60-TE-0370 | PT100 Junction Box | Field
4032 | Trace Heating | PS5-79-TE-0251-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0251 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4033 | Trace Heating | PS5-79-TE-0297-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0297 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4034 | Trace Heating | PS5-79-TE-0296-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0296 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4035 | Trace Heating | PS5-79-TE-0012-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0012 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4036 | Trace Heating | PS5-79-TE-0259-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0259 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4037 | Trace Heating | PS5-79-TE-0257-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0257 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4038 | Trace Heating | PS5-79-TE-0258-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0258 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4039 | Trace Heating | PS5-79-TE-0098-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0098 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4040 | Trace Heating | PS5-79-TE-0300-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0300 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4041 | Trace Heating | PS5-79-TE-0123-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0123 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4042 | Trace Heating | PS5-79-TE-0248-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0248 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4043 | Trace Heating | PS5-79-TE-0254-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0254 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4044 | Trace Heating | PS5-79-TE-0310-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0310 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4045 | Trace Heating | PS5-79-TE-0263-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0263 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4046 | Trace Heating | PS5-79-TE-0122-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0122 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4047 | Trace Heating | PS5-79-TE-0110-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0110 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4048 | Trace Heating | PS5-79-TE-0256-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0256 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4049 | Trace Heating | PS5-79-TE-0320-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0320 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4050 | Trace Heating | PS5-79-TE-0255-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0255 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4051 | Trace Heating | PS5-79-TE-0017-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0017 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4052 | Trace Heating | PS5-79-TE-0250-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0250 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4053 | Trace Heating | PS5-79-TE-0249-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0249 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4054 | Trace Heating | PS5-79-TE-0318-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0318 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4055 | Trace Heating | PS5-79-TE-0309-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0309 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4056 | Trace Heating | PS5-79-TE-0018-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0018 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4057 | Trace Heating | PS5-79-TE-0130-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0130 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4058 | Trace Heating | PS5-79-TE-0299-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0299 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4059 | Trace Heating | PS5-79-TE-0308-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0308 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4060 | Trace Heating | PS5-79-TE-0013-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0013 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4061 | Trace Heating | PS5-79-TE-0015-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0015 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4062 | Trace Heating | PS5-79-TE-0133-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0133 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4063 | Trace Heating | PS5-79-TE-0298-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0298 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4064 | Trace Heating | PS5-79-TE-0026-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0026 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4065 | Trace Heating | PS5-79-TE-0138-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-79-TE-0138 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4066 | Trace Heating | PS5-25-TE-0364-CD01 | PS5-79-IG-0012 | Heat Tracing Panel | Outdoor | PS5-25-TE-0364 | PT100 Junction Box | Field | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4067 | Trace Heating | PS5-79-BE-0175-CW01 | PS5-79-IG-0009 | Heat Tracing Panel | Outdoor | PS5-79-BE-0175 | Marshalling Box | Field
4068 | Trace Heating | PS5-79-IP-9101-CW01 | PS5-79-BE-0175 | Marshalling Box | Outdoor | PS5-79-IP-9101 | ETS-05 | Field
4069 | Trace Heating | PS5-79-IP-9102-CW01 | PS5-79-BE-0175 | Marshalling Box | Outdoor | PS5-79-IP-9102 | ETS-05 | Field
4070 | Trace Heating | PS5-79-BE-0176-CW01 | PS5-79-IG-0007 | Heat Tracing Panel | Outdoor | PS5-79-BE-0176 | Marshalling Box | Field
4071 | Trace Heating | PS5-79-IP-9103-CW01 | PS5-79-BE-0176 | Marshalling Box | Outdoor | PS5-79-IP-9103 | ETS-05 | Field
4072 | Trace Heating | PS5-79-IP-9104-CW01 | PS5-79-BE-0176 | Marshalling Box | Outdoor | PS5-79-IP-9104 | ETS-05 | Field
4073 | Trace Heating | PS5-79-BE-0177-CW01 | PS5-79-IG-0008 | Heat Tracing Panel | Outdoor | PS5-79-BE-0177 | Marshalling Box | Field
4074 | Trace Heating | PS5-79-IP-9105-CW01 | PS5-79-BE-0177 | Marshalling Box | Outdoor | PS5-79-IP-9105 | ETS-05 | Field
4075 | Trace Heating | PS5-79-IP-9106-CW01 | PS5-79-BE-0177 | Marshalling Box | Outdoor | PS5-79-IP-9106 | ETS-05 | Field
4076 | Trace Heating | PS5-79-TE-0175-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0175 | PT100 Junction Box | Field
4077 | Trace Heating | PS5-79-TE-0176-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0176 | PT100 Junction Box | Field
4078 | Trace Heating | PS5-79-TE-0178-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0178 | PT100 Junction Box | Field
4079 | Trace Heating | PS5-79-TE-0177-CD01 | PS5-79-IG-0006 | Heat Tracing Panel | Outdoor | PS5-79-TE-0177 | PT100 Junction Box | Field
4080 | Trace Heating | PS5-71-BE-0363-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4081 | Trace Heating | PS5-79-BE-0123-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4082 | Trace Heating | PS5-79-BE-0309-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4083 | Trace Heating | PS5-79-BE-0018-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4084 | Trace Heating | PS5-79-BE-0130-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4085 | Trace Heating | PS5-79-BE-0015-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4086 | Trace Heating | PS5-79-BE-0133-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4087 | Trace Heating | PS5-79-BE-0298-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4088 | Trace Heating | PS5-79-BE-0026-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4089 | Trace Heating | PS5-79-TE-0309-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4090 | Trace Heating | PS5-79-TE-0018-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4091 | Trace Heating | PS5-79-TE-0130-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4092 | Trace Heating | PS5-79-IG-0001-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4093 | Trace Heating | PS5-79-IG-0002-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4094 | Trace Heating | PS5-79-IG-0003-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4095 | Trace Heating | PS5-79-IG-0004-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4096 | Trace Heating | PS5-79-IG-0005-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4097 | Trace Heating | PS5-79-IG-0006-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4098 | Trace Heating | PS5-79-IG-0007-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4099 | Trace Heating | PS5-79-IG-0008-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4100 | Trace Heating | PS5-79-IG-0009-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4101 | Trace Heating | PS5-79-IG-0010-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4102 | Trace Heating | PS5-79-IG-0011-CL01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4103 | Trace Heating | PS5-79-IG-0012-CL01
4104 | Trace Heating | PS5-79-IG-0001-CG01
4105 | Trace Heating | PS5-79-IG-0002-CG01
4106 | Trace Heating | PS5-79-IG-0003-CG01
4107 | Trace Heating | PS5-79-IG-0004-CG01
4108 | Trace Heating | PS5-79-IG-0005-CG01
4109 | Trace Heating | PS5-79-IG-0006-CG01
4110 | Trace Heating | PS5-79-IG-0007-CG01
4111 | Trace Heating | PS5-79-IG-0008-CG01
4112 | Trace Heating | PS5-79-IG-0009-CG01
4113 | Trace Heating | PS5-79-IG-0010-CG01
4114 | Trace Heating | PS5-79-IG-0011-CG01
4115 | Trace Heating | PS5-79-IG-0012-CG01
4116 | Trace Heating | PS5-79-IG-0001-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4117 | Trace Heating | PS5-79-IG-0002-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4118 | Trace Heating | PS5-79-IG-0003-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4119 | Trace Heating | PS5-79-IG-0004-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4120 | Trace Heating | PS5-79-IG-0005-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4121 | Trace Heating | PS5-79-IG-0006-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4122 | Trace Heating | PS5-79-IG-0007-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4123 | Trace Heating | PS5-79-IG-0008-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4124 | Trace Heating | PS5-79-IG-0009-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4125 | Trace Heating | PS5-79-IG-0010-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4126 | Trace Heating | PS5-79-IG-0011-CD01 | [6 empty] | CPP-RFI-68-33-2-03-0302 | CPP-RFI-68-33-2-03-0302 |  | 2026-05-26 | TZ-MID-68-WPR2-151115 To perform cleanning for EHT Distribution board body and surround area
4127 | Trace Heating | PS5-79-IG-0012-CD01
4128 | Trace Heating | PS5-79-BE-0316-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4129 | Trace Heating | PS5-79-BE-0315-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4130 | Trace Heating | PS5-79-BE-0168-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4131 | Trace Heating | PS5-79-BE-0170-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4132 | Trace Heating | PS5-79-BE-0163-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4133 | Trace Heating | PS5-79-BE-0167-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4134 | Trace Heating | PS5-79-SP-0167-CL01
4135 | Trace Heating | PS5-79-BE-0169-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4136 | Trace Heating | PS5-79-SP-0169-CL01
4137 | Trace Heating | PS5-79-BE-0159-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4138 | Trace Heating | PS5-79-BE-0164-CL01
4139 | Trace Heating | PS5-79-BE-0151-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4140 | Trace Heating | PS5-79-BE-0356-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4141 | Trace Heating | PS5-79-BE-0206-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4142 | Trace Heating | PS5-79-BE-0148-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4143 | Trace Heating | PS5-79-BE-0314-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4144 | Trace Heating | PS5-79-BE-0149-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4145 | Trace Heating | PS5-79-BE-0234-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4146 | Trace Heating | PS5-79-BE-0114-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4147 | Trace Heating | PS5-79-BE-0165-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4148 | Trace Heating | PS5-79-BE-0166-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4149 | Trace Heating | PS5-79-BE-0157-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4150 | Trace Heating | PS5-79-BE-0153-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4151 | Trace Heating | PS5-79-BE-0313-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4152 | Trace Heating | PS5-79-BE-0188-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4153 | Trace Heating | PS5-79-BE-0202-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4154 | Trace Heating | PS5-79-BE-0103-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4155 | Trace Heating | PS5-79-BE-0317-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4156 | Trace Heating | PS5-79-BE-0306-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Field run cable tray not yet complete
4157 | Trace Heating | PS5-79-BE-0197-CL01
4158 | Trace Heating | PS5-71-BE-0361-CL01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side
4159 | Trace Heating | PS5-79-BE-0181-CL01
4160 | Trace Heating | PS5-79-BE-0184-CL01
4161 | Trace Heating | PS5-79-BE-0302-CL01
4162 | Trace Heating | PS5-79-BE-0185-CL01
4163 | Trace Heating | PS5-79-BE-0182-CL01
4164 | Trace Heating | PS5-79-BE-0303-CL01
4165 | Trace Heating | PS5-79-BE-0304-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4166 | Trace Heating | PS5-79-BE-0325-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4167 | Trace Heating | PS5-79-BE-0311-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4168 | Trace Heating | PS5-79-BE-0312-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4169 | Trace Heating | PS5-79-BE-0173-CL01
4170 | Trace Heating | PS5-79-BE-0183-CL01
4171 | Trace Heating | PS5-79-BE-0355-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4172 | Trace Heating | PS5-79-BE-0354-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4173 | Trace Heating | PS5-79-BE-0201-CL01
4174 | Trace Heating | PS5-79-BE-0172-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4175 | Trace Heating | PS5-79-BE-0180-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4176 | Trace Heating | PS5-79-BE-0191-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4177 | Trace Heating | PS5-79-BE-0192-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4178 | Trace Heating | PS5-79-BE-0193-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4179 | Trace Heating | PS5-79-BE-0196-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
4180 | Trace Heating | PS5-79-BE-0179-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4181 | Trace Heating | PS5-79-BE-0326-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4182 | Trace Heating | PS5-79-BE-0238-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
4183 | Trace Heating | PS5-79-BE-0174-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4184 | Trace Heating | PS5-79-BE-0244-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
4185 | Trace Heating | PS5-79-BE-0199-CL01
4186 | Trace Heating | PS5-79-BE-0187-CL01
4187 | Trace Heating | PS5-79-BE-0190-CL01
4188 | Trace Heating | PS5-79-BE-0023-CL01
4189 | Trace Heating | PS5-79-BE-0278-CL01
4190 | Trace Heating | PS5-79-BE-0307-CL01
4191 | Trace Heating | PS5-79-BE-0198-CL01
4192 | Trace Heating | PS5-79-BE-0046-CL01
4193 | Trace Heating | PS5-79-BE-0195-CL01
4194 | Trace Heating | PS5-79-BE-0252-CL01
4195 | Trace Heating | PS5-79-BE-0253-CL01
4196 | Trace Heating | PS5-79-BE-0200-CL01
4197 | Trace Heating | PS5-79-BE-0194-CL01
4198 | Trace Heating | PS5-79-BE-0246-CL01
4199 | Trace Heating | PS5-79-BE-0189-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
4200 | Trace Heating | PS5-79-BE-0210-CL01
4201 | Trace Heating | PS5-79-BE-0186-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
4202 | Trace Heating | PS5-79-BE-0279-CL01
4203 | Trace Heating | PS5-79-BE-0260-CL01
4204 | Trace Heating | PS5-79-BE-0211-CL01
4205 | Trace Heating | PS5-79-BE-0305-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4206 | Trace Heating | PS5-79-BE-0322-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4207 | Trace Heating | PS5-79-BE-0346-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4208 | Trace Heating | PS5-79-BE-0348-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
4209 | Trace Heating | PS5-79-BE-0352-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
4210 | Trace Heating | PS5-79-BE-0242-CL01
4211 | Trace Heating | PS5-79-BE-0109-CL01
4212 | Trace Heating | PS5-79-BE-0113-CL01
4213 | Trace Heating | PS5-79-BE-0106-CL01
4214 | Trace Heating | PS5-79-BE-0351-CL01
4215 | Trace Heating | PS5-79-BE-0243-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
4216 | Trace Heating | PS5-60-BE-0365-CL01
4217 | Trace Heating | PS5-79-BE-0280-CL01
4218 | Trace Heating | PS5-79-BE-0331-CL01
4219 | Trace Heating | PS5-79-BE-0327-CL01
4220 | Trace Heating | PS5-79-BE-0266-CL01
4221 | Trace Heating | PS5-79-BE-0265-CL01
4222 | Trace Heating | PS5-79-BE-0212-CL01
4223 | Trace Heating | PS5-79-BE-0049-CL01
4224 | Trace Heating | PS5-79-BE-0329-CL01
4225 | Trace Heating | PS5-79-BE-0285-CL01
4226 | Trace Heating | PS5-79-BE-0220-CL01
4227 | Trace Heating | PS5-79-BE-0217-CL01
4228 | Trace Heating | PS5-79-BE-0219-CL01
4229 | Trace Heating | PS5-79-BE-0237-CL01
4230 | Trace Heating | PS5-79-SP-0237-CL01
4231 | Trace Heating | PS5-79-BE-0282-CL01
4232 | Trace Heating | PS5-79-BE-0213-CL01
4233 | Trace Heating | PS5-79-BE-0086-CL01
4234 | Trace Heating | PS5-79-BE-0214-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4235 | Trace Heating | PS5-79-BE-0283-CL01
4236 | Trace Heating | PS5-79-BE-0092-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
4237 | Trace Heating | PS5-79-BE-0216-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side
4238 | Trace Heating | PS5-79-BE-0215-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4239 | Trace Heating | PS5-79-BE-0099-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4240 | Trace Heating | PS5-79-BE-0171-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4241 | Trace Heating | PS5-79-BE-0264-CL01
4242 | Trace Heating | PS5-79-BE-0281-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4243 | Trace Heating | PS5-79-BE-0284-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4244 | Trace Heating | PS5-60-BE-0366-CL01
4245 | Trace Heating | PS5-79-BE-0332-CL01
4246 | Trace Heating | PS5-79-BE-0330-CL01
4247 | Trace Heating | PS5-79-BE-0269-CL01
4248 | Trace Heating | PS5-79-BE-0267-CL01
4249 | Trace Heating | PS5-79-BE-0268-CL01
4250 | Trace Heating | PS5-79-BE-0334-CL01
4251 | Trace Heating | PS5-79-BE-0333-CL01
4252 | Trace Heating | PS5-79-BE-0272-CL01
4253 | Trace Heating | PS5-79-BE-0270-CL01
4254 | Trace Heating | PS5-79-BE-0271-CL01
4255 | Trace Heating | PS5-79-BE-0335-CL01
4256 | Trace Heating | PS5-79-BE-0339-CL01
4257 | Trace Heating | PS5-79-BE-0275-CL01
4258 | Trace Heating | PS5-79-BE-0273-CL01
4259 | Trace Heating | PS5-79-BE-0274-CL01
4260 | Trace Heating | PS5-79-BE-0328-CL01
4261 | Trace Heating | PS5-79-BE-0061-CL01
4262 | Trace Heating | PS5-79-BE-0218-CL01
4263 | Trace Heating | PS5-79-BE-0229-CL01
4264 | Trace Heating | PS5-79-BE-0223-CL01
4265 | Trace Heating | PS5-79-BE-0224-CL01
4266 | Trace Heating | PS5-79-BE-0221-CL01
4267 | Trace Heating | PS5-79-BE-0235-CL01
4268 | Trace Heating | PS5-79-BE-0222-CL01
4269 | Trace Heating | PS5-79-BE-0350-CL01
4270 | Trace Heating | PS5-79-BE-0228-CL01
4271 | Trace Heating | PS5-79-BE-0236-CL01
4272 | Trace Heating | PS5-60-BE-0367-CL01
4273 | Trace Heating | PS5-79-BE-0136-CL01
4274 | Trace Heating | PS5-79-BE-0027-CL01
4275 | Trace Heating | PS5-79-BE-0039-CL01
4276 | Trace Heating | PS5-79-BE-0037-CL01
4277 | Trace Heating | PS5-79-BE-0025-CL01
4278 | Trace Heating | PS5-79-BE-0343-CL01
4279 | Trace Heating | PS5-79-BE-0118-CL01
4280 | Trace Heating | PS5-79-BE-0137-CL01
4281 | Trace Heating | PS5-79-BE-0024-CL01
4282 | Trace Heating | PS5-79-BE-0150-CL01
4283 | Trace Heating | PS5-79-BE-0203-CL01
4284 | Trace Heating | PS5-79-BE-0204-CL01
4285 | Trace Heating | PS5-79-BE-0262-CL01
4286 | Trace Heating | PS5-79-BE-0102-CL01
4287 | Trace Heating | PS5-79-BE-0081-CL01
4288 | Trace Heating | PS5-79-BE-0036-CL01
4289 | Trace Heating | PS5-79-BE-0066-CL01
4290 | Trace Heating | PS5-79-BE-0067-CL01
4291 | Trace Heating | PS5-79-BE-0245-CL01
4292 | Trace Heating | PS5-79-BE-0134-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4293 | Trace Heating | PS5-79-BE-0063-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4294 | Trace Heating | PS5-79-BE-0154-CL01
4295 | Trace Heating | PS5-79-BE-0319-CL01
4296 | Trace Heating | PS5-79-BE-0290-CL01
4297 | Trace Heating | PS5-79-BE-0152-CL01
4298 | Trace Heating | PS5-79-BE-0002-CL01
4299 | Trace Heating | PS5-79-BE-0005-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4300 | Trace Heating | PS5-79-BE-0146-CL01
4301 | Trace Heating | PS5-79-BE-0041-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4302 | Trace Heating | PS5-79-BE-0135-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150359 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4303 | Trace Heating | PS5-79-BE-0239-CL01
4304 | Trace Heating | PS5-79-IP-9901-CL01
4305 | Trace Heating | PS5-79-IP-9101-CL01
4306 | Trace Heating | PS5-79-IP-9102-CL01
4307 | Trace Heating | PS5-79-BE-0247-CL01
4308 | Trace Heating | PS5-79-BE-0084-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0007
4309 | Trace Heating | PS5-79-BE-0090-CL01
4310 | Trace Heating | PS5-79-BE-0085-CL01
4311 | Trace Heating | PS5-79-BE-0082-CL01
4312 | Trace Heating | PS5-79-BE-0101-CL01
4313 | Trace Heating | PS5-79-BE-0156-CL01
4314 | Trace Heating | PS5-79-BE-0107-CL01
4315 | Trace Heating | PS5-79-BE-0020-CL01
4316 | Trace Heating | PS5-79-BE-0147-CL01
4317 | Trace Heating | PS5-79-BE-0043-CL01
4318 | Trace Heating | PS5-79-BE-0344-CL01
4319 | Trace Heating | PS5-79-BE-0019-CL01
4320 | Trace Heating | PS5-79-BE-0100-CL01
4321 | Trace Heating | PS5-79-BE-0112-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4322 | Trace Heating | PS5-79-BE-0068-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4323 | Trace Heating | PS5-79-BE-0042-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4324 | Trace Heating | PS5-79-BE-0121-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4325 | Trace Heating | PS5-79-BE-0072-CL01
4326 | Trace Heating | PS5-79-BE-0116-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4327 | Trace Heating | PS5-79-BE-0145-CL01
4328 | Trace Heating | PS5-79-BE-0155-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4329 | Trace Heating | PS5-79-BE-0071-CL01
4330 | Trace Heating | PS5-79-BE-0083-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4331 | Trace Heating | PS5-79-BE-0291-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4332 | Trace Heating | PS5-79-BE-0003-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4333 | Trace Heating | PS5-79-BE-0143-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4334 | Trace Heating | PS5-79-BE-0059-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4335 | Trace Heating | PS5-79-BE-0006-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4336 | Trace Heating | PS5-79-BE-0144-CL01
4337 | Trace Heating | PS5-79-BE-0240-CL01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150359 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150359 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4338 | Trace Heating | PS5-79-IP-9902-CL01
4339 | Trace Heating | PS5-79-IP-9103-CL01
4340 | Trace Heating | PS5-79-IP-9104-CL01
4341 | Trace Heating | PS5-79-BE-0241-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
4342 | Trace Heating | PS5-79-BE-0208-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4343 | Trace Heating | PS5-79-BE-0292-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
4344 | Trace Heating | PS5-79-BE-0058-CL01
4345 | Trace Heating | PS5-79-BE-0140-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
4346 | Trace Heating | PS5-79-BE-0004-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
4347 | Trace Heating | PS5-79-BE-0007-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
4348 | Trace Heating | PS5-79-BE-0161-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4349 | Trace Heating | PS5-79-BE-0139-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
4350 | Trace Heating | PS5-79-BE-0162-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4351 | Trace Heating | PS5-79-BE-0074-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4352 | Trace Heating | PS5-79-BE-0142-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
4353 | Trace Heating | PS5-79-BE-0160-CL01
4354 | Trace Heating | PS5-79-BE-0077-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4355 | Trace Heating | PS5-79-BE-0075-CL01
4356 | Trace Heating | PS5-79-BE-0053-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4357 | Trace Heating | PS5-79-BE-0076-CL01
4358 | Trace Heating | PS5-79-BE-0070-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4359 | Trace Heating | PS5-79-BE-0158-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4360 | Trace Heating | PS5-79-BE-0060-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4361 | Trace Heating | PS5-79-BE-0115-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4362 | Trace Heating | PS5-79-BE-0108-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4363 | Trace Heating | PS5-79-BE-0111-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4364 | Trace Heating | PS5-79-BE-0062-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4365 | Trace Heating | PS5-79-BE-0141-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150359 Cable coiled around 10 meter at field side waiting for field run cable tray
4366 | Trace Heating | PS5-79-BE-0207-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4367 | Trace Heating | PS5-79-BE-0205-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4368 | Trace Heating | PS5-79-BE-0044-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4369 | Trace Heating | PS5-79-BE-0045-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4370 | Trace Heating | PS5-79-BE-0261-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4371 | Trace Heating | PS5-79-BE-0209-CL01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150359 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150359 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150359 Field run cable tray to be install at equipment side
4372 | Trace Heating | PS5-79-IP-9903-CL01
4373 | Trace Heating | PS5-79-IP-9105-CL01
4374 | Trace Heating | PS5-79-IP-9106-CL01
4375 | Trace Heating | PS5-79-BE-0064-CL01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150359 To be complete cable dressing up to both side; TZ-MID-68-NVS1-150359 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150359 To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0006
4376 | Trace Heating | PS5-79-BE-0057-CL01
4377 | Trace Heating | PS5-79-BE-0021-CL01
4378 | Trace Heating | PS5-79-BE-0128-CL01
4379 | Trace Heating | PS5-79-BE-0008-CL01
4380 | Trace Heating | PS5-79-SP-0008-CL01
4381 | Trace Heating | PS5-79-BE-0047-CL01
4382 | Trace Heating | PS5-79-BE-0052-CL01
4383 | Trace Heating | PS5-79-BE-0056-CL01
4384 | Trace Heating | PS5-79-BE-0055-CL01
4385 | Trace Heating | PS5-79-BE-0028-CL01
4386 | Trace Heating | PS5-79-BE-0294-CL01
4387 | Trace Heating | PS5-79-BE-0293-CL01
4388 | Trace Heating | PS5-79-BE-0129-CL01
4389 | Trace Heating | PS5-79-BE-0073-CL01
4390 | Trace Heating | PS5-79-BE-0010-CL01
4391 | Trace Heating | PS5-79-SP-0010-CL01
4392 | Trace Heating | PS5-79-BE-0124-CL01
4393 | Trace Heating | PS5-79-BE-0295-CL01
4394 | Trace Heating | PS5-79-BE-0030-CL01
4395 | Trace Heating | PS5-79-BE-0127-CL01
4396 | Trace Heating | PS5-79-BE-0051-CL01
4397 | Trace Heating | PS5-79-BE-0032-CL01
4398 | Trace Heating | PS5-79-BE-0033-CL01
4399 | Trace Heating | PS5-79-BE-0126-CL01
4400 | Trace Heating | PS5-79-BE-0125-CL01
4401 | Trace Heating | PS5-79-BE-0011-CL01
4402 | Trace Heating | PS5-79-BE-0301-CL01
4403 | Trace Heating | PS5-79-BE-0001-CL01
4404 | Trace Heating | PS5-79-BE-0009-CL01
4405 | Trace Heating | PS5-79-BE-0014-CL01
4406 | Trace Heating | PS5-79-BE-0034-CL01
4407 | Trace Heating | PS5-79-BE-0353-CL01
4408 | Trace Heating | PS5-71-BE-0362-CL01
4409 | Trace Heating | PS5-79-BE-0132-CL01
4410 | Trace Heating | PS5-79-BE-0131-CL01
4411 | Trace Heating | PS5-79-BE-0040-CL01
4412 | Trace Heating | PS5-79-BE-0233-CL01
4413 | Trace Heating | PS5-79-BE-0054-CL01
4414 | Trace Heating | PS5-79-BE-0022-CL01
4415 | Trace Heating | PS5-79-BE-0078-CL01
4416 | Trace Heating | PS5-79-BE-0105-CL01
4417 | Trace Heating | PS5-79-BE-0029-CL01
4418 | Trace Heating | PS5-79-BE-0035-CL01
4419 | Trace Heating | PS5-79-BE-0094-CL01
4420 | Trace Heating | PS5-79-BE-0120-CL01
4421 | Trace Heating | PS5-79-BE-0095-CL01
4422 | Trace Heating | PS5-79-BE-0087-CL01
4423 | Trace Heating | PS5-79-BE-0119-CL01
4424 | Trace Heating | PS5-79-BE-0117-CL01
4425 | Trace Heating | PS5-79-BE-0323-CL01
4426 | Trace Heating | PS5-79-BE-0096-CL01
4427 | Trace Heating | PS5-79-BE-0079-CL01
4428 | Trace Heating | PS5-79-BE-0345-CL01
4429 | Trace Heating | PS5-79-BE-0104-CL01
4430 | Trace Heating | PS5-79-BE-0230-CL01
4431 | Trace Heating | PS5-79-BE-0093-CL01
4432 | Trace Heating | PS5-79-BE-0088-CL01
4433 | Trace Heating | PS5-79-BE-0089-CL01
4434 | Trace Heating | PS5-79-BE-0091-CL01
4435 | Trace Heating | PS5-79-BE-0097-CL01
4436 | Trace Heating | PS5-79-BE-0321-CL01
4437 | Trace Heating | PS5-79-BE-0227-CL01
4438 | Trace Heating | PS5-60-BE-0364-CL01
4439 | Trace Heating | PS5-79-BE-0286-CL01
4440 | Trace Heating | PS5-79-BE-0347-CL01
4441 | Trace Heating | PS5-79-BE-0289-CL01
4442 | Trace Heating | PS5-79-BE-0342-CL01
4443 | Trace Heating | PS5-79-BE-0232-CL01
4444 | Trace Heating | PS5-79-BE-0231-CL01
4445 | Trace Heating | PS5-79-BE-0288-CL01
4446 | Trace Heating | PS5-79-BE-0225-CL01
4447 | Trace Heating | PS5-79-BE-0324-CL01
4448 | Trace Heating | PS5-79-BE-0080-CL01
4449 | Trace Heating | PS5-79-BE-0065-CL01
4450 | Trace Heating | PS5-79-BE-0287-CL01
4451 | Trace Heating | PS5-79-BE-0277-CL01
4452 | Trace Heating | PS5-79-BE-0276-CL01
4453 | Trace Heating | PS5-79-BE-0226-CL01
4454 | Trace Heating | PS5-79-BE-0340-CL01
4455 | Trace Heating | PS5-79-BE-0336-CL01
4456 | Trace Heating | PS5-79-BE-0031-CL01
4457 | Trace Heating | PS5-79-BE-0016-CL01
4458 | Trace Heating | PS5-79-BE-0038-CL01
4459 | Trace Heating | PS5-79-BE-0341-CL01
4460 | Trace Heating | PS5-79-BE-0337-CL01
4461 | Trace Heating | PS5-79-BE-0050-CL01
4462 | Trace Heating | PS5-79-BE-0048-CL01
4463 | Trace Heating | PS5-79-BE-0069-CL01
4464 | Trace Heating | PS5-79-BE-0349-CL01
4465 | Trace Heating | PS5-79-BE-0338-CL01
4466 | Trace Heating | PS5-60-BE-0368-CL01
4467 | Trace Heating | PS5-60-BE-0369-CL01
4468 | Trace Heating | PS5-60-BE-0370-CL01
4469 | Trace Heating | PS5-79-BE-0251-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4470 | Trace Heating | PS5-79-BE-0297-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4471 | Trace Heating | PS5-79-BE-0296-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4472 | Trace Heating | PS5-79-BE-0012-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
4473 | Trace Heating | PS5-79-BE-0259-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
4474 | Trace Heating | PS5-79-BE-0257-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
4475 | Trace Heating | PS5-79-BE-0258-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4476 | Trace Heating | PS5-79-BE-0098-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4477 | Trace Heating | PS5-79-BE-0300-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4478 | Trace Heating | PS5-79-BE-0248-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4479 | Trace Heating | PS5-79-BE-0254-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
4480 | Trace Heating | PS5-79-BE-0310-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
4481 | Trace Heating | PS5-79-BE-0263-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
4482 | Trace Heating | PS5-79-BE-0122-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
4483 | Trace Heating | PS5-79-BE-0110-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
4484 | Trace Heating | PS5-79-BE-0256-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
4485 | Trace Heating | PS5-79-BE-0320-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
4486 | Trace Heating | PS5-79-BE-0255-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
4487 | Trace Heating | PS5-79-BE-0017-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
4488 | Trace Heating | PS5-79-BE-0250-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
4489 | Trace Heating | PS5-79-BE-0249-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
4490 | Trace Heating | PS5-79-BE-0318-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
4491 | Trace Heating | PS5-79-SP-0018-CL01
4492 | Trace Heating | PS5-79-BE-0299-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
4493 | Trace Heating | PS5-79-BE-0308-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
4494 | Trace Heating | PS5-79-BE-0013-CL01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150359 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150359 Cable dressing to be done at both side; TZ-MID-68-NVS1-150359 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.; TZ-MID-68-NVS1-150359 Cable shortage at field side coiled only 2 Meter
4495 | Trace Heating | PS5-79-SP-0133-CL01
4496 | Trace Heating | PS5-79-BE-0138-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150359 Field Run Cable Tray to be installed
4497 | Trace Heating | PS5-25-BE-0364-CL01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150359 Cable Dressing to complete at both side
4498 | Trace Heating | PS5-79-TE-0316-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4499 | Trace Heating | PS5-79-TE-0315-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4500 | Trace Heating | PS5-79-TE-0168-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4501 | Trace Heating | PS5-79-TE-0170-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4502 | Trace Heating | PS5-79-TE-0163-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4503 | Trace Heating | PS5-79-TE-0167-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4504 | Trace Heating | PS5-79-TE-0169-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4505 | Trace Heating | PS5-79-TE-0159-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4506 | Trace Heating | PS5-79-TE-0164-CD01
4507 | Trace Heating | PS5-79-TE-0151-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4508 | Trace Heating | PS5-79-TE-0356-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4509 | Trace Heating | PS5-79-TE-0206-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4510 | Trace Heating | PS5-79-TE-0148-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4511 | Trace Heating | PS5-79-TE-0314-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4512 | Trace Heating | PS5-79-TE-0149-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4513 | Trace Heating | PS5-79-TE-0234-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4514 | Trace Heating | PS5-79-TE-0114-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4515 | Trace Heating | PS5-79-TE-0165-CD01
4516 | Trace Heating | PS5-79-TE-0166-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4517 | Trace Heating | PS5-79-TE-0157-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4518 | Trace Heating | PS5-79-TE-0153-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4519 | Trace Heating | PS5-79-TE-0313-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4520 | Trace Heating | PS5-79-TE-0188-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4521 | Trace Heating | PS5-79-TE-0202-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4522 | Trace Heating | PS5-79-TE-0103-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4523 | Trace Heating | PS5-79-TE-0317-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4524 | Trace Heating | PS5-79-TE-0306-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Field run cable tray not yet complete
4525 | Trace Heating | PS5-79-TE-0197-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4526 | Trace Heating | PS5-71-TE-0361-CD01 | [6 empty] | CPP-RFI-68-331-05-0322 | CPP-RFI-68-331-05-0322 |  | 2026-06-07 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side
4527 | Trace Heating | PS5-79-TE-0181-CD01
4528 | Trace Heating | PS5-79-TE-0184-CD01
4529 | Trace Heating | PS5-79-TE-0302-CD01
4530 | Trace Heating | PS5-79-TE-0185-CD01
4531 | Trace Heating | PS5-79-TE-0182-CD01
4532 | Trace Heating | PS5-79-TE-0303-CD01
4533 | Trace Heating | PS5-79-TE-0304-CD01
4534 | Trace Heating | PS5-79-TE-0325-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4535 | Trace Heating | PS5-79-TE-0311-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4536 | Trace Heating | PS5-79-TE-0312-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4537 | Trace Heating | PS5-79-TE-0173-CD01
4538 | Trace Heating | PS5-79-TE-0183-CD01
4539 | Trace Heating | PS5-79-TE-0355-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4540 | Trace Heating | PS5-79-TE-0354-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4541 | Trace Heating | PS5-79-TE-0201-CD01
4542 | Trace Heating | PS5-79-TE-0172-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4543 | Trace Heating | PS5-79-TE-0180-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4544 | Trace Heating | PS5-79-TE-0191-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4545 | Trace Heating | PS5-79-TE-0192-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4546 | Trace Heating | PS5-79-TE-0193-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4547 | Trace Heating | PS5-79-TE-0196-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
4548 | Trace Heating | PS5-79-TE-0179-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4549 | Trace Heating | PS5-79-TE-0326-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4550 | Trace Heating | PS5-79-TE-0238-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
4551 | Trace Heating | PS5-79-TE-0174-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4552 | Trace Heating | PS5-79-TE-0244-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
4553 | Trace Heating | PS5-79-TE-0199-CD01
4554 | Trace Heating | PS5-79-TE-0187-CD01
4555 | Trace Heating | PS5-79-TE-0190-CD01
4556 | Trace Heating | PS5-71-TE-0363-CD01
4557 | Trace Heating | PS5-79-TE-0023-CD01
4558 | Trace Heating | PS5-79-TE-0278-CD01
4559 | Trace Heating | PS5-79-TE-0307-CD01
4560 | Trace Heating | PS5-79-TE-0198-CD01
4561 | Trace Heating | PS5-79-TE-0046-CD01
4562 | Trace Heating | PS5-79-TE-0195-CD01
4563 | Trace Heating | PS5-79-TE-0252-CD01
4564 | Trace Heating | PS5-79-TE-0253-CD01
4565 | Trace Heating | PS5-79-TE-0200-CD01
4566 | Trace Heating | PS5-79-TE-0194-CD01
4567 | Trace Heating | PS5-79-TE-0246-CD01
4568 | Trace Heating | PS5-79-TE-0189-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
4569 | Trace Heating | PS5-79-TE-0210-CD01
4570 | Trace Heating | PS5-79-TE-0186-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
4571 | Trace Heating | PS5-79-TE-0279-CD01
4572 | Trace Heating | PS5-79-TE-0260-CD01
4573 | Trace Heating | PS5-79-TE-0211-CD01
4574 | Trace Heating | PS5-79-TE-0305-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4575 | Trace Heating | PS5-79-TE-0322-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4576 | Trace Heating | PS5-79-TE-0346-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0269 | CPP-RFI-68-33/1-05-0269 |  | 2026-05-20 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable Ladder at panel side not yet install (PS5-79-IG-0002) and field run cable tray at field side
4577 | Trace Heating | PS5-79-TE-0348-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
4578 | Trace Heating | PS5-79-TE-0352-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
4579 | Trace Heating | PS5-79-TE-0242-CD01
4580 | Trace Heating | PS5-79-TE-0109-CD01
4581 | Trace Heating | PS5-79-TE-0113-CD01
4582 | Trace Heating | PS5-79-TE-0106-CD01
4583 | Trace Heating | PS5-79-TE-0351-CD01
4584 | Trace Heating | PS5-79-TE-0243-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
4585 | Trace Heating | PS5-60-TE-0365-CD01
4586 | Trace Heating | PS5-79-TE-0280-CD01
4587 | Trace Heating | PS5-79-TE-0331-CD01
4588 | Trace Heating | PS5-79-TE-0327-CD01
4589 | Trace Heating | PS5-79-TE-0266-CD01
4590 | Trace Heating | PS5-79-TE-0265-CD01
4591 | Trace Heating | PS5-79-TE-0212-CD01
4592 | Trace Heating | PS5-79-TE-0049-CD01
4593 | Trace Heating | PS5-79-TE-0329-CD01
4594 | Trace Heating | PS5-79-TE-0285-CD01
4595 | Trace Heating | PS5-79-TE-0220-CD01
4596 | Trace Heating | PS5-79-TE-0217-CD01
4597 | Trace Heating | PS5-79-TE-0219-CD01
4598 | Trace Heating | PS5-79-TE-0237-CD01
4599 | Trace Heating | PS5-79-TE-0282-CD01
4600 | Trace Heating | PS5-79-TE-0213-CD01
4601 | Trace Heating | PS5-79-TE-0086-CD01
4602 | Trace Heating | PS5-79-TE-0214-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4603 | Trace Heating | PS5-79-TE-0283-CD01
4604 | Trace Heating | PS5-79-TE-0092-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be Install Vertical cable Ladder Panel side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side
4605 | Trace Heating | PS5-79-TE-0216-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4606 | Trace Heating | PS5-79-TE-0215-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4607 | Trace Heating | PS5-79-TE-0099-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4608 | Trace Heating | PS5-79-TE-0171-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4609 | Trace Heating | PS5-79-TE-0264-CD01
4610 | Trace Heating | PS5-79-TE-0281-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4611 | Trace Heating | PS5-79-TE-0284-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Vertical cable ladder to be install at DB panel side (PS5-79-IG-0004)
4612 | Trace Heating | PS5-60-TE-0366-CD01
4613 | Trace Heating | PS5-79-TE-0332-CD01
4614 | Trace Heating | PS5-79-TE-0330-CD01
4615 | Trace Heating | PS5-79-TE-0269-CD01
4616 | Trace Heating | PS5-79-TE-0267-CD01
4617 | Trace Heating | PS5-79-TE-0268-CD01
4618 | Trace Heating | PS5-79-TE-0334-CD01
4619 | Trace Heating | PS5-79-TE-0333-CD01
4620 | Trace Heating | PS5-79-TE-0272-CD01
4621 | Trace Heating | PS5-79-TE-0270-CD01
4622 | Trace Heating | PS5-79-TE-0271-CD01
4623 | Trace Heating | PS5-79-TE-0335-CD01
4624 | Trace Heating | PS5-79-TE-0339-CD01
4625 | Trace Heating | PS5-79-TE-0275-CD01
4626 | Trace Heating | PS5-79-TE-0273-CD01
4627 | Trace Heating | PS5-79-TE-0274-CD01
4628 | Trace Heating | PS5-79-TE-0328-CD01
4629 | Trace Heating | PS5-79-TE-0061-CD01
4630 | Trace Heating | PS5-79-TE-0218-CD01
4631 | Trace Heating | PS5-79-TE-0229-CD01
4632 | Trace Heating | PS5-79-TE-0223-CD01
4633 | Trace Heating | PS5-79-TE-0224-CD01
4634 | Trace Heating | PS5-79-TE-0221-CD01
4635 | Trace Heating | PS5-79-TE-0235-CD01
4636 | Trace Heating | PS5-79-TE-0222-CD01
4637 | Trace Heating | PS5-79-TE-0350-CD01
4638 | Trace Heating | PS5-79-TE-0228-CD01
4639 | Trace Heating | PS5-79-TE-0236-CD01
4640 | Trace Heating | PS5-60-TE-0367-CD01
4641 | Trace Heating | PS5-79-TE-0136-CD01
4642 | Trace Heating | PS5-79-TE-0027-CD01
4643 | Trace Heating | PS5-79-TE-0039-CD01
4644 | Trace Heating | PS5-79-TE-0037-CD01
4645 | Trace Heating | PS5-79-TE-0025-CD01
4646 | Trace Heating | PS5-79-TE-0343-CD01
4647 | Trace Heating | PS5-79-TE-0118-CD01
4648 | Trace Heating | PS5-79-TE-0137-CD01
4649 | Trace Heating | PS5-79-TE-0024-CD01
4650 | Trace Heating | PS5-79-TE-0150-CD01
4651 | Trace Heating | PS5-79-TE-0203-CD01
4652 | Trace Heating | PS5-79-TE-0204-CD01
4653 | Trace Heating | PS5-79-TE-0262-CD01
4654 | Trace Heating | PS5-79-TE-0102-CD01
4655 | Trace Heating | PS5-79-TE-0081-CD01
4656 | Trace Heating | PS5-79-TE-0036-CD01
4657 | Trace Heating | PS5-79-TE-0066-CD01
4658 | Trace Heating | PS5-79-TE-0067-CD01
4659 | Trace Heating | PS5-79-TE-0245-CD01
4660 | Trace Heating | PS5-79-TE-0134-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4661 | Trace Heating | PS5-79-TE-0063-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4662 | Trace Heating | PS5-79-TE-0154-CD01
4663 | Trace Heating | PS5-79-TE-0319-CD01
4664 | Trace Heating | PS5-79-TE-0290-CD01
4665 | Trace Heating | PS5-79-TE-0152-CD01
4666 | Trace Heating | PS5-79-TE-0002-CD01
4667 | Trace Heating | PS5-79-TE-0005-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4668 | Trace Heating | PS5-79-TE-0146-CD01
4669 | Trace Heating | PS5-79-TE-0041-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4670 | Trace Heating | PS5-79-TE-0135-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4671 | Trace Heating | PS5-79-TE-0239-CD01
4672 | Trace Heating | PS5-79-TE-0247-CD01
4673 | Trace Heating | PS5-79-TE-0084-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150359 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0009)
4674 | Trace Heating | PS5-79-TE-0090-CD01
4675 | Trace Heating | PS5-79-TE-0085-CD01
4676 | Trace Heating | PS5-79-TE-0082-CD01
4677 | Trace Heating | PS5-79-TE-0101-CD01
4678 | Trace Heating | PS5-79-TE-0156-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4679 | Trace Heating | PS5-79-TE-0107-CD01
4680 | Trace Heating | PS5-79-TE-0020-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0281 | CPP-RFI-68-33/1-05-0281 |  | 2026-05-25 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing to be complete at both side; TZ-MID-68-NVS1-150360 Field run cable tray shall be install; TZ-MID-68-NVS1-150360 Cable trecnh backfilled to be done, protection tiles and warning tape installation at panel side (PS5-79-IG-0007)
4681 | Trace Heating | PS5-79-TE-0147-CD01
4682 | Trace Heating | PS5-79-TE-0043-CD01
4683 | Trace Heating | PS5-79-TE-0344-CD01
4684 | Trace Heating | PS5-79-TE-0019-CD01
4685 | Trace Heating | PS5-79-TE-0100-CD01
4686 | Trace Heating | PS5-79-TE-0112-CD01
4687 | Trace Heating | PS5-79-TE-0068-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4688 | Trace Heating | PS5-79-TE-0042-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4689 | Trace Heating | PS5-79-TE-0121-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4690 | Trace Heating | PS5-79-TE-0072-CD01
4691 | Trace Heating | PS5-79-TE-0116-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4692 | Trace Heating | PS5-79-TE-0145-CD01
4693 | Trace Heating | PS5-79-TE-0155-CD01
4694 | Trace Heating | PS5-79-TE-0071-CD01
4695 | Trace Heating | PS5-79-TE-0083-CD01
4696 | Trace Heating | PS5-79-TE-0291-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4697 | Trace Heating | PS5-79-TE-0003-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4698 | Trace Heating | PS5-79-TE-0143-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4699 | Trace Heating | PS5-79-TE-0059-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4700 | Trace Heating | PS5-79-TE-0006-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4701 | Trace Heating | PS5-79-TE-0144-CD01
4702 | Trace Heating | PS5-79-TE-0240-CD01 | [6 empty] | CPP-RFI-68-331-05-0315 | CPP-RFI-68-331-05-0315 |  | 2026-06-05 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable Tag to be installed at both side; TZ-MID-68-NVS1-150360 Cable to be dressing completely at both side; TZ-MID-68-NVS1-150360 Cable trench backfiled, protection tiles, and warning tape installation to be complete at EHT DB side (PS5-79-IG-0007)
4703 | Trace Heating | PS5-79-TE-0241-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
4704 | Trace Heating | PS5-79-TE-0208-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4705 | Trace Heating | PS5-79-TE-0292-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
4706 | Trace Heating | PS5-79-TE-0058-CD01
4707 | Trace Heating | PS5-79-TE-0140-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
4708 | Trace Heating | PS5-79-TE-0004-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
4709 | Trace Heating | PS5-79-TE-0007-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
4710 | Trace Heating | PS5-79-TE-0161-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4711 | Trace Heating | PS5-79-TE-0139-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
4712 | Trace Heating | PS5-79-TE-0162-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4713 | Trace Heating | PS5-79-TE-0074-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4714 | Trace Heating | PS5-79-TE-0142-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side; TZ-MID-68-NVS1-150360 Cable coiled around 10 meter at field side waiting for field run cable tray
4715 | Trace Heating | PS5-79-TE-0160-CD01
4716 | Trace Heating | PS5-79-TE-0077-CD01 | [6 empty] | CPP-RFI-68-331-05-0277 | CPP-RFI-68-331-05-0277 |  | 2026-05-23 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tag to be install at both side; TZ-MID-68-NVS1-150360 To be complete cable dressing at both side; TZ-MID-68-NVS1-150360 To be complete field run/secondary cable tray at field side; TZ-MID-68-NVS1-150360To be complete cable trench backfilled, protection tiles, and warning tape installation at cable trench DB panel side PS5-79-IG-0008
4717 | Trace Heating | PS5-79-TE-0075-CD01
4718 | Trace Heating | PS5-79-TE-0053-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4719 | Trace Heating | PS5-79-TE-0076-CD01
4720 | Trace Heating | PS5-79-TE-0070-CD01
4721 | Trace Heating | PS5-79-TE-0158-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4722 | Trace Heating | PS5-79-TE-0060-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4723 | Trace Heating | PS5-79-TE-0115-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4724 | Trace Heating | PS5-79-TE-0108-CD01
4725 | Trace Heating | PS5-79-TE-0111-CD01
4726 | Trace Heating | PS5-79-TE-0062-CD01
4727 | Trace Heating | PS5-79-TE-0141-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4728 | Trace Heating | PS5-79-TE-0207-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4729 | Trace Heating | PS5-79-TE-0205-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4730 | Trace Heating | PS5-79-TE-0044-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4731 | Trace Heating | PS5-79-TE-0045-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4732 | Trace Heating | PS5-79-TE-0261-CD01 | [6 empty] | CPP-RFI-68-33/1-05-0280 | CPP-RFI-68-33/1-05-0280 |  | 2026-05-24 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS Cable tag to be install; TZ-MID-68-NVS1-150360 Cable Dressing cable to be complete both side; TZ-MID-68-NVS1-150360 Trench backfilling,protection tiles & warning tape installation to be done at panel (side PS5-79-BE-0208); TZ-MID-68-NVS1-150360 Field run cable tray to be install at equipment side
4733 | Trace Heating | PS5-79-TE-0209-CD01
4734 | Trace Heating | PS5-79-TE-0064-CD01
4735 | Trace Heating | PS5-79-TE-0057-CD01
4736 | Trace Heating | PS5-79-TE-0021-CD01
4737 | Trace Heating | PS5-79-TE-0128-CD01
4738 | Trace Heating | PS5-79-TE-0008-CD01
4739 | Trace Heating | PS5-79-TE-0047-CD01
4740 | Trace Heating | PS5-79-TE-0052-CD01
4741 | Trace Heating | PS5-79-TE-0056-CD01
4742 | Trace Heating | PS5-79-TE-0055-CD01
4743 | Trace Heating | PS5-79-TE-0028-CD01
4744 | Trace Heating | PS5-79-TE-0294-CD01
4745 | Trace Heating | PS5-79-TE-0293-CD01
4746 | Trace Heating | PS5-79-TE-0129-CD01
4747 | Trace Heating | PS5-79-TE-0073-CD01
4748 | Trace Heating | PS5-79-TE-0010-CD01
4749 | Trace Heating | PS5-79-TE-0124-CD01
4750 | Trace Heating | PS5-79-TE-0295-CD01
4751 | Trace Heating | PS5-79-TE-0030-CD01
4752 | Trace Heating | PS5-79-TE-0127-CD01
4753 | Trace Heating | PS5-79-TE-0051-CD01
4754 | Trace Heating | PS5-79-TE-0032-CD01
4755 | Trace Heating | PS5-79-TE-0033-CD01
4756 | Trace Heating | PS5-79-TE-0126-CD01
4757 | Trace Heating | PS5-79-TE-0125-CD01
4758 | Trace Heating | PS5-79-TE-0011-CD01
4759 | Trace Heating | PS5-79-TE-0301-CD01
4760 | Trace Heating | PS5-79-TE-0001-CD01
4761 | Trace Heating | PS5-79-TE-0009-CD01
4762 | Trace Heating | PS5-79-TE-0014-CD01
4763 | Trace Heating | PS5-79-TE-0034-CD01
4764 | Trace Heating | PS5-79-TE-0353-CD01
4765 | Trace Heating | PS5-71-TE-0362-CD01
4766 | Trace Heating | PS5-79-TE-0132-CD01
4767 | Trace Heating | PS5-79-TE-0131-CD01
4768 | Trace Heating | PS5-79-TE-0040-CD01
4769 | Trace Heating | PS5-79-TE-0233-CD01
4770 | Trace Heating | PS5-79-TE-0054-CD01
4771 | Trace Heating | PS5-79-TE-0022-CD01
4772 | Trace Heating | PS5-79-TE-0078-CD01
4773 | Trace Heating | PS5-79-TE-0105-CD01
4774 | Trace Heating | PS5-79-TE-0029-CD01
4775 | Trace Heating | PS5-79-TE-0035-CD01
4776 | Trace Heating | PS5-79-TE-0094-CD01
4777 | Trace Heating | PS5-79-TE-0120-CD01
4778 | Trace Heating | PS5-79-TE-0095-CD01
4779 | Trace Heating | PS5-79-TE-0087-CD01
4780 | Trace Heating | PS5-79-TE-0119-CD01
4781 | Trace Heating | PS5-79-TE-0117-CD01
4782 | Trace Heating | PS5-79-TE-0323-CD01
4783 | Trace Heating | PS5-79-TE-0096-CD01
4784 | Trace Heating | PS5-79-TE-0079-CD01
4785 | Trace Heating | PS5-79-TE-0345-CD01
4786 | Trace Heating | PS5-79-TE-0104-CD01
4787 | Trace Heating | PS5-79-TE-0230-CD01
4788 | Trace Heating | PS5-79-TE-0093-CD01
4789 | Trace Heating | PS5-79-TE-0088-CD01
4790 | Trace Heating | PS5-79-TE-0089-CD01
4791 | Trace Heating | PS5-79-TE-0091-CD01
4792 | Trace Heating | PS5-79-TE-0097-CD01
4793 | Trace Heating | PS5-79-TE-0321-CD01
4794 | Trace Heating | PS5-79-TE-0227-CD01
4795 | Trace Heating | PS5-60-TE-0364-CD01
4796 | Trace Heating | PS5-79-TE-0286-CD01
4797 | Trace Heating | PS5-79-TE-0347-CD01
4798 | Trace Heating | PS5-79-TE-0289-CD01
4799 | Trace Heating | PS5-79-TE-0342-CD01
4800 | Trace Heating | PS5-79-TE-0232-CD01
4801 | Trace Heating | PS5-79-TE-0231-CD01
4802 | Trace Heating | PS5-79-TE-0288-CD01
4803 | Trace Heating | PS5-79-TE-0225-CD01
4804 | Trace Heating | PS5-79-TE-0324-CD01
4805 | Trace Heating | PS5-79-TE-0080-CD01
4806 | Trace Heating | PS5-79-TE-0065-CD01
4807 | Trace Heating | PS5-79-TE-0287-CD01
4808 | Trace Heating | PS5-79-TE-0277-CD01
4809 | Trace Heating | PS5-79-TE-0276-CD01
4810 | Trace Heating | PS5-79-TE-0226-CD01
4811 | Trace Heating | PS5-79-TE-0340-CD01
4812 | Trace Heating | PS5-79-TE-0336-CD01
4813 | Trace Heating | PS5-79-TE-0031-CD01
4814 | Trace Heating | PS5-79-TE-0016-CD01
4815 | Trace Heating | PS5-79-TE-0038-CD01
4816 | Trace Heating | PS5-79-TE-0341-CD01
4817 | Trace Heating | PS5-79-TE-0337-CD01
4818 | Trace Heating | PS5-79-TE-0050-CD01
4819 | Trace Heating | PS5-79-TE-0048-CD01
4820 | Trace Heating | PS5-79-TE-0069-CD01
4821 | Trace Heating | PS5-79-TE-0349-CD01
4822 | Trace Heating | PS5-79-TE-0338-CD01
4823 | Trace Heating | PS5-60-TE-0368-CD01
4824 | Trace Heating | PS5-60-TE-0369-CD01
4825 | Trace Heating | PS5-60-TE-0370-CD01
4826 | Trace Heating | PS5-79-TE-0251-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4827 | Trace Heating | PS5-79-TE-0297-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4828 | Trace Heating | PS5-79-TE-0296-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4829 | Trace Heating | PS5-79-TE-0012-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4830 | Trace Heating | PS5-79-TE-0259-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4831 | Trace Heating | PS5-79-TE-0257-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4832 | Trace Heating | PS5-79-TE-0258-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4833 | Trace Heating | PS5-79-TE-0098-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4834 | Trace Heating | PS5-79-TE-0300-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4835 | Trace Heating | PS5-79-TE-0123-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4836 | Trace Heating | PS5-79-TE-0248-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4837 | Trace Heating | PS5-79-TE-0254-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4838 | Trace Heating | PS5-79-TE-0310-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4839 | Trace Heating | PS5-79-TE-0263-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4840 | Trace Heating | PS5-79-TE-0122-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4841 | Trace Heating | PS5-79-TE-0110-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4842 | Trace Heating | PS5-79-TE-0256-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4843 | Trace Heating | PS5-79-TE-0320-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4844 | Trace Heating | PS5-79-TE-0255-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4845 | Trace Heating | PS5-79-TE-0017-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4846 | Trace Heating | PS5-79-TE-0250-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4847 | Trace Heating | PS5-79-TE-0249-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4848 | Trace Heating | PS5-79-TE-0318-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4849 | Trace Heating | PS5-79-TE-0299-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4850 | Trace Heating | PS5-79-TE-0308-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4851 | Trace Heating | PS5-79-TE-0013-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4852 | Trace Heating | PS5-79-TE-0015-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4853 | Trace Heating | PS5-79-TE-0133-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4854 | Trace Heating | PS5-79-TE-0298-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4855 | Trace Heating | PS5-79-TE-0026-CD01 | [6 empty] | CPP-RFI-68-331-05-0274 | CPP-RFI-68-331-05-0274 |  | 2026-05-22 00:00:00 | TZ-MID-68-NVS1-150360 Permanent SS tagging to be install at both side; TZ-MID-68-NVS1-150360 Cable dressing to be done at both side; TZ-MID-68-NVS1-150360 Cable trench PS5-88-BU-LV-00102 to be done protection tiles, warning tape , and backfilled at panel side PS5-79-IG-0012.
4856 | Trace Heating | PS5-79-TE-0138-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side; TZ-MID-68-NVS1-150360 Field Run Cable Tray to be installed
4857 | Trace Heating | PS5-25-TE-0364-CD01 | [6 empty] | CPP-RFI-68-331-05-0370 | CPP-RFI-68-331-05-0370 |  | 2026-06-20 00:00:00 | TZ-MID-68-NVS1-150360 Cable Dressing to complete at both side
4858 | Trace Heating | PS5-79-BE-0175-CW01
4859 | Trace Heating | PS5-79-IP-9101-CW01
4860 | Trace Heating | PS5-79-IP-9102-CW01
4861 | Trace Heating | PS5-79-BE-0176-CW01
4862 | Trace Heating | PS5-79-IP-9103-CW01
4863 | Trace Heating | PS5-79-IP-9104-CW01
4864 | Trace Heating | PS5-79-BE-0177-CW01
4865 | Trace Heating | PS5-79-IP-9105-CW01
4866 | Trace Heating | PS5-79-IP-9106-CW01
4867 | Trace Heating | PS5-79-TE-0175-CD01
4868 | Trace Heating | PS5-79-TE-0176-CD01
4869 | Trace Heating | PS5-79-TE-0178-CD01
4870 | Trace Heating | PS5-79-TE-0177-CD01

## SIDMAP (hidden)
PS5-01-01 - Fire Water Jockey Pump A/B | PS5-01-01
PS5-01-02 - Fire Water Pump A | PS5-01-02
PS5-01-03 - Fire Water Pump B | PS5-01-03
PS5-01-04 - Fire Water Pump Mini Flow Recycle | PS5-01-04
PS5-01-05 - Foam Skid | PS5-01-05
PS5-01-06 - Foam Concentrate Distribution | PS5-01-06
PS5-01-07 - Fire Water Ring Main & Distribution | PS5-01-07
PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | PS5-01-08
PS5-01-09 - Inergen for EITS Building | PS5-01-09
PS5-01-10 - Water Mist Package | PS5-01-10
PS5-01-11 - Inergen for Power Gen Building | PS5-01-11
PS5-02-01 - Miscellaneous Safety equipment | PS5-02-01
PS5-02-02 - Portable Fire Fighting Equipments | PS5-02-02
PS5-03-01 - FZ-01 - Process Area | PS5-03-01
PS5-03-03 - FZ-03 - Buildings Area | PS5-03-03
PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | PS5-03-04
PS5-03-06 - FZ-06 - Transformer Area | PS5-03-06
PS5-03-07 - FZ-07 - Pretreatment Area | PS5-03-07
PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08
PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | PS5-03-09
PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | PS5-03-10
PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | PS5-03-11
PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | PS5-03-12
PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | PS5-03-13
PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | PS5-03-14
PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | PS5-03-15
PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | PS5-03-16
PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | PS5-03-17
PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | PS5-03-18
PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | PS5-03-19
PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | PS5-03-20
PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | PS5-03-21
PS5-03-22 - FZ-G1 - Guard House | PS5-03-22
PS5-03-23 - FZ-E1 to E3 - EITS Building | PS5-03-23
PS5-03-24 - FZ - Office and Facilities Building | PS5-03-24
PS5-03-25 - FZ - Workshop & Warehouse | PS5-03-25
PS5-04-01 - Office Building PCS System | PS5-04-01
PS5-04-02 - Office Building SIS/FGS System | PS5-04-02
PS5-04-03 - 33kV ICSS System | PS5-04-03
PS5-04-04 - 33kV PCS System | PS5-04-04
PS5-04-05 - 33kV SIS/FGS System | PS5-04-05
PS5-05-01 - Emergency Diesel Generator Package | PS5-05-01
PS5-05-02 - Emergency Diesel Generator Package (UCP) | PS5-05-02
PS5-06-01 - AC UPS - EITS Building | PS5-06-01
PS5-06-02 - AC UPS - Power Generator Building | PS5-06-02
PS5-06-03 - AC UPS - Office & Facilities Building | PS5-06-03
PS5-06-04 - AC UPS - Guard House | PS5-06-04
PS5-06-05 - AC UPS - Workshop & Warehouse | PS5-06-05
PS5-08-01 | PS5-08-01
PS5-08-01a - PAGA (Required for SU) | PS5-08-01a
PS5-08-01b - PAGA (Not required for SU) | PS5-08-01b
PS5-08-03 - Telephone | PS5-08-03
PS5-08-04 - Hotline | PS5-08-04
PS5-08-07 - Multi-Channel Voice Recorder | PS5-08-07
PS5-08-11 - Corporate LAN (SIE) | PS5-08-11
PS5-08-12 - Corporate Wireless LAN (SIE) | PS5-08-12
PS5-08-13 - Safety Data Network (SII SP3 SAF) | PS5-08-13
PS5-08-14 - Industrial Data Network (SII SP1) | PS5-08-14
PS5-08-15 - Security Data Network (SII SP3 SEC) | PS5-08-15
PS5-08-23 - VHF Trunk Radio System | PS5-08-23
PS5-08-34 - Satphone | PS5-08-34
PS5-08-35 - Optical Transport Network | PS5-08-35
PS5-08-36 - Pipeline FO Cable & EPRS | PS5-08-36
PS5-08-51 - Entertainment | PS5-08-51
PS5-08-52a - Process & Security CCTV (Required for SU) | PS5-08-52a
PS5-08-52b - Process & Security CCTV (Not required for SU) | PS5-08-52b
PS5-08-55 - Videoconference | PS5-08-55
PS5-08-61 - Meteocean | PS5-08-61
PS5-08-71 - Structured Cabling (CAT6) | PS5-08-71
PS5-08-72 - Structured Cabling (FO) | PS5-08-72
PS5-08-81 - Guard tour | PS5-08-81
PS5-08-82 - Key Management | PS5-08-82
PS5-08-83 - Perimeter & Pipeline intrusion detection system | PS5-08-83
PS5-08-85 | PS5-08-85
PS5-08-85a - Access Control, POB & e-Mustering (Required for SU) | PS5-08-85a
PS5-08-85b - Access Control, POB & e-Mustering (Not required for SU) | PS5-08-85b
PS5-08-86 - Integrated Security Management System | PS5-08-86
PS5-08-92 - Telecom Mast | PS5-08-92
PS5-08-93 - Telecom Monitoring System | PS5-08-93
PS5-09-01 - HVAC for Office and Facilities building | PS5-09-01
PS5-09-02 - HVAC for Guard House | PS5-09-02
PS5-09-03 - HVAC for Generator Building | PS5-09-03
PS5-09-04 - HVAC for Workshop & Warehouse | PS5-09-04
PS5-09-05 - HVAC for EITS Building | PS5-09-05
PS5-0H-01 - HIPPS | PS5-0H-01
PS5-25-01 - Export Pipeline Pig Receiver | PS5-25-01
PS5-25-02 - Crude Oil Export Pump A | PS5-25-02
PS5-25-03 - Crude Oil Export Pump B | PS5-25-03
PS5-25-04 - Crude Oil Export Pump C | PS5-25-04
PS5-25-05 - Crude Oil Export Pumps Bypass | PS5-25-05
PS5-25-06 - Crude Oil Export Pumps Discharge | PS5-25-06
PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07
PS5-28-01 - Closed Drain Header 1 | PS5-28-01
PS5-28-02 - Closed Drain Header 2 | PS5-28-02
PS5-28-03 - Closed Drain Drum and Pump 01 | PS5-28-03
PS5-28-04 - Closed Drain Drum and Pump 02 | PS5-28-04
PS5-28-05 - HP Relief Header | PS5-28-05
PS5-28-06 - Relief Drum and Pump | PS5-28-06
PS5-28-07 - Open Drains (OD2) | PS5-28-07
PS5-28-08 - Open Drain Sump and Pumps | PS5-28-08
PS5-28-09 - Observation Basin | PS5-28-09
PS5-28-10 - Oil Skimmer Package | PS5-28-10
PS5-28-11 - Open Drain Interceptor | PS5-28-11
PS5-28-12 - Open Drains (OD3) | PS5-28-12
PS5-28-13 - Seal Oil Drain Drum & Pump A | PS5-28-13
PS5-28-14 - Seal Oil Drain Drum & Pump B | PS5-28-14
PS5-28-15 - Seal Oil Drain Drum & Pump C | PS5-28-15
PS5-28-16 - LP Relief Header | PS5-28-16
PS5-28-17 - Reinjection Pump | PS5-28-17
PS5-50-01 - Water Well Submersible Pumps (3100) | PS5-50-01
PS5-50-02 - Water Well Submersible Pumps (3200) | PS5-50-02
PS5-50-03 - Water Pre-Treatment Package | PS5-50-03
PS5-53-01 - Utility Water / Storage Tank | PS5-53-01
PS5-53-02 - Water Distribution Pump A/B | PS5-53-02
PS5-53-03 - Water Softener Package | PS5-53-03
PS5-53-04 - Water Treatment Purification Package | PS5-53-04
PS5-53-05 - Water Distribution Header | PS5-53-05
PS5-53-06 - Water Distribution Consumers | PS5-53-06
PS5-60-01 - Power Generation Package A | PS5-60-01
PS5-60-02 - Power Gen Package A (UCP) | PS5-60-02
PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | PS5-60-03
PS5-60-04 - Power Generation Package B | PS5-60-04
PS5-60-05 - Power Gen Package B (UCP) | PS5-60-05
PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | PS5-60-06
PS5-60-07 - Power Generation Package C | PS5-60-07
PS5-60-08 - Power Gen Package C (UCP) | PS5-60-08
PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | PS5-60-09
PS5-60-10 - Power Generation Package D | PS5-60-10
PS5-60-11 - Power Gen Package D (UCP) | PS5-60-11
PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | PS5-60-12
PS5-60-13 - Power Generation Package E | PS5-60-13
PS5-60-14 - Power Gen Package E (UCP) | PS5-60-14
PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | PS5-60-15
PS5-60-16 - Power Generation Package F | PS5-60-16
PS5-60-17 - Power Gen Package F (UCP) | PS5-60-17
PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | PS5-60-18
PS5-60-19 - Power Generation Package G | PS5-60-19
PS5-60-20 - Power Gen Package G (UCP) | PS5-60-20
PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | PS5-60-21
PS5-60-22 - Power Gen Master UCP | PS5-60-22
PS5-60-23 - Instrument Air Distribution lines | PS5-60-23
PS5-60-24 - Cooling Water Tank & Pump | PS5-60-24
PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | PS5-60-25
PS5-60-26 - Instrument Air Compressor Skid | PS5-60-26
PS5-60-27 - Compressed Air Starting Skid | PS5-60-27
PS5-60-28 - Air Receiver A & Air Regulator A | PS5-60-28
PS5-60-29 - Air Receiver B & Air Regulator B | PS5-60-29
PS5-60-30 - Air Receiver C & Air Regulator C | PS5-60-30
PS5-60-31 - Air Receiver D & Air Regulator D | PS5-60-31
PS5-60-32 - Air Receiver E & Air Regulator E | PS5-60-32
PS5-60-33 - Air Receiver F & Air Regulator F | PS5-60-33
PS5-60-34 - Air Receiver G & Air Regulator G | PS5-60-34
PS5-60-35 - Injector Tip Cooling Module A | PS5-60-35
PS5-60-36 - Injector Tip Cooling Module B | PS5-60-36
PS5-60-37 - Injector Tip Cooling Module C | PS5-60-37
PS5-60-38 - Injector Tip Cooling Module D | PS5-60-38
PS5-60-39 - Injector Tip Cooling Module E | PS5-60-39
PS5-60-40 - Injector Tip Cooling Module F | PS5-60-40
PS5-60-41 - Injector Tip Cooling Module G | PS5-60-41
PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | PS5-60-42
PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | PS5-60-43
PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | PS5-60-44
PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | PS5-60-45
PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | PS5-60-46
PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | PS5-60-47
PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | PS5-60-48
PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | PS5-60-49
PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | PS5-60-50
PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | PS5-60-51
PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | PS5-60-52
PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | PS5-60-53
PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | PS5-60-54
PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | PS5-60-55
PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | PS5-60-56
PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | PS5-60-57
PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | PS5-60-58
PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | PS5-60-59
PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | PS5-60-60
PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | PS5-60-61
PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | PS5-60-62
PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | PS5-60-63
PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | PS5-60-64
PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | PS5-60-65
PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | PS5-60-66
PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | PS5-60-67
PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | PS5-60-68
PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | PS5-60-69
PS5-60-70 - Engine A Cooling system | PS5-60-70
PS5-60-71 - Engine B Cooling system | PS5-60-71
PS5-60-72 - Engine C Cooling system | PS5-60-72
PS5-60-73 - Engine D Cooling system | PS5-60-73
PS5-60-74 - Engine E Cooling system | PS5-60-74
PS5-60-75 - Engine F Cooling system | PS5-60-75
PS5-60-76 - Engine G Cooling system | PS5-60-76
PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | PS5-61-01
PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | PS5-61-02
PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | PS5-61-03
PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | PS5-61-04
PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | PS5-61-05
PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | PS5-61-06
PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | PS5-61-07
PS5-61-08 - Electrical Control System | PS5-61-08
PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | PS5-61-09
PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | PS5-61-10
PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | PS5-61-11
PS5-61-12 - EITS 33kV Bld. Normal Auxiliary DP - PS5-61-IG-0008 | PS5-61-12
PS5-61-13 - Power Distribution Board Office Building - PS5-61-IG-0020 | PS5-61-13
PS5-61-14 - Power Distribution Board Workshop & Warehouse - PS5-61-IG-0009 | PS5-61-14
PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | PS5-62-01
PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | PS5-62-02
PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | PS5-62-03
PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | PS5-62-04
PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | PS5-62-05
PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | PS5-62-06
PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | PS5-62-07
PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | PS5-62-08
PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | PS5-62-09
PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | PS5-62-10
PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | PS5-62-11
PS5-62-12 - EITS 33kV Bld. Emergency L&SP DP - PS5-05-IG-0003 | PS5-62-12
PS5-62-13 - EITS 33kV Bld. Normal L&SP DP - PS5-61-IG-0003 | PS5-62-13
PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | PS5-62-14
PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | PS5-62-15
PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | PS5-62-16
PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | PS5-62-17
PS5-62-18 - Workshop & Warehouse Normal L&SP DB - PS5-61-IG-0004 | PS5-62-18
PS5-62-19 - Workshop & Warehouse Emergency L&SP DB - PS5-05-IG-0101 | PS5-62-19
PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | PS5-62-20
PS5-63-01 - Electrical Earthing | PS5-63-01
PS5-63-02 - Electrical Earthing - Office and Facilities building | PS5-63-02
PS5-63-03 - Electrical Earthing - Generator Building | PS5-63-03
PS5-63-04 - Electrical Earthing - EITS Building | PS5-63-04
PS5-63-05 - Electrical Earthing - Guard Hut A & B | PS5-63-05
PS5-63-06 - Electrical Earthing - Guard House | PS5-63-06
PS5-63-07 - Electrical Earthing - Workshop & Warehouse | PS5-63-07
PS5-71-01 - CFO Storage Tank Feed Heater | PS5-71-01
PS5-71-02 - CFO Allocation Metering Package | PS5-71-02
PS5-71-03 - CFO Allocation Metering Package (UCP) | PS5-71-03
PS5-71-04 - CFO Storage Tank | PS5-71-04
PS5-71-05 - CFO Transfer Pump A/B | PS5-71-05
PS5-71-06 - Crude Fuel Separation Module | PS5-71-06
PS5-71-07 - Crude Fuel Separation Module (UCP) | PS5-71-07
PS5-71-08 - CFO Pre-Pressure Modules | PS5-71-08
PS5-71-09 - CFO Pre-Pressure Modules (UCP) | PS5-71-09
PS5-71-12 - CFO Service Tank | PS5-71-12
PS5-71-13 - CFO Service Pump A/B | PS5-71-13
PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | PS5-71-14
PS5-71-15 - Diesel Fuel Storage Tank | PS5-71-15
PS5-71-16 - Diesel Fuel Supply Pump A/B | PS5-71-16
PS5-71-17 - Diesel Fuel Distribution Header | PS5-71-17
PS5-71-18 - Diesel Separator Module | PS5-71-18
PS5-71-19 - Diesel Separator Module (UCP) | PS5-71-19
PS5-71-20 - Diesel Fuel Day Tank | PS5-71-20
PS5-71-21 - Diesel Transfer Pump A/B | PS5-71-21
PS5-71-22 - Diesel Fuel Pre Pressure Module | PS5-71-22
PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | PS5-71-23
PS5-74-01 - N2 Generation Skid | PS5-74-01
PS5-74-02 - N2 Generation Skid (UCP) | PS5-74-02
PS5-74-03 - Nitrogen Receiver | PS5-74-03
PS5-74-04 - Nitrogen Distribution Header | PS5-74-04
PS5-75-01 - DRA Injection Package | PS5-75-01
PS5-75-02 - Biocide Injection Package | PS5-75-02
PS5-75-03 - Corrosion Inhibitor Injection Package | PS5-75-03
PS5-78-01 - Lifting and handling equipment | PS5-78-01
PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | PS5-79-01
PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | PS5-79-02
PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | PS5-79-03
PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | PS5-79-04
PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | PS5-79-05
PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | PS5-79-06
PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | PS5-79-07
PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | PS5-79-08
PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | PS5-79-09
PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | PS5-79-10
PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | PS5-79-11
PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | PS5-79-12
PS5-82-01 - Sanitary Sewage Collection | PS5-82-01
PS5-82-02 - Sewage Treatment Plant Package | PS5-82-02
PS5-82-03 - Sewage Treatment Plant Package (UCP) | PS5-82-03
PS5-82-04 - Sewage Treatment Plant Discharge Piping | PS5-82-04
PS5-82-05 - Office and Facilities building | PS5-82-05
PS5-82-06 - Guard House Building | PS5-82-06
PS5-82-07 - Guard Huts | PS5-82-07
PS5-83-01 - EITS Building | PS5-83-01
PS5-84-01 - Generator Building | PS5-84-01
PS5-84-02 - Workshop & Warehouse | PS5-84-02
PS5-84-03 - Shelters | PS5-84-03
PS5-86-01 - Shelters | PS5-86-01
PS5-91-01 - Multicore cables & JB | PS5-91-01
PS5-99-01 - Area Completion for Building area | PS5-99-01
PS5-99-02 - Area Completion for Utility area | PS5-99-02
PS5-99-03 - Area Completion for Power Distribution area | PS5-99-03
PS5-99-04 - Area Completion for Process area | PS5-99-04
PS5-99-05 - Area Completion for CFO area | PS5-99-05
PS5-99-06 - Area Completion for Power Generation area | PS5-99-06